## Referance (hidden)
Activity Type | Node Name | Status | Owner | Team
New Product Validation | ACI | In Progress | Abhijeet | IPSE
Pluggables Testing | NXOS | Completed | Shweta | IPSE
Regression Testing | DCNM | Yet to start | Gurkirat | IPSE
MoP Validation | NDO | On Hold | Konda | IPSE
Solution Testing | CGNAT |  | Sairam | IPSE
Feature Testing | CPNR |  | Kazi | Telco
Provisioning and Configuration | CLMS |  | Sumit | Telco
Issue Analysis & Testing | TWAMP |  | Neelmani | Telco
Infosec Testing | Splunk |  | Dilpreet | Telco
Audit and Analysis | DNS |  | Ronak | Telco
Support Activity | SSM
Documentation | ISE
ATP 1A | Arbor
ATP 1B | CGNAT LC
Other | Telemetry
Release Testing | DCNM/NXOS
Lab Troubleshooting | ACI/NXOS
Production Troubleshooting | RST
Other Domain

## Gurkirat
| Completed | In Progress | On Hold | Total
| 148 | 7 | 13 | 168
SN | Activity ID | Activity | Node Name | Activity Type | Status | Start date | End Date | Duration | 45302 | 45303 | 45306 | 45307 | 45308 | 45309 | 45310 | 45314 | 45315 | 45316 | 45320 | 45321 | 45322 | 45323 | 45324 | 45327 | 45328 | 45329 | 45330 | 45331 | 45334 | 45335 | 45336 | 45337 | 45338 | 45341 | 45342 | 45343 | On leave upto 17th March 2024 | 45369 | 45370 | 45371 | 45372 | 45373 | 45377 | 45378 | 45379 | 45380 | 45383 | 45384 | 45385 | 45386 | 45387 | 45390 | 45391 | 45392 | 45393 | 45394 | 45397 | 45398 | 45399 | 45400 | 45401 | 45404 | 45405 | 45406 | 45407 | 45412 | 45414 | 45415 | 45418 | 45419 | 45420 | 45421 | 45422 | 45425 | 45426 | 45427 | 45428 | 45429 | 45433 | 45434 | 45435 | 45436 | 45439 | 45440 | 45441 | 45442 | 45443 | 45446 | 45447 | 45448 | 45449 | 45450 | 45454 | 45455 | 45456 | 45457 | 45460 | 45461 | 45462 | 45463 | 45464 | 45467 | 45468 | 45469 | 45470 | 45471 | 45474 | 45475 | 45476 | 45477 | 45478 | 45481 | 45482 | 45483 | 45484 | 45488 | 45489 | 45490 | 45491 | 45492 | 45510 | 45511 | 45512 | 45513 | 45516 | 45517 | 45518 | 45520 | 45523 | 45524 | 45525 | 45526 | 45527 | 45530 | 45531 | 45532 | 45533 | 45534 | 45537 | 45538 | 45539 | 45540 | 45541 | 45544 | 45545 | 45546 | 45547 | 45548 | 45551 | 45552 | 45553 | 45554 | 45558 | 45559 | 45560 | 45561 | 45562 | 2024-09-30 | 45566 | 45568 | 45572 | 45573 | 45574 | 45575 | 2024-10-11 | 2024-10-14 | 2024-10-15 | 2024-10-16 | 2024-10-17 | 2024-10-18 | 2024-10-19 | 2024-10-21 | 2024-10-22 | 2024-10-23 | 2024-10-25 | 2024-12-05 | 2024-12-16 | 2024-12-18 | 2024-12-19 | 2024-12-23 | 2024-12-30 | 2025-01-02 | 2025-01-03 | 2025-01-06 | 2025-01-09 | 2025-01-10 | 2025-01-14 | 2025-01-15 | 2025-01-16 | 2025-01-17 | 2025-01-20 | 2025-01-21 | 2025-01-22 | 2025-01-23 | 2025-01-24 | 2025-01-27 | 2025-01-28 | 2025-01-30 | 2025-02-03 | 2025-02-04 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-10 | 2025-02-11 | 2025-02-12 | 2025-02-14 | 2025-02-17 | 2025-02-18 | 2025-02-19 | 2025-02-20 | 2025-02-21 | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | ON LEAVE | 2025-04-03 | 2025-04-04 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11
1 | 11-01-24-33 | CGNAT integration with Jio IPM | CGNAT | Solution Testing | Completed | 2024-01-11 | 2024-01-12 | 2 | Yes | Yes
2 | 15-01-24-34 | Provisioning and validation of Syslog-ng log collector as RST solution. | CLMS | Provisioning and Configuration | Completed | 2024-01-15 | 2024-04-08 | 31 |  |  | Yes | Yes | Yes | [5 empty] | Yes |  | Yes | Yes |  | HA configuration for syslogNG CLMS has been done. |  |  | HA alarm configuration has been completed. | Requested for all required scripts for completing the syslogNG deployment in the replica lab. |  | SyslogNG scripts imported pcs config updated syslogNG latest rpm file downloaded and installed. | Provisioned scripts provided. Watchqueue, crontab setup. Issue - sqlite3 package not available. | Sqlite3 installed. Troubleshooted issue in watchqueue. Vendor not available in second half | Sqlite3 installed. Troubleshooted issue in watchqueue. Vendor not available in second half | Discussed with Suresh to provide all updated script and TLS config for HA |  |  |  | 45369: Gone through some of completed testcases.; 45370: Done config for raw data writing on seperate file for IPv4 and IPv6 server. Checking data forwarding rules.; 45371: IPv4 logs forwarding to IPv4 destination and IPv6 logs forwarding to IPv6 destination. -> Completed. IPv4 and IPv6 logs forwarding via VIPv6 -> Completed. Some watchqueue values are not getting populated -> Completed.; 45372: Open issue: HA VIP reverting to original host after restart. --> Working VIP for IPv4 not forwarding logs, logs going via RST1 interface IP. Syslog-alarms.sh script error on RST2. --> Working VIP not moving to secondary server after stopping syslog-ng service. "EPS - PREVIOUS DAY REPORT" values not showing.; 45373: shared testing status on mail; 45377: Troubleshooting issues in hamon and syslogmon scripts for VIP migration upon down syslog-ng service. Troubleshooted physical interface not preferred over VIP for log forwarding.; 45378: Troubleshooting issues in hamon and syslogmon scripts for VIP migration upon down syslog-ng service. Troubleshooted physical interface not preferred over VIP for log forwarding.; 45379: Updated results for exisiting test cases.; 45380: Buffer logs count configuration done and tested today. --> Working (Need to copy config on RST2 as well) HA alert testing --> pending; 45384: Buffer logs count configuration done and tested today. --> Working (Need to copy config on RST2 as well) HA alert testing --> pending Rest is completed.; 45385: HA alert testing : Alert being generated for VIP movement. --> working Syslog-ng team to check if we can customize alert format . --> need to with NPE Destination IP need to be specified using pcs command separately. --> need to check with NPE pcs cluster stop/start logs are not specific. --> need to confirm if these are usable or not.; 45386: buffer logs are not deleting even after buffer is cleared; 45387: new script added for buffer clearing; 45390: CLM ID 1358265 released; 45391: discussion on buffer log deletion via script.; 45397: Update syslog.pl script to remove alarm on buffer creation updated watchqueue script to not display buffer disk utilization and buffer file size, to avoid any confusion with actual buffer size.; 45398: Created MOP for configuring new VM using OVF .
3 | 15-01-24-35 | ISE integration of RAD MDS ETX-2i-10G-B-8SFPP | ISE | Provisioning and Configuration | Completed | 2024-01-15 | 2024-01-15 | 1 |  |  | Yes
4 | 15-01-24-36 | A10 TH7440-11 CGNAT config for IPV6 IPDR solution for wireline. | CGNAT | Provisioning and Configuration | Completed | 2024-01-15 | 2024-02-09 | 14 |  |  | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  |  |  | CLM ID: 1356361 released | [9 empty] | 2024-10-16: 2023-08-23
5 | 15-01-24-37 | Syslog-NG as CLMS TLS cofiguration. | CLMS | Provisioning and Configuration | Completed | 2024-01-15 | 2024-01-15 | 1 |  |  | Yes
6 | 17-01-24-38 | CGNAT configuration for FTTx NAT64 solution | CGNAT | Provisioning and Configuration | Completed | 2024-01-17 | 2024-01-17 | 1 |  |  |  |  | Yes
7 | 15-01-24-39 | One-NDS CA certificate issue with Tibco CLMS | CLMS | Troubleshooting | Completed | 2024-01-15 |  | 1 |  |  | Yes
8 | 18-01-24-40 | Cisco ACI APIC V-5.2(8d) ¦¦ Audit & Sys logs format validation | CLMS | Audit and Analysis | Completed | 2024-01-18 | 2024-02-14 | 6 | [5 empty] | Yes | Yes | [12 empty] | Was ON HOLD | Supported with ISE log forwarding and collection at syslog |  | Collected required logs by taking tcpdump | Collected required logs by taking tcpdump
9 | 18-01-24-41 | Troubleshooting BGLRRLB1EDS006 login issue | ISE | Troubleshooting | Completed | 2024-01-18 | 2024-02-23 | 3 | [5 empty] | Yes | Yes | Yes
10 | 23-01-24-42 | ISE configuration for specific access to IP MPLS nodes | ISE | Provisioning and Configuration | Completed | 2024-01-23 | 2024-02-19 | 4 | [7 empty] | Yes | [15 empty] | Re-enabled profile. Troubleshooting issues with users | Troubleshooting done for multiple users | Updated profiles ,new groups ,new profile , new access given, Troubleshooting done for multiple users
11 | 30-01-24-43 | CGNAT configuration for new Jio internal BNG UP solution | CGNAT | Provisioning and Configuration | Completed | 2024-01-30 |  | 1 | [11 empty] | Yes
12 | 30-01-24-44 | CLMS log validation for Techroute S2928F-I firmware 120348 | CLMS | Troubleshooting | Completed | 2024-01-30 |  | 1 | [11 empty] | Yes
13 | 30-01-24-45 | ISE user confirmation for Techroute S2928F-I firmware 120348 | ISE | Troubleshooting | Completed | 2024-01-30 |  | 1 | [11 empty] | Yes
14 | 29-01-24-46 | TACACS and CLMS validation for ACI inband testing. | ISE | Solution Testing | Completed | 2024-01-29 |  | 1 | [10 empty] | Yes
15 | 30-01-24-68 | DNS configuration for clickstream.jio.com and myjio-gateway.jio.com | DNS | Provisioning and Configuration | Completed | 2024-01-30 | 2024-01-30 | 1 | [11 empty] | Yes
16 | 31-01-24-69 | ISE Configuration for admin access to Alok4 Pandey for Infosec scanning. | ISE | Provisioning and Configuration | Completed | 2024-01-31 | 2024-01-31 | 1 | [12 empty] | Yes
17 | 02-02-24-70 | Troubleshooting ISE login issue for Geniel1 and Geniel3 users. | ISE | Lab Troubleshooting | Completed | 2024-02-02 | 2024-02-02 | 1 | [14 empty] | Yes
18 | 02-02-24-71 | A10 TH7440-11 CGNAT UE pool configuration for BNG airfiber solution. | CGNAT | Provisioning and Configuration | Completed | 2024-02-02 | 2024-02-02 | 1 | [14 empty] | Yes
19 | 06-02-24-81 | Knowledge transfer for CGNAT SRIOV functionality. | CGNAT | Support Activity | Completed | 2024-02-06 | 2024-02-06 | 1 | [16 empty] | Knowledge transferred successfully.
20 | 06-02-24-82 | A10 VNF for IPDR solution SRIOV configuration. | CGNAT | Provisioning and Configuration | Completed | 2024-02-06 | 2024-02-06 | 1 | [16 empty] | SRIOV configuration and VM management config done
21 | 07-02-24-85 | CGNAT configuration for tracking CGNAT IN for BNG Airfiber | CGNAT | Provisioning and Configuration | Completed | 2024-02-07 | 2024-02-07 | 2 | Gurkirat | [16 empty] | Reverse route added for IAG loopback IP.
22 | 07-02-24-86 | Troubleshooting BGLRRLABESR033 login issue. | ISE | Lab Troubleshooting | On Hold | 2024-02-07 |  | 1 | [17 empty] | Device is not forwarding request to ISE. Need device team need to verfiy there device config
23 | 07-02-24-87 | Validation of A10 TH7440-11 upgrade from version 4_1_4-GR1-P5 to version 5_2_1-P9 | CGNAT | Release Testing | Completed | 2024-02-07 | 2024-02-14 | 3 | [17 empty] | After upgrade observations have been made and shared on mail. SFP verifed and observation verified by jack in out the SFP. |  |  |  | Support provided with regression test cases | CLM ID:1356381 A10 CGNAT TH-7440-11-5.2.1.P9
24 | 07-02-24-88 | A10 TH7440-11 CGNAT UE pool configuration for BNG airfiber solution. | CGNAT | Provisioning and Configuration | Completed | 2024-02-07 | 2024-02-07 | 1 | [17 empty] | 2405:200:1412:c350::/61 2405:200:1412:c338::/62 config done for above pool.
25 | 17-01-24-55 | Create new VM for F5 and A10 for IPDR testing | CGNAT | Solution Testing | Completed | 2024-01-17 | 2024-02-06 | 2 | [18 empty] | Done running configuration for IPDR |  |  |  |  | Discussion on how to migrate traffic to A10 VNF with Sumit sir and swati mam and sent mail for it
26 | 09-02-24-89 | Support provided for Dlink image upgrade | ISE | Support Activity | Completed | 2024-02-09 | 2024-02-09 | 1 | [19 empty] | Setup TFTP server for upgrade.
27 | 09-02-24-90 | ISE and syslog support for TR-2506 Infosec open points | CLMS | Audit and Analysis | On Hold | 2024-02-09 |  | 2 | [19 empty] | checked critical NC points 1) Password is getting printed in plain text in the log line. 2) Source IP missing for all test cases. | Shared ISE end observations on mail. 1. The device port provided by the device is listed as 'NotDefined' for all AAA logs. 2. Remote Address is absent in all AAA logs. 3. Passwords can be seen in plain text in Authorization and command accounting logs.
28 | 13-02-24-96 | ISE validation for Dlink HUB and SPOKE with upgraded firmware Build 11377 | ISE | Audit and Analysis | Completed | 2024-02-13 | 2024-02-13 | 2 | Gurkirat | [20 empty] | Generated AAA logs from HUB and SPOKE and shared updated observation after firware upgrade. 1. The device port value appears as 'port=Unknown' for authentication and shell profile authorization logs. 2. The remote address field displays an incomplete IPv6 address for authentication and shell profile authorization logs.
29 | 13-02-24-97 | IPDR FTTX Design for Netflow // CGNAT Failure | CGNAT | Feature Testing | On Hold | 2024-02-13 |  | 2 | Gurkirat | [20 empty] | Discussion on CGNAT/BL/IAG failover scenerio.
30 | 14-02-24-99 | Troubleshooting ESXi reachability issue. | CGNAT LC | Lab Troubleshooting | Completed | 2024-02-14 | 2024-02-14 | 1 | [22 empty] | Cable patched out at leaf end
31 | 15-02-24-104 | Troubleshooting A10 IPDR gateway not reachable issue | CGNAT | Lab Troubleshooting | Completed | 2024-02-15 | 2024-02-15 | 1 | [23 empty] | i40en ESXi config updated. Need to check config at ACI end.
32 | 16-02-24-114 | CGNAT config for subscriber pool for new OLT | CGNAT | Provisioning and Configuration | Completed | 2024-02-16 | 2024-02-16 | 1 | [24 empty] | Pool allowed and reverse route added at CGNAT
33 | 19-02-24-115 | Support provided for NTP sync testing for APIC 5.3.2a | CGNAT | Support Activity | Completed | 2024-02-19 | 2024-02-21 | 3 | [25 empty] | Supported aci team with NTP testing using F5 appliance and F5 VNF. | Supported aci team with NTP testing using F5 appliance and F5 VNF. | Validated NTP sync with Management gateway IP
34 | 28-03-2024-192 | F5 VNF deployement and provisioning for IPDR testing | CGNAT | New Product Validation | Completed | 2024-02-19 | 2024-04-16 | 7 | [25 empty] | VM deployement done. Troubleshooting | License installed successfully. Trunk, vlan, self IP config done.working on profiles | Requested updated MOP |  | 45373: follow up done in mail; 45385: Configuration done on F5 VNF MUM along with Vendor. Requested vendor to share updated MOP on mail.; 45386: ACI reachability done; 45398: F5 VNF logging troubleshooting. Reverse route was not present for LC.
35 | 20-02-24-123 | Troubleshooting done for pappur user login to ESR XR devices | ISE | Lab Troubleshooting | Completed | 2024-02-20 | 2024-02-20 | 1 | [26 empty] | ESR not added in XR profile.
36 | 21-02-24-124 | Troubleshooting login issue on vCRR | ISE | Lab Troubleshooting | Completed | 2024-02-21 | 2024-02-21 | 1 | [27 empty] | Device not added in any node type and profile changed from XE to XR
37 | 21-02-24-125 | Troubleshooting for write access to ESR for 'pappur' user | ISE | Lab Troubleshooting | Completed | 2024-02-21 | 2024-02-21 | 1 | [27 empty] | Clocking profile added to Access XR devices
38 | 10-01-24-126 | Syslog-NG CGNAT LC export size shrinking and updated scripts validations | CGNAT LC | Feature Testing | Completed | 2024-01-10 | 2024-02-21 | 2 | [26 empty] | Was on hold till now | Resuts updated on CLM ID: 1351453
39 | 21-02-24-127 | Banglore ACI integration with TACACS and syslog through inband IP | ISE | Support Activity | Completed | 2024-02-21 | 2024-02-21 | 1 | [27 empty] | Current integration with OUTBAND working. Checked with INBAND.
40 | 19-03-24-171 | Troubleshooting Genie anlaytics login authorization issue | ISE | Lab Troubleshooting | Completed | 2024-03-19 | 2024-03-29 | 2 | [29 empty] | 45369: ISE authorization logs not available. Need to open case with cisco; 45380: Genie ATM device forwading request via GUI but not via CLI. Device team need to check config
41 | 21-03-24-183 | Hotpatchs not refleted on MNT primary node | ISE | Lab Troubleshooting | Completed | 2024-03-21 | 2024-05-10 | 10 | [29 empty] | 45372: Tried reinstallation of hotpatches on MNT primary node. Below are the observations: 1. Hotpatches were not being reflected on the MNT primary node but were already installed. 2. Repository configuration was visible in the GUI of the PAN node but not reflected in the CLI of all nodes.; 45373: TAC Case Number 697089866 created.; 45377: Requested update on mail and call scheduled for tommorow; 45378: Call with Cisco tac: Rollback one hotpatch and reinstalled to verifiy MNT pri behaviour.; 45383: Requested for update on mail.; 45397: New VM creation using exisiting ISE3.1 OVA.; 45414: VM configuration done and patch 7 installed successfully; 45415: Call with TAC. Took support bundle and installed hotpatchs; 45418: MNT primary pesona reverted to primary. As per TAC, need to hold for 3 days to see logs; 45422: MNT primary working as expected. Confirmation done on mail.
42 | 22-03-24-184 | ATP1B for F5 IOT sites | CGNAT | Lab Troubleshooting | Completed | 2024-03-22 | 2024-03-22 | 1 | [29 empty] | 45373: Supported Sricharan with ATP 1B review for F5 sites
43 | 26-03-24-185 | Troubleshooting TR2506: 2405:200:1410:398::325 switch login issue. | ISE | Lab Troubleshooting | On Hold | 2024-03-26 |  | 1 | [29 empty] | 45377: ISE authentication giving pass respone. Need to check authorization part.
44 | 28-03-24-186 | Support provided for Syslog for APICL4 logging | CLMS | Support Activity | Completed | 2024-03-28 | 2024-03-28 | 0
45 | 18-03-24-187 | A10 VNF validation of IPDR solution for FTTx IPv6 forward traffic | CGNAT | Solution Testing | Completed | 2024-03-18 | 2024-03-21 | 4 | [29 empty] | 45369: Troubleshooting A10 VNF IPDR timeout issue for linkedin.com and cisco.com; 45370: Validated again for VNF and appliance and observations shared on mail.; 45371: Checked observations for UDP session on A10 VNF; 45372: Updated testing report and shared with NPE and Vendor for remarks.
46 | 28-03-24-188 | A10 VNF validation of IPDR solution for 4G,5G IPv6 forward traffic | CGNAT | Solution Testing | Completed | 2024-03-28 | 2024-04-17 | 11 | [29 empty] | 45379: Had discussion on IPDR solution for 4G and 5G traffic; 45384: Requested for partitioning configuration; 45387: configuration confict while using single interface for IN and OUT; 45390: logging not supported via shared partitioning; 45391: Seperate logging interface configuration in new partitioning. Route segregation config done for 4G and 5G traffic; 45393: TCP and UDP traffic validation; 45394: CLM ID released: 1358355 for 4G; 45397: TCP traffic validation for 5G traffic; 45398: UDP traffic validation for 5G traffic; 45399: CLM ID released: 1358399 for 5G; 45400: validating IDPR failover with Neelmani mam
47 | 28-03-24-189 | TLS validation on Syslog-NG as CLMS | CLMS | Solution Testing | Completed | 2024-03-28 | 2024-05-28 | 19 | [29 empty] | 45379: Discussion with Anatha C and Tejas Yadav on TLS config on syslog-NG as CLMS; 45393: RST VM's cloned to be used as CLMS; 45394: Previous cloned VM deleted. Created new clones after infosec scanning and done fresh configuration of cluster; 45399: TLS configuration done in syslog-ng.conf file; 45400: Shared CLMS details with device team.; 45401: Certificate generated and CA.cert shared with one-NDS team. Receving logs .; 45404: Logs confimation done on mail. Attached logs as well; 45405: Troubleshooting logs not receiving on secondary node.; 45407: Shared .csr for CA signed certificate with Anatha C; 45412: Shared cert chain with device team to config device with CA signed certificate; 45414: Joint discussion on open issue; 45418: Troubleshooting invalid certificate issue. checked with both self signed and CA signed certificate.; 45420: call with NPE for discussion on requirements in syslog-ng CLMS. Generated new CSR with key size 2048 as per device requirement.; 45421: new cert with 2048 bit key config on server. shared CA cert with NDS team.; 45422: TLS working with new certs .Team requested for .cert file instead of .pem file.; 45426: Working after subCA and rootCA is removed from CA cert chain at client end. need to generate new CSR and share for final confirmation.; 45427: Client able to connect with both servers with different CA certs.; 45436: TLS not working in production because of client openssl version was not updated . Client team proceeded with using without TLS; 45440: Production implementation successful without TLS.
48 | 29-03-24-203 | CGNAT configuration for FTTX airfiber UE pool. | CGNAT | Provisioning and Configuration | Completed | 2024-03-29 | 2024-03-29 | 1 | [29 empty] | 45380: everse route for 2405:200:1412:c2c4::/62 in CGNAT with inside IP-2405:200:1410:2d0::45a
49 | 01-04-24-204 | Support provided for ACI Inband ISE testing | ISE | Support Activity | Completed | 2024-04-01 | 2024-04-01 | 1 | [29 empty] | 45383: checked logs from Inband and Outband IP's
50 | 01-04-24-205 | Support provided for ACI Inband syslog testing | CLMS | Support Activity | Completed | 2024-04-01 | 2024-04-01 | 1 | [29 empty] | 45383: checked logs from Inband and Outband IP's
51 | 02-04-24-206 | Troubleshooting reachabilty issue with DPI pool. | CGNAT | Lab Troubleshooting | Completed | 2024-04-02 | 2024-04-03 | 2 | [29 empty] | 45384: Traffic hitting on VLAN 651 of A10 which is IPv6 but source is IPv4.; 45385: Configuration issue at ACI
52 | 04-04-24-207 | Troubleshooting alopk login issue | ISE | Lab Troubleshooting | Completed | 2024-04-04 | 2024-04-04 | 1 | [29 empty] | 45386: Hostname was wrongly configured in authentication policy
53 | 04-04-24-208 | F5 CGNAT configuration to segregate 4G and 5G traffic. | CGNAT | Solution Testing | Completed | 2024-04-04 | 2024-04-12 | 1 | [29 empty] | 45386: configuration completed at CGNAT end. ACI config pending; 45392: Requested for 5G IP pool; 45393: Partitioning and running config completed and VM setup for traffic validation done; 45394: Logging configuration done and service validation for NAT44 , XLAT and IPDR completed with RHEL VM.
54 | 05-04-24-209 | Troubleshooting MUMBRLABEDS001-100G integration issue | ISE | Lab Troubleshooting | Completed | 2024-04-05 | 2024-04-05 | 1 | [29 empty] | 45387: Secret key not configured.
55 | 09-04-24-217 | Infosec validation of syslog-ng as RST. | CLMS | Infosec Testing | Completed | 2024-04-09 | 2024-04-16 | 5 | [29 empty] | 45391: Infosec script pushed on both nodes but not working; 45392: New scripts executed and working on both nodes; 45394: Requested infosec to close open points, ignoring vFat finding; 45397: 175859 RHEL 8 : libtiff (RHSA-2023:2883) pending; 45398: All open points cleared
56 | 11-04-24-237 | ISE validation of DLink DI-SR-F3000 version 8.1.1C (BASE) Build 11388 | ISE | Lab Troubleshooting | Completed | 2024-04-11 | 2024-05-08 | 4 | [29 empty] | 45393: current status of observations in last testing: 1. The device port value appears as 'port=Unknown' for authentication and shell profile authorization logs. PERSISTING 2. The remote address field displays an incomplete IPv6 address for authentication and shell profile authorization logs. RESOLVED; 45398: Join call to troubleshoot port="unknown " issue. Need to perform more iterations and monitor.; 45406: Observation's shared on mail.; 45420: confirmed 'port=unknown ' observation on both pass and failed authentication attempt.
57 | 15-04-24-238 | Infosec validation for A10 VNF 5.2.1-P9 IPDR scanning. | CGNAT | Infosec Testing | Completed | 2024-04-15 | 2024-04-17 | 2 | [29 empty] | 45397: ISE access provided.; 45398: Conditional approval by Infosec
58 | 16-04-24-239 | Troubleshooting reachability issue with TR device. | CLMS | Lab Troubleshooting | Completed | 2024-04-16 | 2024-04-17 | 2 | [29 empty] | 45398: Device reponding to ping response, shared pcap with Dinesh on mail; 45399: Joined troubleshooting with Dinesh, need to take pcap at device end.
59 | 18-04-24-240 | RST VM thinning and clonig for production deployement. | CLMS | Provisioning and Configuration | Completed | 2024-04-18 | 2024-04-23 | 4 | [29 empty] | 45400: VM Zeroing and VMDK thining done; 45401: cloning done but file size more than 10GB.; 45404: Tried VMDK shrinking again but file size remains same. Files shared with NPE for production deployment; 45405: Supported at prodution config at Jaipur Site.
60 | 22-04-24-241 | CGNAT configuration for 5G UE pool. | CGNAT | Provisioning and Configuration | Completed | 2024-04-22 | 2024-04-22 | 1 | [29 empty] | 45404: 2405:0200:1412:c012:0000:0000:0000:0118/125 pool. CGNAT IN IP:- 2405:200:1410:2d0::7f2
61 | 19-02-24-116 | F5 VNF validation of IPDR solution for wireling FTTx IPv6 forward traffic | CGNAT | Solution Testing | Completed | 2024-04-18 | 2024-06-18 | 6 | [29 empty] | 45400: TCP-(linkedin.com) f5 session,pcap from f5 end, syslogs; 45401: UDP-(whatsapp-audio) captured f5 session,pcap from f5 end, syslogs; 45406: Verified TCP testing. NAT64 traffic reaching IPDR server.; 45407: shared obsevation's on mail.; 45415: Jointed troubleshooting with vendor for ICMP and UDP timeout , and session closed logs issue.; 45441: Vendor checking with TAC team.
62 | 26-04-24-259 | CLMS validation for One-NDS | CLMS | Provisioning and Configuration | Completed | 2024-04-26 | 2024-05-16 | 4 | [29 empty] | 45406: meeting to check logging from mutiple device; 45407: verified logs from provided IP addresses.; 45427: shared logs for required timestamp.; 45428: Logs validation on joint meeting
63 | 30-04-24-267 | Troubleshooting DCN login issue | ISE | Lab Troubleshooting | Completed | 2024-04-30 | 2024-04-30 | 1 | [29 empty] | 45412: Read access provided for all IPMPLS nodes to user 'Kazi'
64 | 24-04-24-268 | CLMS validation of RJIO-CLI-Spoofing | CLMS | Provisioning and Configuration | Completed | 2024-04-24 | 2024-04-30 | 2 | [29 empty] | 45406: Syslog server details shared over mail; 45412: log confirmation done.
65 | 04-11-24-251 | checking the ILO IP addresses for two Cache DNS servers in the lab to wipe-off the configuration. | DNS | Support Activity | Completed | 4/24/2024 | 4/24/2024 | 1 | [29 empty] | 45406: Checking the ILO IP address to erase the configuration for the server to use another purpose. (cache DNS migrated from sourceT to x86 )
66 | 07-05-24-289 | Troubleshooting SAR packet drop issue | CGNAT | Lab Troubleshooting | Completed | 2024-05-07 | 2024-05-07 | 7 | [29 empty] | 45419: ACI interface 1/27 going in configuration fail state . Temporary work around by disabling that interface.
67 | 07-05-24-290 | Troubleshooting mumbai gdc syslog-ng resource movement issue | CLMS | Production Troubleshooting | Completed | 2024-05-07 | 2024-05-07 | 3 | [29 empty] | 45419: hostname(Captial) mismatch due to which syslogmon scripts was not working.
68 | 06-05-24-291 | Write access to Abhishek1 user for ICR devices. | ISE | Provisioning and Configuration | Completed | 2024-05-06 | 2024-05-06 | 1 | [29 empty] | 45418: Requested by Gopal prajapati
69 | 08-05-24-292 | Troubleshooting login issue for 'genie' user | ISE | Lab Troubleshooting | Completed | 2024-05-08 | 2024-05-08 | 1 | [29 empty] | 45420: Device not forwading request to ISE since genie is also a local user.
70 | 08-05-24-277 | F5 appliance i15k upgrade version 15.1.10.4 with EHF. | CGNAT | Release Testing | Completed | 2024-05-27 | 2024-06-05 | 4 | [29 empty] | 45421: 5G traffic not working . after license installation service restart was required.; 45440: Image and hotpatch installed successfully; 45446: regression test report validated.; 45448: CLM ID released : 1359609
71 | 09-05-24-293 | CLMS testing with radisys R3.2.1 | CLMS | Provisioning and Configuration | Completed | 2024-05-09 | 2024-05-09 | 1 | [29 empty] | 45421: shared required logs via SFTP to client server.
72 | 08-05-24-294 | ISE validation for Techroute MDS devices. | ISE | Provisioning and Configuration | Completed | 2024-05-08 | 2024-05-09 | 1 | [29 empty] | 45421: observation shared on mail by Sairam
73 | 10-05-24-295 | Troubleshooting user login failed for the SR-PCE virtual routers | ISE | Lab Troubleshooting | Completed | 2024-05-10 | 2024-05-10 | 1 | [29 empty] | 45422: Devices were not included in new IP MPLS profile
74 | 13-05-24-296 | Troubleshooting user login issue for Juniper esar | ISE | Lab Troubleshooting | Completed | 2024-05-13 | 2024-05-13 | 1 | [29 empty] | 45425: User 'pappur' was not added in Juniper group
75 | 15-05-24-297 | Infosec MSR scanning for replica A10 CGNAT devices | CGNAT | Support Activity | On Hold | 2024-05-15 | 2024-05-16 | 2 | [29 empty] | 45427: shared required details on mail. Need to provide TACACS access aswell.; 45428: ISE user 'mayank5' created and credentials shared one to one.
76 | 15-05-24-286 | A10 TH6630 mgmt reachabiltiy issue | CGNAT | Lab Troubleshooting | Completed | 2024-05-15 | 2024-05-15 | 1 | [29 empty] | 45427: Device was in hang state ,reachable after hard boot.
77 | 16-05-24-298 | CGNAT logcollector syslog-ng rpm upgrade from 7.0.32 to 7.0.34 | CGNAT LC | Solution Testing | On Hold | 2024-05-16 |  | 2 | [29 empty] | 45428: RPM upgrade completed; 45488: Regression testing in progress
78 | 17-05-24-299 | ATP 1B document discussion for CGNAT LC and RST devices. | CGNAT LC | ATP 1B | Completed | 2024-05-17 | 2025-02-12 | 7 | [29 empty] | 45429: Created ATP 1B required testcase; 45448: requested for NDD and GCT. | [7 empty] | Discussion with Mahima about required commands for ATP 1B. | Creating SHELL script to get the required command output in one go. | [15 empty] | Validated shared production results upon executing the script and shared observation on mail | Shared updated script i.e version 2 |  |  |  |  | Go ahead given for the CGNAT LC script.
79 | 17-05-24-300 | Infosec MSR scanning for replica ISE. | ISE | Support Activity | Completed | 2024-05-17 | 2024-05-28 | 3 | [29 empty] | 45429: Created Super admin user and shared required details with Infosec team.; 45434: Created CLI user for all 6 nodes shared one to one with Kalyani.; 45440: Team requested for shell access. which is not possible since shell access is available only to TAC
80 | 17-05-24-301 | Infosec MSR scanning for syslog-ng CGNAT LC. | CGNAT LC | Support Activity | Completed | 2024-05-17 | 2024-05-28 | 3 | [29 empty] | 45429: Shared required details on mail.; 45434: Created new infosec user and shared one to one with Kalyani.; 45440: Provided sudo access to infosec user
81 | 22-05-24-330 | CLMS Logs separation(OS & Application Logs) for ENM2 ENIQ COR | CLMS | Provisioning and Configuration | Completed | 2024-05-22 | 2024-06-07 | 3 | [29 empty] | 45434: Shared syslog-ng CLMS IP details; 45440: Receiving OS and Web logs on both CLMS.; 45450: We were able to see seperate logs will facility and severity tagging.
82 | 22-05-24-331 | TLS configuration support in production for syslog-ng CLMS server. | CLMS | Production Troubleshooting | Completed | 2024-05-22 |  | 1 | [29 empty] | 45434: TLS configuration shared with production team in a joint call. Troubleshooting for not working TLS communction via curl. Issue was with wrong CSR generated.
83 | 22-05-24-332 | Validating updated whitelisting script for syslog RST nodes. | CLMS | Feature Testing | Completed | 2024-05-22 | 2024-06-04 | 6 | [29 empty] | 45435: Configuraing whitelisting.sh and other updated scripts; 45436: Troubleshooting HA inactive issue. ICMP allowed for mgmt pool.; 45443: Troubleshooting forwarding issue.; 45446: Tested CLMS prod configuration . Not working along with TLS configuration; 45447: Troubleshooting forwarding issue.; 45448: Issue identified at CLMS end.
84 | 23-05-24-333 | JIO ESG 3.0.0 integration with CLMS in Replica lab | CLMS | Provisioning and Configuration | Completed | 2024-05-23 | 2024-05-23 | 1 | [29 empty] | 45435: shared log status on mail.
85 | 27-05-24-334 | ISE integration of 6connect DNS node using Radius protocol | ISE | Provisioning and Configuration | Completed | 2024-05-27 | 2024-05-27 | 1 | [29 empty] | 45439: Configuration completed on ISE
86 | 29-05-24-342 | To validate SR 697402714 for ISE : Requirment is to disable identity store user ID on 5 wrong login attempts | ISE | Provisioning and Configuration | Completed | 2024-05-29 | 2024-05-29 | 2 | [29 empty] | 45441: Joint testing with NPE and vendor. Shared observation and logs with NPE; 45442: Joint call with TAC for troubleshooting. ISE is doing +1 to number of failed attempts.
87 | 29-05-24-343 | Troubleshooting banglore cache dns IPv6 public IP issue | DNS | Lab Troubleshooting | Completed | 2024-05-29 | 2024-05-29 | 1 | [29 empty] | 45441: Same IPv6 configured at device and ACI end.
88 | 28-05-24-339 | Upgrading the F5 VNF software from version 15.1.10.2 to 15.1.10.4 with Hotfix-BIGIP-15.1.10.4.0.62.5-ENG on an HP DL360 Gen10 Server. | CGNAT | Release Testing | Completed | 2024-05-28 | 2024-06-13 | 2 | [29 empty] | 45447: Traffic migration from F5 appliance to F5 VNF done; 45456: CLM ID released: 1359781
89 | 06-06-24-365 | Provisioning and validation of Syslog-ng log collector as CLMS solution. | CLMS | Solution Testing | On Hold | 2024-08-13 |  | 7 | [29 empty] | 45449: Imported 30G VM and uploaded to repo server via ssh tunnel; 45450: VM deployed; 45454: VM1 configuration completed. Unable to clone to VM2 due to a connectivity issue.; 45455: VM connectivity issue resolved and VM clone created and configuration done.; 45460: Installed Trendmicro rpm using as script provided by NPE team. Also installed NX logs agent on one windows VM to generate and forward logs toward syslog-ng CLMS; 45531: NAS configuration for log storing; 45532: Troubleshooting main.service issue
90 | 12-06-24-366 | Validating updated scripts for syslog RST nodes. | CLMS | Provisioning and Configuration | Completed | 2024-06-12 | 2024-07-11 | 8 | [29 empty] | 45456: New scripts updated on RST1.; 45457: Watchqueue script and logsearch working as expected. Created new /data/buffer partition for syslog-alarm scripts testing. alarms script not working as expected, need to troubleshoot.; 45460: file-cleaner and syslog-alarms working as expected now. backup and restorer not working.; 45464: NPE requested changes in watchqueue , syslog-alarms and filecleaner scripts.; 45467: confbkp.sh not working as expected. unable to restore some files also authorization key script logic is incorrect.; 45474: Unable to do SFTP via oobackup user.; 45475: Shared update scripts and crontab file on mail.; 45484: SFTP issue resolved . oobackup root directory ownership should have been root:root
91 | 00-01-00-367 | Validation of Mellanox MCX623106AS-CDAT Ethernet 100Gb NIC for vCGN in QA | CGNAT | New Product Validation | Completed | 2024-06-19 | 2024-06-25 | 6 | [29 empty] | 45461: Received card today. Requested for ACI port and also requested lab team to install the card in the server.; 45462: Test VM creating with RHEL9.2 iso.; 45463: Installing driver and firmware upgrade but unable to install as per MOP.; 45464: Requested HP team to install Driver. Firmware to be installed by OS team.; 45467: Drivers installed successfully. Firmware installed with support from production. ACOS version upgrade from v 6.0.2 to 6.0.4.; 45468: Regression tested completed and CLM ID 1359996 released
92 | 20-06-24-389 | Read access to infosec for MSR 2024-25 Assessment cycle(CAT3-AE-RS) ¦¦ IP Support - AAA | ISE | Provisioning and Configuration | Completed | 2024-06-20 | 2024-06-20 | 0
93 | 20-06-24-390 | Troubleshooting A10 TH6630 ipv6 reachability issue. | CGNAT | Lab Troubleshooting | Completed | 2024-06-20 | 2024-06-20 | 0
94 | 17-06-24-397 | Syslog-ng CLMS Trendmicro agent testing. | CLMS | Feature Testing | Completed | 2024-06-17 | 2024-06-26 | 1 | [29 empty] | 45460: Scripts executed successfully on both VM's on joined call.
95 | 26-06-24-410 | ISE patch 9 Upgrade. | ISE | Release Testing | On Hold | 2024-06-26 |  | 2 | [29 empty] | 45469: Pathc file downloaded and uploaded to FTP server.; 45470: Certificate backup for all 6 ISE nodes done. Configuration backup done successfully and operational backup unsuccessfull.
96 | 28-06-24-411 | Authorization logs not reflected in ISE and operational backup issue | ISE | Lab Troubleshooting | On Hold | 2024-06-28 |  | 8 | [29 empty] | 45471: TAC case 697579630 raised .; 45475: Joined call with TAC and shared TAC support with TAC.; 45488: ISE TAC case escalation done via cisco portal; 45489: Joint call will TAC.; 45511: Joint call with cisco tac. Shared required TAC support.; 45518: Joint call with vendor .Reload done on MNT node as requested by vendor.; 45530: Joint call with TAC and shared required logs and TAC bundle; 45533: Joint call with TAC and NPE to get update on progress and timeline for closer.
97 | 27-06-24-412 | CGNAT IN interface down issue | CGNAT | Lab Troubleshooting | Completed | 2024-06-27 | 2024-06-27 | 1 | [29 empty] | 45470: Leaf reboot performed at ACI end due to which CGNAT SLB configuration triggered and disabled both interfaces of both VM's load balancing 5G traffic.
98 | 02-07-24-445 | Support porvided to UPF team to validate IPDR log generation at UPF end. | CLMS | Support Activity | Completed | 2024-07-02 | 2024-08-29 | 17 | [29 empty] | 45476: shared required log number and log files.; 45477: shared required log number and log files.; 45478: shared required log number and log files.; 45481: shared required log number and log files.; 45482: Identified issue with logsearch script . shared required log number and log files.; 45489: shared required log number and log files.; 45490: shared required log number and log files.; 45491: Joint troubeshooting with UPD team.; 45492: issue resolved after changing syslog-ng received buffer.; 45511: Observing some loss in packets recieved.; 45516: Stopped syslog-ng service on VM1 to check; 45517: Mutiple iterations done with different mps and shared updated scripts and results with NPE on mail; 45520: Found packet drops at ESXi; 45523: Configured SRIOV and updated Ring buffer to resolve packet drop issue; 45524: Cloned VM and confiured vmfs6 on hardisk with thick provisioning and tested without SRIOV. Shared testing results with NPE on mail.; 45526: shared log count from yesterday 16:10 to 8:50 today; 45533: Shared R8 upf log count from 17:24 to 12:40 today
99 | 04-07-24-446 | Replica syslog-ng CGNAT log collector storage expansion. | CLMS | Provisioning and Configuration | Completed | 2024-07-04 | 2024-07-05 | 2 | [29 empty] | 45477: Recieved two 1.2 TB HDD for expansion. RAID 0 configuration through ILO and discovery and confoguration at ESXi end.; 45478: new LVM creation on both VM's
100 | 05-07-24-447 | Validation of A10 VNF v6.0.4 with Mellanox MCX623106AS-CDAT Ethernet 100Gb NIC with FTTx IPDR traffic and 5G airfiber . | CGNAT | Solution Testing | Completed | 2024-07-05 | 2024-07-25 | 4 | [29 empty] | 45478: VM clone created using existing A10 CGNAT VM.; 45481: VM runing configuration; 45483: Troubleshooting for NTP issue and syslog issue.; 45484: A10 IPDR logs being forwarded to multiple collector. Disabling other resolved the syslog issue.
101 | 15-07-24-448 | Validation of FTTx and 5G airfiber IPDR traffic service on A10 VNF v6.0.4 with Intel E810-C-Q2 100Gb adapter. | CGNAT | Solution Testing | Completed | 2024-07-15 | 2024-08-14 | 4 | [29 empty] | 45488: Server and connectoity planning for new A10 IPDR VM; 45490: IPDR VM clone created for FTTx and 5G airfiber; 45511: Downgraded firmware and driver as requested by NPE.; 45518: CLM ID:1360685
102 | 16-07-24-449 | IPv4 services Not Working in Airfiber Setup (Jamnagar Replica) | CGNAT | Lab Troubleshooting | Completed | 2024-07-16 | 2024-07-16 | 1 | [29 empty] | 45489: A link flap was observed on 12th July on interface connected to eth1/20 of leaf702-752, causing the CGNAT SLB monitoring configuration to disable both interfaces.
103 | 17-07-24-450 | Troubleshooting Twamp Radius authentication issue | ISE | Lab Troubleshooting | Completed | 2024-07-17 | 2024-07-24 | 2 | [29 empty] | 45490: Troubleshooting call with vendor , need to open tac case with cisco ISE; 45511: Issue resolved by making change in ISE config
104 | 06-08-24-501 | Temporary write credentials for ISO testing | ISE | Provisioning and Configuration | Completed | 2024-08-06 | 2024-08-06 | 1 | [29 empty] | 45510: Write access provided for 1 day.
105 | 07-08-24-502 | Validation of CGNAT log collector updated scripts. | CGNAT LC | Solution Testing | Completed | 2024-08-07 | 2024-08-13 | 7 | [29 empty] | 45511: NPE shared updated configuration for cgnatglobals.sh, sync_bi.sh, cgnatglobal.sh; 45512: 1. A loss of approximately 0.5% (~175-180k mps) was observed during testing with the UPF team. 2. Syslog-ng parameters in the syslog-ng.conf file were fine-tuned as recommended by the team. 3. Multiple iterations of testing with the new configuration using loggen showed a 0.02% loss at 175k mps and a 0.046% loss at 200k mps. 4. The sync_bi.sh and cgnatglobals.sh scripts were updated to receive Sub6 logs. 5. Configuration was done on the VM, and cgnatglobals.sh was updated to write CGNAT and IPDR logs service-wise into dedicated folders. 6. A remote server was set up to test rsync on the remote and also tested on local machines. 7. The rsync issue related to writing logs in the relative path and in /data/archive has been resolved.; 45513: Conclusion: The average rate was 170k messages per second, with a drop rate of 1.82% observed using the updated configuration. Additionally, it was noted that syslog-ng is writing logs received from UPF into both the '5G' and 'cgn' directories..; 45516: NPE share updated script with which syslog data will be stored in relative paths based on subnet filter IPs, and the remaining logs will be stored in the CGN directory. the provided configuration is working as expected. However, the following observation has been made: 1. Rsync is writing 5G logs in both the archive directory and the /root directory 2. The epoch time is the same for most of the log files.; 45517: one mistake in the cgnatglobals.conf file was observer. Remove the ‘#’ from the 5G folder path, resolved the issue. the updated compress.sh & logsearch.sh script was shared . logsearch not working as expected.; 45518: Update log search scipts as suggested by vendor.; 45527: shared counter for new IP proivded.
106 | 16-08-24-503 | Troubleshooting ePDG login issue using TACACS authentication. | ISE | Lab Troubleshooting | Completed | 2024-08-16 | 2024-08-21 | 4 | [29 empty] | 45520: Request not receieved at ISE; 45523: ISE was unreachable from the server; 45524: ISE reacheble from one server not from other.; 45525: configuration update on device end. Issue resolved
107 | 22-08-24-524 | A10 CGNAT VNF testing with ACOS v6.0.4, build 158 on HP DL360 Gen10 Server with an Intel(R) Eth E810-CQDA2 100Gb 2-port adapter | CGNAT | Release Testing | Completed | 2024-08-22 | 2024-08-23 | 2 | [29 empty] | 45526: Physical connectivity and configuration on ESXI for A10 VNF for Intel 100G NIC; 45527: CLM ID:1360768
108 | 22-08-24-526 | Validating production ESXi drop counter and health monitoring logs | CGNAT LC | Production Troubleshooting | Completed | 2024-08-22 | 2024-08-23 | 2 | [29 empty] | 45526: shared commands to check drop at ESXi.; 45527: Joint call with production team to check packet drop at ESXi. Found drop at ESXi in production , Team will mointor if increasing after config change.
109 | 00-01-00-527 | Support provided to SAEGW team to validate IPDR log generation and forwarding | CGNAT LC | Support Activity | Completed | 2024-09-22 | 2024-09-30 | 6 | [29 empty] | 45526: share logs confimation on teams.; 45530: shared required logs on mail.; 45533: shared R8 upf log count from 17:24 to 12:40 today; 45541: Shared log count on LC2; 45554: shared logs to conclude IPDR format with new SAEGW & GWU release; 2024-09-30: Shared requested log on mail.
110 | 00-01-00-528 | Syslog-ng CLMS integration of TNMS via TLS | CGNAT LC | Provisioning and Configuration | Completed | 2024-08-12 | 2024-09-12 | 9 | [29 empty] | 45516: Shared TLS cerficate with client; 45523: confirmed log status on CLMS; 45534: Joined call to troubleshoot. Client able to authenticate via curl.; 45537: Issue identified at client configuration for cert path; 45538: After updated getting nothing in TLS logs. Its seems CLMS is not writing logs as per in proper format; 45539: Issue resolved after changing syslog config.; 45540: Shared requested logs for given time period; 45546: Shared requested logs for given time period; 45547: Shared requested logs for given time period
111 | 30-08-24-529 | Troubleshooting Genie ingestor login issue | ISE | Lab Troubleshooting | Completed | 2024-08-30 | 2024-08-30 | 1 | [29 empty] | 45534: Secret key mismatch found. updated secret key via local login.
112 | 02-09-24-530 | A10 Thunder 7440-11 appliace identification and migration | CGNAT | Audit and Analysis | Completed | 2024-09-02 | 2024-09-02 | 1 | [29 empty] | 45537: Power was enabled and console access taken to see device configuration. Device using other A10 appliance mgmt IP. Some required configuration update was done
113 | 02-09-24-531 | Syslog-ng CGNAT log collector OVA export | CGNAT LC | Provisioning and Configuration | Completed | 2024-09-02 | 2024-09-06 | 4 | [29 empty] | 45537: Image clone done to secondary server to do required changes on clone and then export; 45539: VM zeroing done on both / and /data directory; 45540: VMDK thining completed on VMDK1 and VMDK2; 45541: OVF file exported successfully with a approx size of 3GB
114 | 03-09-24-532 | Troubleshooting sub6 UE packet drop issue | CGNAT | Lab Troubleshooting | Completed | 2024-09-03 | 2024-09-03 | 1 | [29 empty] | 45538: 1. Traffic is getting through CGNAT as per expectation. 2. In case of TLS handshake , Client Key Exchange is not received at CGNAT for “irctc.co.in“. 3. For “flipkart.com” TLS handshake is completed
115 | 03-09-24-533 | CGNAT LC logs for GWU node after hotfix | CGNAT LC | Provisioning and Configuration | Completed | 2024-09-03 | 2024-09-03 | 1 | [29 empty] | 45538: shared required logs for given timestamp
116 | 03-09-24-534 | Troubleshooting cache DNS radius login issue | ISE | Lab Troubleshooting | Completed | 2024-09-03 | 2024-09-03 | 1 | [29 empty] | 45538: request not being received in case on SSH on device. No issue in ISE config
117 | 03-09-24-535 | Troubshooting Tibco CLMSv4 unreachability issue | CLMS | Lab Troubleshooting | Completed | 2024-09-03 | 2024-09-03 | 1 | [29 empty] | 45538: VM datastore was full. Deleted one old VM.
118 | 26-07-24-460 | Scheduling periodic back-up job in all servers | CPNR | Audit and Analysis | Completed | 2024-09-10 | 2024-09-13 | 4 | [29 empty] | 45545: Script creation in progress able to tar to particular to /tmp path; 45546: rysnc is working and password login setup in script itself; 45547: log formatting and precheck implemented; 45548: Script tested on pri auth after some updates
119 | 05-09-24-573 | A10 TH7440-11 deployement in Jamnagar fabric | CGNAT | Provisioning and Configuration | On Hold | 2024-09-05 |  | 9 | [29 empty] | 45540: Checking device state, took console and validate A10 configuration.; 45541: Tested BIDI SFP compatibity with ACI leaf using MPO cable; 45544: Mail sent to Telco team for IP pool; 45558: Appliance upgraded to latest release; 45566: Device decommissioned. As per Deepa ma'am, loaner deivce can'nt be moved. Need to recommission device and migrate other CGNAT configuration to this device.; 45568: A10 configuration swapped between loaner and the purchased A10 device.; 45572: Got approval from Deepa Ma'am and Amrish Sir.; 2024-10-22: Shared CGNAT port details with Lab team | [5 empty] | Requested for clarification on why the DNS configuration is required on the base OS instead of using the local DNS?
120 | 13-09-24-574 | Shared requested logs after UPF upgrade | CGNAT LC | Provisioning and Configuration | Completed | 2024-09-13 | 2024-09-13 | 1 | [29 empty] | 45548: UPF release where in the IPDR, same 128-bit IPv6 will be there which is used by UE towards network. shared the rquired logs
121 | 13-09-24-575 | Temporary Admin Access for AG2 node to perform Infosec assessment | ISE | Provisioning and Configuration | Completed | 2024-09-13 | 2024-09-13 | 1 | [29 empty] | 45548: Access provided to Alokp user
122 | 12-09-24-576 | CGNAT Jamnager cloud upgrade | CGNAT | Release Testing | Completed | 2024-09-12 | 2024-12-13 | 13 | [29 empty] | 45547: Joint call to verfiy provided detail and prerequist to upgrade; 45548: call to troubleshoot internet issue; 45551: Internet issue resolved. Team unable to login to some pod.; 45558: Upgrade started; 45559: Team troubshooting upgrade issue; 45560: stuck at building new cgnat cluster with latest version, team debugging it; 45568: Joint call with team; 45572: Joint call with team; 45573: Joint call with team; 45574: Joint call with team; 45575: Joint call with team; 2024-10-18: Started with Kubernetes course from Coursera; 2024-10-19: Module 1 completed
123 | 16-09-24-577 | ISE path9 HP installation and testing | ISE | Release Testing | Completed | 2024-09-16 | 2024-09-30 | 6 | [29 empty] | 45551: HP installation done successfully; 45554: PAN nodes not able sync . Shared observation with TAC on mail.; 45558: New TAC opened. Joint call with TAC to explain the issue; 45560: retested ISE PAN failover setup. encountered : BUG: SE HA ENH Sync the demoted node automatically whenever it comes online CSCvx02844; 45561: Again faces issue with ISE node upon testing backup/restore. Issue raised with TAC on mail.; 2024-09-30: Shared support bundle with TAC and CLM ID released: 1361618
124 | 17-09-24-578 | Production burst traffic IPDR logs analysis | CGNAT LC | Audit and Analysis | Completed | 2024-09-17 | 2024-09-18 | 2 | [29 empty] | 45552: checked for Delhi logs not found request from provide IP as a source; 45553: Shared stats on mail with Naba sir
125 | 10-09-24-579 | Validation of F5 VM with version BIG-IP 17.1.1.3 Build 0.0.5 point release 3 on the Mellanox 100G NIC cards | CGNAT | Solution Testing | Completed | 2024-09-10 | 2024-09-30 | 2 | [29 empty] | 45553: Troubleshooting 5G traffic not working issue.Configuration issue found at F5 end; 45560: NAT64 not working. Issue found in vlan configuration of virtual server.
126 | 27-09-24-580 | Monitoring CGNAT license and generating alert on teams | CGNAT | Audit and Analysis | Completed | 2024-09-27 | 2024-10-21 | 4 | [29 empty] | 45562: Able to generate alert on team for F5 license.; 2024-10-15: Created python script for A10 license check; 2024-10-18: Creating combined scripts for both A10 and F5 CGNAT; 2024-10-21: troubleshooting F5 license NONE response issue and further enhancement in the code
127 | 30-09-24-615 | ISE PAN switchover issue post hotpatch installation | ISE | Lab Troubleshooting | Completed | 2024-09-30 | 2024-10-14 | 3 | [29 empty] | 2024-09-30: Support bundle shared with TAC; 45572: Requested TAC for update on shared logs .; 2024-10-14: as per TAC error is a one-time event as we can see that there is an exception while accessing the node list in deployment. This has no relation to the applied patch.
128 | 08-10-24-616 | RST updated scripts implementation in replica VM's | RST | Provisioning and Configuration | In Progress | 2024-10-08 |  | 2 | [29 empty] | 45573: Executed updated scripts on RST1 VM. execept whitelisting; 45574: Requested prod configuration from NPE
129 | 08-10-24-617 | ISE license renewal | ISE | Provisioning and Configuration | Completed | 2024-10-08 | 2024-10-09 | 2 | [29 empty] | 45573: ISE license renewal sent to cisco team; 45574: Shared required PO and license details. SSM reachability issue with internet resolved essential license issue and for Device Admin perptual license exist but being used by some other ISE
130 | 09-10-24-618 | SSM internet reachabilty issue | CGNAT | Provisioning and Configuration | Completed | 2024-10-09 | 2024-10-09 | 1 | [29 empty] | 45574: SSM internet pool route missing on secondary VM.
131 | 08-10-24-619 | Syslog-ng CLMS IPv6 provisioning | CLMS | Provisioning and Configuration | Completed | 2024-10-08 | 2024-10-14 | 4 | [29 empty] | 45573: Requested updated configuration from production; 45575: cloned existing IPv4 syslog-ng VM to configure as IPv6 VM.; 2024-10-11: VM2 created and HA estabilished between them.; 2024-10-14: Updated configuration loaded on both VM's
132 | 22-10-24-620 | IPSE monitoring VM deployement for Grafana. | Telemetry | Provisioning and Configuration | Completed | 2024-10-22 |  | 2 | [29 empty] | 2024-10-22: Fedora VM deployed; 2024-10-23: VM redepoyement and configuration done
133 | 21-10-24-699 | Troubleshooting F5 i15k appliance NAT not working issue | CGNAT | Lab Troubleshooting | Completed | 2024-10-21 | 2024-11-22 | 3 | [29 empty] | 2024-10-21: Issue reported after license renewal; 2024-10-22: Verified configuration at CGNAT and ACI end; 2024-10-25: Join call with Vendor ping not reaching CGNAT. shared required logs from F5 i15k device with vendor..
134 | 25-12-24-700 | vCSM - CLMS Push Functionality Testing for R 24B | CLMS | Provisioning and Configuration | Completed | 2024-12-25 | 2024-12-25 | 1 | [29 empty] | 2024-10-25: shared required logs on mail.
135 | 27-12-24-701 | DNS configuration in indradhanus baseos for MMP server | DNS | Provisioning and Configuration | Completed | 2024-12-27 | 2025-01-09 | 3 | [172 empty] | Requested clarification on why | Joint call with |  |  | Troubleshooting devopsartifact.jio.com not being resolved. Resolution : created new zone file for devopsartifact.jio.com.zone
136 | 09-01-25-702 | Support provided in pulling image from indradhanus repo server for MMP setup | Other Domain | Support Activity | Completed | 2025-01-09 | 2025-01-09 | 1 | [176 empty] | Ravi was unable to pull image from Repo server. Pull requested from seperate server which loaded the image locally .
137 | 02-12-24-703 | Configuration and validation of CGNAT deployment with on-prem Red Had openshift. | CGNAT | Solution Testing | In Progress | 2024-12-02 |  | 32 | [168 empty] | unable to loging though a10cli command. Updated issue over mail. | [7 empty] | Created Pod 1 on server 4 with updated deployment. | Created manifest file for other pods | Reachability done between TACAS , syslog and A10 Jamnagar CGNAT. | ping loss and delay observed and highlighted with A10 and NPE. Troubleshooting session with A10 vendor | Joined call with vendor to show ping issue took pcap at ACI and worker Node | Troubleshooting session with A10 TAC. TAC suspected image issue, Requested for temporary license to troubleshoot further. | Shared techsupport with A10 TAC and join another troubleshooting session. |  | A10 team shared new image. | [8 empty] | License installation for Jam CGN Pod3 | Troubleshooting CNF not forwading NAT log to log collector issue . |  | unable to export PCAP from the A10 container CLI, and the GUI is also not available. shared details and techsupport with TAC team | Shared obervation list with NPE and A10 team |  |  | Meeting with A10 vendor to showcase the issue list share and try possibel workarounds and also shared techsupport bundle |  | Joint troubleshootin g session with A10 team regrading the NTP issue. |  | Tested update configuration provided by Debasis for A10 cloud. | Joint meeting with A10 TAC regarding export issue. |  |  |  | Applied suggested changes by vendor but still issue persists | NTP configuration updated but issue persists | issue resolved for NTP and A10 shared a new image for SCP issue. For config retention issue TAC will replicate issue locally and update A10 shared .upg image which is not getting loaded to podman. | Troubleshooting host NTP sync issue with A10 pod Status: The A10 container is now in sync after removing the NTP configuration from the startup-config. However, we are unable to switch time zones at the application level. | Validated latency icmp on A10 VNF to compare for the container. |  | Joint call with vendor to troubleshoot export issue with new image, saw a new backup log issue, highlighted on mail and shared showtech logs |  |  |  | A10 new image (acos_docker_6_0_3-p1-sp1-4355019_4_nogui_15553) download and upload on lab repos server | Validating fixes in new image |  |  | regression testcase for new image
138 |  | License installation on A10 pod | CGNAT | Provisioning and Configuration | Completed | 2025-01-17 | 2025-04-18 | [183 empty] | License successfully imported through CLI import command since GUI is not available
139 | 18-12-24-704 | BAVAMA 2024-25 Initial assessment report Quest CLMS and CGNAT | CGNAT LC | Issue Analysis & Testing | Completed | 2024-12-18 | 2025-03-11 | 11 | [169 empty] | Requested confirmation from NPE to which OS to upgrade to. | Requested lab team to upgrade os from RHEL 8.6 to 8.8. | offered for rescaning | [11 empty] | Requested confirmation from NPE for supported OS version and rpm version for syslog-ng and offered to lab team for upgrade |  | Resolved /root mount point full issue |  |  |  | offered for rescaning |  | Closed podman-plugin and authpriv.info finding and shared logs on mail | [5 empty] | Resolved WA TRACK and TRACE vulnerability | The ‘Password Management Standard’ finding has been closed. Regarding the ‘authpriv.info’ finding, it has already been addressed, as mentioned in the attached mail. However, even after removing the double space, the finding is still visible. | [8 empty] | System found complaint for all BAVAMA findings | [7 empty] | CLM ID:1364019 provided for Validation of the Quest_SyslogNG v7.0.34 and RHEL 9.4 CGNAT Log Collector VM
140 | 05-12-24-705 | Telco - MSR 2024-25 Assessment cycle ¦¦ CAT3 ¦¦ Cisco ISE ¦¦ AAA | ISE | Infosec Testing | Completed | 2024-12-05 | 2024-12-05 | 1 | [167 empty] | SNMP and weak password finding closed.
141 | 13-01-25-706 | Syslog-ng windows Agent testing on IPv6 Server for forwarding logs to CLMS server | CLMS | Feature Testing | On Hold | 2025-01-13 |  | 2 | [173 empty] | Agent installation done successfully |  | agent not forwarding logs to CLMS server. Issue raised with NPE.
142 |  | Troubleshooting MMP image pull issue. | Other Domain | Support Activity | Completed | 2025-01-14 | 2025-01-14 | 1 | [178 empty] | deleted existing image and pulled a new one.
143 | 21-01-25-725 | Software Upgrade of F5 VPR-C2400 CGNAT from 15.1.10.4 to BIGIP-17.1.1.4-0.0.9 with Hotfix-BIGIP-17.1.1.4.0.67.9-ENG | CGNAT | Release Testing | Completed | 2025-01-21 | 2025-02-12 | 1 | [183 empty] | done image upload on appliance and VNF and installation on viprion.
144 | 21-01-25-823 | DNS configuration for MMP cluster on localdns | DNS | Support Activity | Completed | 2025-01-21 | 2025-01-21 | 1 | [183 empty] | Configuration done on indradhanus baseos
145 | 21-04-25-824 | Configuration and provisioning of Jamanager server for A10 HC, DCAP, Test VM etc. | Other Domain | Provisioning and Configuration | Completed | 2025-04-21 | 2025-01-22 | 2 | [183 empty] | Hypervisor installation done joint call with Adabala for multiple VM deployment ILO details: Server1: 2405:200:1410:143a:0:63:28:231 Server2: 2405:200:1410:143a:0:63:28:235 | RAID 1 configuraiton done on both servers
146 | 05-12-24-825 | BAVAMA 2024-25 Initial Assessment report ¦ IP Support ¦ IPAM -FusionLayer - IPAM | Other Domain | Infosec Testing | On Hold | 2024-12-05 |  | 1 | [167 empty] | Direct root user login has been disabled.
147 | 15-01-25-826 | Provisioning and configuration of A10 Harmony controller | CGNAT | New Product Validation | Completed | 2025-01-15 | 2025-04-01 | 7 | [179 empty] | Vendor shared resource requirment and image link. Dowloaded the required images | [5 empty] | Base OS VM creation done as per the requirment |  | Joint call with A10 team, unable to integrate our lab A10 nodes with the Harmony Controller. |  |  | Joint call with A10 team for harmony controller. Was able to configure devices after one path installation. |  | Tried mutiple iteration to register nodes under tenant |  |  | we were able to register the A10 container with the Harmony Controller, but we are unable to provision it with the Tenant. | [23 empty] | Vendor response "Product team is working on Symphony which is a new version of Harmony controller will provide the image once available probable in this week."
148 | 22-01-25-827 | Troubleshooting F5 viprion BGP down issue | CGNAT | Lab Troubleshooting | Completed | 2025-01-22 | 2025-01-22 | 1 | [184 empty] | Wrong AS number configured and Port channel not UP.
149 | 22-01-25-828 | F5 viprion unable to perform NAT. | CGNAT | Lab Troubleshooting | Completed | 2025-01-22 | 2025-01-22 | 1 | [184 empty] | VLAN configuration missing hash mapping and public pool configuration was wrong.
150 | 23-01-25-829 | Support provided in pulling image from indradhanus repo server for MMP setup | Other Domain | Support Activity | Completed | 2025-01-23 | 2025-01-23 | 1 | [185 empty] | Support provide to Ravi and team to delete images repos.
151 | 28-01-25-830 | ED-ECS4150-28P-POE addition in ISE as ESS L2 switch | ISE | Provisioning and Configuration | On Hold | 2025-01-28 |  | 1 | [196 empty] | The provided ISE configuration MOP differs from the previously tested configuration. Please find below the issues observed with the previously tested MOP: 1. In AAA logs, the device port and remote address appear as 'console' and 'async' respectively. 2. Failover is not functioning as expected.
152 | 21-01-25-831 | Kubernetes setup for DCAP application | Other Domain | Provisioning and Configuration | In Progress | 2025-01-21 |  | 13 | [183 empty] | Ubuntu VM creation done as per the requirement | snap package installation done as per the required version but rolled back to install latest version. | Setup Kubernetes cluster and created 3 worker nodes and 1 Master node. | Done Kubernetes network configuration (i.e setup crio network for this cluster). | Setup Kubernetes dashboard to GUI access | DCAP k8s route removed after restart. Disabled cloud init network and done netplan config. |  |  |  | Joint call with DCAP team to discuss further requirement and env config |  | KT session for current setup and kuberneters concept to Kazi sir and Naba sir |  |  |  |  | Deployed DCAP redis, postgress, rabbitMQ VM's | Package installation and network configuration done for these vms |  |  |  |  | LoadBalancer service creation from provided dcap service yamls |  |  | MetalLB installation and configuration done |  |  |  | NDO front end srv creation and allocation of new pool for it.
153 | 06-02-25-832 | Forwarding syslog from Quest-syslog-ng and Tibco syslog-ng to Splunk | CLMS | Provisioning and Configuration | Completed | 2025-02-06 | 2025-02-07 | 2 | [193 empty] | configured forwarding from syslog-ng to splunk with didn't worked at first. Issue found with licensing, upon renewing started working | configured forwarding from Tibco server
154 | 10-02-25-833 | Snmp trap forwarding testing with ACI switch | Other Domain | Support Activity | Completed | 2025-02-10 | 2025-02-10 | 1 | [195 empty] | Switch forwarded Traps to server which were captured using tcpdump
155 | 24-02-25-751 | ISE Upgradation from 3.1 patch 9 to 3.3 patch 4. | ISE | Release Testing | In Progress | 2025-02-07 |  | 12 | [195 empty] | Joint discussion with NPE regarding the upgrade. | [5 empty] | Downloaded required upgrade, patch and URT bundle from cisco and also uploaded to replica FTP server | TAC case created to align suppport for major ISE upgrade. | ISE prerequisite before upgrade. | ISE prerequisite before upgrade. | Troubleshooting ops backup issue with new repo | upgrade completed on PAN Sec and MNT Sec nodes | upgrade completed on PSN sec and PSN pri. Troubleshooting, after upgrading the second PSN node, both the management and service IP addresses have become unreachable. | upgrade completed on PAN pri and MNT pri | [5 empty] | patch 4 installation on all 6 nodes Status updated on mail with required changes in the MOP |  |  |  |  | Joint call with NPE for ISE production issue and rollout. |  |  |  |  | Joint call with cisco TAC regrading the network user disable issue.
156 | 11-02-25-835 | DNS configuration for MMP cluster on localdns | DNS | Support Activity | Completed | 2025-02-11 | 2025-02-11 | 1 | [196 empty] | entries in DNS in the system 2405:200:1410:1457:63::229 file name: /etc/bind/qa/knot/mmp.gj.jmgr.qa.jio.indradhanus.com.zone nbi.mmp.gj.jmgr.qa.jio.indradhanus.com. IN AAAA 2405:200:1410:915:101::10 IN A 10.60.191.115 sbi.mmp.gj.jmgr.qa.jio.indradhanus.com. IN AAAA 2405:200:1410:915:101::11
157 | 17-02-25-836 | Troubleshooting read access for ECR and AG2 .i.e. MUMBRLB1ECR001, MUMBRLB1ECR003 and MUMBRLB1AAR001 | ISE | Provisioning and Configuration | Completed | 2025-02-17 | 2025-02-17 | 1 | [199 empty] | It appears that MUMBRLB1AAR001 is not forwarding authentication requests to ISE as we are not able to see ISE prompt. However, for MUMBRLB2AAR001, we can see the ‘ISE password’ prompt
158 | 21-02-25-837 | Troubleshooting ISE SSM registration issue. | SSM | Lab Troubleshooting | Completed | 2025-02-21 | 2025-02-21 | 1 | [203 empty] | Resolved: Transport gateway cert was expired. Renewed by changing SAN.
159 | 03-03-25-838 | Troubleshooting Syslog-ng CGNAT LC rsync issue | CGNAT LC | Lab Troubleshooting | Completed | 2025-03-03 | 2025-03-03 | 1 | [210 empty] | rsync dest passwd expired and rsync command had too many arg to process
160 | 00-01-00-839 | Troubleshooting devopsartifact repository error code 500. | CGNAT | Lab Troubleshooting | In Progress |  |  | 2 | [215 empty] | increased resources for the VM but issue still exists | Issue resolved after restarting the container
161 | 13-03-25-840 | Troubleshooting KVM network not reachable issue | CGNAT | Lab Troubleshooting | Completed | 2025-03-13 |  | 2 | [216 empty] | Gateways is reachable but VMs are unable to reach gateway even though baseOS is able to reach. | Joint call with indradhanus team. Unable to find the exact issue but resolved after multiple VM restarts
162 |  | NIC CARD HPE P42046-001 Mellanox Mcx631102as-adat Ethernet 10/25gb 2-port Sfp28 Adapter Testing for Syslog-NG LC | CGNAT | New Product Validation | In Progress | 2025-04-07 |  | 2 | [221 empty] | Mellanox card was not visible in the ESXi. Enabled NIC through ILO. | vSwitch and port group configuration done at ESXi Cable connectivity done with new NIC.
163 |  | IPDR configuration for 5G mobility service in Bangalore replica | CGNAT | Provisioning and Configuration | Completed | 2025-04-04 | 2025-04-10 | 2 | [222 empty] | new pool and vlan allocated and configuration done on A10 ban vnf4 |  | configuration moved to 5G Airfiber partitioning
164 |  | Troubleshooting user "akku" admin access not working on DCN device | ISE | Lab Troubleshooting | Completed | 2025-04-08 | 2025-04-08 | 1 | [222 empty] | Policy set and user configuration profile priorty updated
165 |  | Validating CGNAT traffic on IPDR traffic for 5G AF UE IP. | CGNAT | Support Activity | Completed | 2025-04-09 | 2025-04-11 | 3 | [223 empty] | Requested by Kazi Sir for source 2405:200:145b:ffff:ffff:ffff:ffff:ffff and IPDR IN 2405:200:1410:2d0::e03 | Iteration 2 | Iteration 3
166 |  | Troubleshooting syslog-ng CLMS down issue | CLMS | Provisioning and Configuration | Completed | 2025-04-11 | 2025-04-11 | 1 | [225 empty] | root storage was full because pacemaker generated too many log. Deleted pacemaker logs and restart HA services on both VMs
167 |  | Addition of Jamnagar CGNAT server in nautobot | CGNAT | Provisioning and Configuration | Completed | 2025-04-11 | 2025-04-11 | 1 | [225 empty] | Jamnagar CGNAT servers added in nautobot
|  | Troubleshooting CGNAT banglore testing VM down issue | CGNAT | Lab Troubleshooting | In Progress |  |  | 2 | [224 empty] | Expanded datastore my using addition hardisk | VM disk consolidation done to increase storage.
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0