## Kazi
| Completed | In Progress | On Hold | Total
| 299 | 6 | 2 | 307
SN | Activity ID | Activity | Node Name | Activity Type | Status | Start date | End Date | Duration | 2024-01-11 | 2024-01-12 | 2024-01-15 | 2024-01-16 | 2024-01-17 | 2024-01-18 | 2024-01-19 | 2024-01-23 | 2024-01-24 | 2024-01-25 | 2024-01-29 | 2024-01-30 | 2024-01-31 | 2024-02-01 | 2024-02-02 | 2024-02-06 | 2024-02-07 | 2024-02-09 | 2024-02-12 | 2024-02-13 | 2024-02-14 | 2024-02-15 | 2024-02-16 | 2024-02-18 | 2024-02-19 | 2024-02-20 | 2024-02-21 | 2024-02-22 | 2024-02-23 | 2024-02-26 | 2024-02-27 | 2024-03-04 | 2024-03-05 | 2024-03-06 | 2024-03-07 | 2024-03-08 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-22 | 2024-04-23 | 2024-04-24 | 2024-04-25 | 2024-04-26 | 2024-04-29 | 2024-04-30 | 2024-05-02 | 2024-05-03 | 2024-05-06 | 2024-05-07 | 2024-05-08 | 2024-05-09 | 2024-05-10 | 2024-05-13 | 2024-05-14 | 2024-05-15 | 2024-05-16 | 2024-05-17 | 2024-05-21 | 2024-05-22 | 2024-05-23 | 2024-05-24 | 2024-05-27 | 2024-05-28 | 2024-05-29 | 2024-05-30 | 2024-05-31 | 2024-06-01 | 2024-06-03 | 2024-06-04 | 2024-06-05 | 2024-06-06 | 2024-06-07 | 2024-06-10 | 2024-06-11 | 2024-06-12 | 2024-06-13 | 2024-06-14 | 2024-07-02 | 2024-07-03 | 2024-07-04 | 2024-07-05 | 2024-07-08 | 2024-07-09 | 2024-07-10 | 2024-07-11 | 2024-07-12 | 2024-07-15 | 2024-07-16 | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-22 | 2024-07-25 | 2024-07-26 | 2024-07-29 | 2024-07-30 | 2024-07-31 | 2024-08-01 | 2024-08-02 | 2024-08-06 | 2024-08-07 | 2024-08-08 | 2024-08-09 | 2024-08-12 | 2024-08-13 | 2024-08-14 | 2024-08-16 | 2024-08-19 | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-26 | 2024-08-27 | 2024-08-28 | 2024-08-29 | 2024-08-30 | 2024-09-02 | 2024-09-03 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-09 | 2024-09-10 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-16 | 2024-09-17 | 2024-09-18 | 2024-09-19 | 2024-09-20 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | 2024-09-27 | 2024-09-30 | 2024-10-01 | 2024-10-03 | 2024-10-03 | 2024-10-04 | 2024-10-07 | 2024-10-08 | 2024-10-09 | 2024-10-10 | 2024-10-11 | 2024-10-14 | 2024-10-15 | 2024-10-16 | 2024-10-17 | 2024-10-18 | 2024-10-21 | 2024-10-22 | 2024-10-23 | 2024-10-24 | 2024-10-25 | 2024-11-01 | 2024-11-02 | 2024-11-03 | 2024-11-04 | 2024-11-05 | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-09 | 2024-11-10 | 2024-11-11 | 2024-11-12 | 2024-11-13 | 2024-11-14 | 2024-11-15 | 2024-11-16 | 2024-11-17 | 2024-11-18 | 2024-11-19 | 2024-11-20 | 2024-11-21 | 2024-11-22 | 2024-11-23 | 2024-11-24 | 2024-11-25 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 2024-11-30 | 2024-12-01 | 2024-12-02 | 2024-12-03 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-07 | 2024-12-08 | 2024-12-09 | 2024-12-10 | 2024-12-11 | 2024-12-12 | 2024-12-13 | 2024-12-14 | 2024-12-15 | 2024-12-16 | 2024-12-17 | 2024-12-18 | 2024-12-19 | 2024-12-20 | 2024-12-21 | 2024-12-22 | 2024-12-23 | 2024-12-24 | 2024-12-25 | 2024-12-26 | 2024-12-27 | 2024-12-28 | 2024-12-29 | 2024-12-30 | 2024-12-31 | 2025-01-01 | 2025-01-02 | 2025-01-03 | 2025-01-04 | 2025-01-05 | 2025-01-06 | 2025-01-07 | 2025-01-08 | 2025-01-09 | 2025-01-10 | 2025-01-11 | 2025-01-12 | 2025-01-13 | 2025-01-14 | 2025-01-15 | 2025-01-16 | 2025-01-17 | 2025-01-18 | 2025-01-19 | 2025-01-20 | 2025-01-21 | 2025-01-22 | 2025-01-23 | 2025-01-24 | 2025-01-25 | 2025-01-26 | 2025-01-27 | 2025-01-28 | 2025-01-29 | 2025-01-30 | 2025-01-31 | 2025-02-01 | 2025-02-02 | 2025-02-03 | 2025-02-04 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-08 | 2025-02-09 | 2025-02-10 | 2025-02-11 | 2025-02-12 | 2025-02-13 | 2025-02-14 | 2025-02-15 | 2025-02-16 | 2025-02-17 | 2025-02-18 | 2025-02-19 | 2025-02-20 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09 | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31
1 | 16-01-24-1 | Basic configuration and remote reachability of ToRs (that will be used for OOB connectivity of ACI leaf and spine switches | ACI | New Product Validation | Completed | 2024-01-16 | 2024-04-15 | 4 |  |  |  | Yes | [25 empty] | Discussed the blocker point, need support to arrange cables. | Explain task to Neelmani. | [158 empty] | 45614
2 | 12-01-24-2 | Rate limit testing in NXOS to reduce DNS QPS in production network | NXOS | Feature Testing | Completed | 2024-01-12 | 2024-01-12 | 2 |  | Yes | [187 empty] | 45615
3 | 16-01-24-3 | Anantapur MCN(110 Mn)- Intermittent Packet Loss while Pinging DNS,eNB and ASBC IPs | ACI | Issue Analysis & Testing | Completed | 2024-01-16 | 2024-01-26 | 2 |  |  |  | Yes | [185 empty] | 45616
4 | 16-01-24-4 | Remote ERSPAN testing with L2 link | ACI | Feature Testing | Completed | 2024-01-16 | 2024-01-31 | 4 |  |  |  | Yes |  |  |  |  | Yes |  |  |  | Yes | [176 empty] | 45617
5 | 17-01-24-5 | Support for CnBNG failover testing issue troubleshooting . | ACI | Support Activity | Completed | 2024-01-17 | 2024-01-18 | 3 |  |  |  |  | Yes | Yes | [183 empty] | 45618
6 | 18-01-24-6 | Reachability between Mumbai ePDG and Jamnagar Replica Spirent TS44 | ACI | Provisioning and Configuration | Completed | 2024-01-18 | 2024-01-18 | 2 | [5 empty] | Yes | [183 empty] | 45619
7 | 17-01-24-7 | Routing of new UE pool of spirent and PCSCF connectivity. | ACI | Provisioning and Configuration | Completed | 2024-01-17 | 2024-01-17 | 2 |  |  |  |  | Yes | [184 empty] | 45620
8 | 17-01-24-8 | Testing of ERSPAN solution for Remote Analyzer | ACI | Feature Testing | Completed | 2024-01-17 | 2024-01-24 | 4 |  |  |  |  | Yes | Yes |  |  | Yes | [180 empty] | 45621
9 | 19-01-24-9 | New VLAN config for UCS M5 VPC DI RHOSP. | ACI | Provisioning and Configuration | Completed | 2024-01-19 | 2024-01-19 | 2 | [6 empty] | Yes | [182 empty] | 45622
10 | 23-01-24-10 | Connectivity between FMS Replica to CRM GCP Setup | ACI | Provisioning and Configuration | Completed | 2024-01-23 | 2024-01-23 | 2 | [7 empty] | Yes | [181 empty] | 45623
11 | 23-01-24-11 | Reachability from Replica AMF NGAP GW to Spirent- Inter VRF | ACI | Provisioning and Configuration | Completed | 2024-01-23 | 2024-01-23 | 2 | [28 empty] | Reachability has been done. | [160 empty] | 45624
12 | 24-02-24-12 | Reachability between AMF and spirent TS42 | ACI | Provisioning and Configuration | Completed | 2024-02-24 | 2024-02-24 | 2 | [8 empty] | Yes | [180 empty] | 45625
13 | 24-01-24-13 | Troubleshooting call with NPE for Vijayawada MCN- Intermittent Packet Loss while Pinging DNS and ASBC IPs issue. | ACI | Production Troubleshooting | Completed | 2024-01-24 | 2024-02-24 | 2 | [8 empty] | No packet loss observed while pinging from TOR. | [180 empty] | 45626
14 | 25-02-24-14 | DCAAP automation setup | NDO | New Product Validation | Completed | 2024-02-25 | 2024-03-15 | 15 | [9 empty] | Yes |  | Yes | [5 empty] | Discussed and ask to provde repo access and MOP. |  |  | Discussed and informed about repo access issue. |  | Internet reachability on the server and git installation. Cloning issue has been reported to DCAP team. | [6 empty] | Discussed with team regarding error in installation. Need to continue the installation process. | Frontend installation is in progress. | Backend server installation | Backend server installation | Backend app and DB update with new code. | Frontend and backend integration. | NDO integration. | DCAP tp NDO connectivity | DCAP and NDO API functionality | [151 empty] | 45627
15 | 29-02-24-15 | Verification of PFC and ECN testing for AI/ML fabric | NXOS | Solution Testing | Completed | 2024-02-29 | 2025-03-20 | 10 | [10 empty] | Yes | Yes |  |  |  | Configuration for setup readiness. | Configuration for setup readiness. | [12 empty] | Need support to arrange tester. | [6 empty] | Explain setup to Ronak | Support for making setup. | Support for making setup. | [14 empty] | Call with Cisco | [135 empty] | 45628
16 | 06-02-24-123 | Reachability between AMF To Spirent Test Server 32 and 35 | ACI | Lab Troubleshooting | Completed | 2024-02-06 | 2024-02-07 | 3 | [15 empty] | Troubleshooting has been done. | Troubleshooting has been done. | [172 empty] | 45629
17 | 06-02-24-124 | Qos implementation for FMS VLAN 1655 and 1656 | ACI | Provisioning and Configuration | Completed | 2024-02-06 | 2024-02-06 | 2 | [15 empty] | Required configuration has been done. | [173 empty] | 45630
18 | 06-02-24-125 | OOB management connectivity of TOR from jump server. | ACI | Provisioning and Configuration | Completed | 2024-02-06 | 2024-02-06 | 2 | [15 empty] | Required reachability has been made. | [173 empty] | 45631
19 | 07-02-24-126 | FMS server 1654 vlan interface down issue. | ACI | Lab Troubleshooting | Completed | 2024-02-07 | 2024-02-07 | 2 | [15 empty] | Server side interface was down. | [173 empty] | 45632
20 | 09-02-24-133 | Discuss and follow up with cisco for ERSPAN solution for Remote Analyzer. | ACI | Provisioning and Configuration | Completed | 2024-02-09 | 2024-02-09 | 2 | [17 empty] | Discuss and follow up with cisco for ERSPAN solution for Remote Analyzer. | [171 empty] | 45633
21 | 09-02-24-134 | Discuss and follow up with Priyam regarding physical connectivity between leaf's management interface s to management TOR. | ACI | Provisioning and Configuration | Completed | 2024-02-09 | 2024-02-09 | 2 | [17 empty] | Discuss and follow up with Priyam regarding physical connectivity between leaf's management interface s to management TOR. | [171 empty] | 45634
22 | 12-02-24-135 | New Jamnagar BL to Mumbai SAR connectivity. | ACI | Provisioning and Configuration | Completed | 2024-02-12 | 2024-03-27 | 14 | [18 empty] | Physical connectivity 3K to SAR, Review of L3out configured in BL, Micro IP planning for BL to SAR connectivity. | Started L3OUT configuration and BGP configuration. | L3OUT configuration and BGP configuration. |  |  |  |  | Troubleshooting of po down issue between 3k to SAR. | Pending BGP peer configuration. |  | Troubleshooting of bgp down issue between 3k to SAR. | BGP configuration between iBL and Jamanagar BL , physical connectivity. |  | Troubleshooting 3k to SAR po down issue. Need to raise TAC. | Troubleshooting 3k to SAR po down issue. TAC case has been raised. | Worked with TAC. Will have joint troubleshooting with ASR9K tac. | Worked with TAC. | Tried to take show tech in standby 3k and it's failing. Shared logs to tac. |  |  | L span mirroring and captured shared. | [150 empty] | 45635
23 | 13-02-24-149 | Replica Connectivity Issue for Jio NIP server. | ACI | Lab Troubleshooting | Completed | 2024-02-13 | 2024-02-13 | 2 | [19 empty] | Reachability has been done. | [169 empty] | 45636
24 | 13-02-24-150 | Discussion on lab topology diagram. | ACI/NXOS | Documentation | Completed | 2024-02-13 | 2024-02-13 | 2 | [19 empty] | Discussion on lab topology diagram. | [169 empty] | 45637
25 | 13-02-24-151 | Discussion on ACI Regression test plan. | ACI | Documentation | Completed | 2024-02-13 | 2024-02-13 | 2 | [19 empty] | Discussion on regression test plan. | [169 empty] | 45638
26 | 17-01-24-5 | Support to CnBNG fallback testing | ACI | Support Activity | Completed | 2024-02-13 | 2024-02-14 | 2 | [20 empty] | Supported to CnBNG fallback testing | [168 empty] | 45639
27 | 14-02-24-156 | Reachability between Replica SIB and Port Mirroring Server | ACI | Lab Troubleshooting | Completed | 2024-02-14 | 2024-02-14 | 2 | [20 empty] | Reachability has been done. | [168 empty] | 45640
28 | 15-02-24-157 | Audit of infra IP ping issue from UE. | ACI | Audit and Analysis | Completed | 2024-02-15 | 2024-02-15 | 3 | [21 empty] | Audit of infra IP ping issue from UE. | Audit of infra IP ping issue from UE. | [166 empty] | 45641
29 | 15-02-24-158 | SMF to UPF connectivity issue in Bhopal. | ACI | Production Troubleshooting | Completed | 2024-02-15 | 2024-02-15 | 3 | [21 empty] | Issue analysis has been done. | We have checked for sample source and destination which are located at same fabric. We have not found any anomaly that can cause KPI dip. | [166 empty] | 45642
30 | 16-02-24-159 | ReplicaAKSCluster ¦ replica.jiofms.jiolabs.com ¦ ConnectivityIssue | ACI | Lab Troubleshooting | Completed | 2024-02-16 | 2024-02-16 | 2 | [22 empty] | Troubleshooting has been done. | [166 empty] | 45643
31 | 16-02-24-160 | CLM access to Mayur from RF team | Other Domain | Support Activity | Completed | 2024-02-16 | 2024-02-16 | 2 | [28 empty] | CLM access has been provided. | [160 empty] | 45644
32 | 17-02-24-161 | Supoort for ACI to 5.3(2a) regression testing. | ACI | Support Activity | Completed | 2024-02-17 | 2024-02-17 | 2 | [23 empty] | Supoort for ACI to 5.3(2a) regression testing. | [165 empty] | 45645
33 | 19-02-24-162 | Port mirroring to new NIP server. | ACI | Provisioning and Configuration | Completed | 2024-02-19 | 2024-02-19 | 2 | [24 empty] | Required port mirroring config is done. | [164 empty] | 45646
34 | 19-02-24-163 | Reachability between Samsung NFVO and Jio NMS. | ACI | Provisioning and Configuration | Completed | 2024-02-19 | 2024-02-19 | 2 | [24 empty] | Required configuration has been done. | [164 empty] | 45647
35 | 20-02-24-164 | Cisco issue tracker update. | ACI/NXOS | Documentation | Completed | 2024-02-20 | 2024-02-20 | 2 | [25 empty] | Document has been updated. | [163 empty] | 45648
36 | 20-02-24-165 | Solution discussion of Separate DNN for Device Management on 5G LM. | ACI | Support Activity | Completed | 2024-02-20 | 2024-02-20 | 2 | [25 empty] | Solution discussion of Separate DNN for Device Management on 5G LM. | [163 empty] | 45649
37 | 20-02-24-166 | Discussion on private 5G requrement. | NXOS | Support Activity | Completed | 2024-02-20 | 2024-02-20 | 2 | [25 empty] | Discussion on private 5G requrement. | [163 empty] | 45650
38 | 21-02-24-197 | Reachability requirement between device and NSO RFS node 2 | ACI | Provisioning and Configuration | Completed | 2024-02-21 | 2024-02-21 | 2 | [26 empty] | Reachability requirement between device and NSO RFS node 2 | [162 empty] | 45651
39 | 21-02-24-211 | Connectivity Issue On HL2 UPF between CM and DP | ACI | Support Activity | Completed | 2024-02-21 | 2024-02-21 | 2 | [26 empty] | Connectivity Issue On HL2 UPF between CM and DP | [162 empty] | 45652
40 | 17-01-24-5 | Support to CnBNG failover testing. | ACI | Support Activity | Completed | 2024-02-21 | 2024-02-21 | 2 | [26 empty] | Support to CnBNG failover testing. | [162 empty] | 45653
41 | 22-02-24-212 | Analysis of 4G telco node infra IPv4 accessible from UE. It should not reachable. | ACI | Production Troubleshooting | Completed | 2024-02-22 | 2024-02-22 | 2 | [27 empty] | Analysis of 4G telco node infra IPv4 accessible from UE. It should not reachable. | [161 empty] | 45654
42 | 22-02-24-213 | Discussion with NIP dev team. | ACI | Support Activity | Completed | 2024-02-22 | 2024-02-22 | 2 | [27 empty] | Discussion with NIP dev team. | [161 empty] | 45655
43 | 22-02-24-214 | Internet reachability for new OLT pool. | ACI | Provisioning and Configuration | Completed | 2024-02-22 | 2024-02-23 | 3 | [27 empty] | Required config is done. | Troubleshooting is done with team. | [160 empty] | 45656
44 | 23-02-24-175 | Remote ERSPAN testing with L2 link for different destination. | ACI | Solution Testing | Completed | 2024-02-23 | 2024-03-08 | 5 | [28 empty] | Required config is done. | Multiple static endpoint cant be configured withing same EPG and different BD also. |  | Tested with different vrf. |  |  |  | Testing done. Discussed with Cisco and observation shared. | [153 empty] | 45657
45 | 27-02-24-210 | Remote desktop setup for team. | ACI/NXOS | Support Activity | Completed | 2024-02-27 | 2024-03-01 | 3 | [30 empty] | RD license and BA/VA is pending from lab team. | RD setup completed, | [157 empty] | 45658
46 | 04-03-24-227 | Support to transport team for server reachability. | ACI | Support Activity | Completed | 2024-03-04 | 2024-03-04 | 2 | [31 empty] | Required support has been provided. | [157 empty] | 45659
47 | 04-03-24-228 | Connectivity issue in Replica LIC FMS server. | ACI | Lab Troubleshooting | Completed | 2024-03-04 | 2024-03-04 | 2 | [31 empty] | Physical link issue is resolved after jack out and in of cables. | [157 empty] | 45660
48 | 05-03-24-229 | Reachability between EITK and scanning server. |  | Lab Troubleshooting | Completed | 2024-03-05 | 2024-03-05 | 2 | [32 empty] | Reachability has been done. | [156 empty] | 45661
49 | 05-03-24-230 | Rechability between wifi nodes and IOT network. | NXOS | Lab Troubleshooting | Completed | 2024-03-05 | 2024-03-06 | 3 | [32 empty] | Requested information has been provided. | Reachability has been done. | [155 empty] | 45662
50 | 06-03-24-246 | MW team node reachability from RD server. | NXOS | Lab Troubleshooting | Completed | 2024-03-06 | 2024-03-07 | 3 | [33 empty] | Reachability has been done. | Troubleshooting for one subnet. | [154 empty] | 45663
51 | 07-03-24-251 | NEW ALPHA AMF reachability from IOT network. | NXOS | Lab Troubleshooting | Completed | 2024-03-07 | 2024-03-07 | 2 | [35 empty] | Reachability has been done. | [153 empty] | 45664
52 | 11-03-24-255 | OTA FT Stage reachability from RD server. | ACI | Lab Troubleshooting | Completed | 2024-03-11 | 2024-03-11 | 2 | [36 empty] | Required info has been provided to IOT team for routing. | [152 empty] | 45665
53 | 11-03-24-257 | Troubleshooting of internet reachability from UE in HL1 setup | ACI | Lab Troubleshooting | Completed | 2024-03-12 | 2024-03-12 | 2 | [37 empty] | Troubleshooting done. | [151 empty] | 45666
54 | Activity not clear | Support 5GC team for DB IP telnet issue. | ACI | Support Activity | Completed | 2024-03-12 | 2024-03-12 | 2 | [37 empty] | Required support provided. | [151 empty] | 45667
55 | 12-03-24-264 | Meeting with DCAP dev, Cisco and NPE team. | ACI | Support Activity | Completed | 2024-03-12 | 2024-03-12 | 2 | [37 empty] | Attended meeting. | [151 empty] | 45668
56 | 13-03-24-265 | BoQ preparation for Jamnagar and Mumbai replica lab. | ACI | Documentation | Completed | 2024-03-13 | 2024-03-26 | 6 | [38 empty] | Boq | Boq |  |  |  | Diagram prepared for Bangalore multipod design. |  | BoQ | BoQ | [142 empty] | 45669
57 | 13-03-24-266 | Support for Rama4 setup migrate to IP access | ACI | Support Activity | Completed | 2024-03-13 | 2024-03-13 | 2 | [38 empty] | Required info provided. | [150 empty] | 45670
58 |  | Discussion on airfiber voice routing. | ACI | Support Activity | Completed | 2024-03-14 | 2024-03-14 | 2 | [39 empty] | discussed | [149 empty] | 45671
59 | 14-03-24-267 | NTP sync issue in all nodes of KA_UDM,5G-EIR,AUSF,HSS in Kolkata | ACI | Production Troubleshooting | Completed | 2024-03-14 | 2024-03-14 | 2 | [39 empty] | Issue seems in server side. | [149 empty] | 45672
60 | 14-03-24-268 | IPDR CGNAT reachability issue. | ACI | Lab Troubleshooting | Completed | 2024-03-14 | 2024-03-15 | 2 | [39 empty] | Asked to check server side interface. | [149 empty] | 45673
61 | 15-03-24-269 | Ixia setup in RDP | ACI/NXOS | Support Activity | Completed | 2024-03-15 | 2024-03-27 | 5 | [40 empty] | copy error from other machine | Enable intenet and downloading software |  | Ix network is installed, IxLoad installation error. |  |  |  | .NET ramwork and iXload installation | [141 empty] | 45674
62 | 15-03-24-277 | Reachability issue between Replica ACS server(2405:200:1410:1409:10:64:77:231) and Replica HL1 UE pool | ACI | Lab Troubleshooting | Completed | 2024-03-15 | 2024-03-15 | 2 | [40 empty] | Required action has been taken with IP-MPLS team. | [148 empty] | 45675
63 | 18-03-24-278 | Reachability between Jamnagar and Mumbai HSS/UDM Server. | ACI | Provisioning and Configuration | Completed | 2024-03-18 | 2024-03-18 | 2 | [41 empty] | Reachability has been done. | [147 empty] | 45676
64 | 18-03-24-279 | Jio NMS to IPM server packet drop issue. | ACI | Lab Troubleshooting | Completed | 2024-03-18 | 2024-03-20 | 2 | [41 empty] | We have not observed any issue while pinging from gw to gw. | [147 empty] | 45677
65 | 18-03-24-280 | Check 5G ENT deployment in Vikashpuri | ACI | Support Activity | Completed | 2024-03-18 | 2024-03-19 | 2 | [41 empty] | Discuss with 5G tac and IOT team. Verified TOR deployment as per p2p. | [147 empty] | 45678
66 | 19-03-24-292 | reachability of Wi-Fi Boards from IOT. | ACI | Provisioning and Configuration | Completed | 2024-03-19 | 2024-03-19 | 2 | [42 empty] | Reachability has been done. | [146 empty] | 45679
67 | 19-03-24-293 | FMS to IDC OSS server reachability. | ACI | Provisioning and Configuration | Completed | 2024-03-19 | 2024-03-19 | 2 | [42 empty] | Reachability has been done. | [146 empty] | 45680
68 | 19-03-24-294 | Genie IAT Telco to SIT reacability. | ACI | Support Activity | Completed | 2024-03-19 | 2024-03-19 | 2 | [42 empty] | Discussed and provided required info. | [146 empty] | 45681
69 | 20-03-24-295 | ERSPAN requiremrnt to new NIP server. | ACI | Provisioning and Configuration | Completed | 2024-03-20 | 2024-03-20 | 2 | [42 empty] | Migrated to new NIP server. | [146 empty] | 45682
70 | 20-03-24-296 | NR UP IP to LTE UP IP reachibiity. | ACI | Provisioning and Configuration | Completed | 2024-03-20 | 2024-03-20 | 2 | [43 empty] | Reachability has been done. | [145 empty] | 45683
71 | 20-03-24-297 | LTE IP is not reachable from NR UP IP. | ACI | Lab Troubleshooting | Completed | 2024-03-20 | 2024-03-20 | 2 | [43 empty] | Reachability has been done. | [145 empty] | 45684
72 | 20-03-24-298 | Connectivity issue between internal Production servers at FMS. | ACI | Production Troubleshooting | Completed | 2024-03-20 | 2024-03-20 | 2 | [43 empty] | We have checked in ACI fabric, and we have not found any anomaly that can cause the connectivity issue on mentioned timestamped . | [145 empty] | 45685
73 | 20-03-24-291 | LIC setup switches went down abruptly | ACI | Lab Troubleshooting | Completed | 2024-03-20 | 2024-04-03 | 2 | [43 empty] | Switch went down due to high tem. TAC case rasied | [145 empty] | 45686
74 | 20-03-24-299 | gNB 513 control plane IP to LTE UP reachability | ACI | Lab Troubleshooting | Completed | 2024-03-20 | 2024-03-20 | 2 | [43 empty] | Reachability has been done. | [145 empty] | 45687
75 | 21-03-24-300 | 2 FMS server login issue. | ACI | Lab Troubleshooting | Completed | 2024-03-21 | 2024-03-21 | 2 | [44 empty] | Required connectivity is done. | [144 empty] | 45688
76 | 21-03-24-301 | Mirror traffic routing to different NIP server. | ACI | Provisioning and Configuration | Completed | 2024-03-21 | 2024-03-21 | 2 | [44 empty] | Required connectivity is done. | [144 empty] | 45689
77 | 21-03-24-302 | Connectivity required for NIP server testing. | ACI | Lab Troubleshooting | Completed | 2024-03-21 | 2024-03-21 | 2 | [44 empty] | Required connectivity is done. | [144 empty] | 45690
78 | 22-03-24-303 | P2p config for NIP server. | ACI | Provisioning and Configuration | Completed | 2024-03-22 | 2024-03-22 | 2 | [45 empty] | Config is done. | [143 empty] | 45691
v | 22-03-24-304 | Audit for 5G fabric location. | ACI | Documentation | Completed | 2024-03-22 | 2024-04-22 | 4 | [45 empty] | 5G location list | Audit | Audit | [141 empty] | 45692
80 | 26-03-24-305 | Reachability issue in 2 servers for NIP. | ACI | Lab Troubleshooting | Completed | 2024-03-26 | 2024-03-26 | 2 | [46 empty] | Reachability has been done. | [142 empty] | 45693
81 | 27-03-24-311 | DCAP automation testing. | ACI | Support Activity | Completed | 2024-03-27 | 2024-09-06 | 8 | [47 empty] | discussion |  |  |  | call with DCAP dev team for lab data import in DCAP BD. | [32 empty] | testing with DCAP team |  | testing with DCAP team | testing with DCAP team |  |  |  |  | DCAP | DCAP | [95 empty] | 45694
82 | 27-03-24-312 | User creation in new RDP for sairam. | ACI/NXOS | Support Activity | Completed | 2024-03-27 | 2024-03-27 | 31 | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | [18 empty] | Needful has been done. | [141 empty] | 45695
83 | 28-03-24-313 | 5G NF Reachability issue in Kalyan. | ACI | Production Troubleshooting | Completed | 2024-03-28 | 2024-03-28 | 31 | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | [19 empty] | Fiber issue | [140 empty] | 45696
84 | 28-03-24-314 | NIP server reachability. | ACI | Lab Troubleshooting | Completed | 2024-03-28 | 2024-03-28 | 2 | [48 empty] | Reachability is done. | [140 empty] | 45697
85 | 28-03-24-315 | CnBNG inter cluster connectivity issue. | ACI | Lab Troubleshooting | Completed | 2024-03-28 | 2024-03-29 | 3 | [48 empty] | Reachability is done. |  | Reachability has been done. | [138 empty] | 45698
86 | 28-03-24-316 | Cisco switches immersion in LIC setup | ACI | Solution Testing | Completed | 2024-03-28 | 2024-04-05 | 7 | [48 empty] | Mail communication started with Cisco. |  | Prepared topology and shared with cisco to take it forward. |  | Meeting with Dell and Atul Sir | Design digram, BoQ | [6 empty] | Discussed and shared setup topology with cisco. | [8 empty] | Meeting with Amogh | [119 empty] | 45699
| 29-03-24-317 | Replica node reachability issue from jump server. | ACI | Support Activity | Completed | 2024-03-29 | 2024-03-29 | 2 | [49 empty] | Informed IOT team regarding the issue. | [139 empty] | 45700
| 29-03-24-318 | Common DPI solution testing. | ACI | Solution Testing | Completed | 2024-03-29 | 2024-05-17 | 12 | [49 empty] | Troubleshooting call with Cisco team. |  | Troubleshooting |  |  |  |  | Worked with Cisco TAC |  |  |  |  | Webex with Cisco TAC | Webex with Cisco TAC and shared prod tenant config. |  | Webex with Cisco TAC. | Config changes as recommended by TAC | shared requested logs and tech support files. |  | Webex with Cisco TAC and BU. |  | Webex with Cisco TAC and BU. |  |  | Below is the sequence of scenarios tested in the lab during DPI solution testing: 1. Internet for IPv4 and XLAT services were not working in DPI two node PBR solution. We raised TAC case for this issue. 2. As per Cisco TAC, Implemented solution is not supported. Cisco TAC/BU/DU has suggested workaround where we have to explicitly leak the DPI ingress route from “RJIL-5G-DATA-DPI-SUBSCRIBER” vrf to “RJIL-GLOBAL” vrf. (BU confirmed that this solution is still not recommended with workaround and during any outage in production they will not be able to provide any RCA). 3. As per Cisco suggestion we leaked routes between DPI ingress and Global vrf and internet starts working for both IPv4 and XLAT. 4. We reverted the IPv4 route-leaking workaround, but the IPv6 workaround remained configured. Despite this, no ping drop was observed for IPv4. We need to understand this behaviour from Cisco. 5. When we reverted the IPv6 route-leaking workaround, IPv4 ping stopped working. We need Cisco to confirm the link between IPv4 and IPv6 route leaking. 6. All Cisco requested logs in this non-working scenario were captured and shared with TAC. 7. We reapplied the workaround for both IPv4 and IPv6 but observed intermittent ping drops for about 4 minutes before the ping stabilized. 8. Logs in the working scenario were shared with Cisco. | [115 empty] | 45701
| 22-04-24-394 | Internet reachability issue for FTTX user. | ACI | Lab Troubleshooting | Completed | 2024-04-22 | 2024-04-22 | 2 | [55 empty] | Troubleshooting for Internet reachability issue for FTTX user. | [133 empty] | 45702
| 23-04-24-395 | FMS to SIT server reachability. | ACI | Lab Troubleshooting | Completed | 2024-04-23 | 2024-04-23 | 2 | [56 empty] | Observationshared with team. | [132 empty] | 45703
| 23-04-24-396 | Verification of QoS marking for FMS vlan 3872 in production. | ACI | Production Troubleshooting | Completed | 2024-04-23 | 2024-04-23 | 3 | [56 empty] | Observationshared with team. |  |  |  | Verified in prod that CS5 qos config is done and same is inform to team. | [128 empty] | 45704
| 24-04-24-397 | Internet reachability issue of IPv4 and IPv6 from Jamnagar replica Jio Air fibre set up | ACI | Lab Troubleshooting | Completed | 2024-04-24 | 2024-04-24 | 2 | [57 empty] | Server is not responding. | [131 empty] | 45705
| 24-04-24-398 | VPC down issue for Jio Enterprise UPF in Delhi Vikaspuri AG3. | ACI | Production Troubleshooting | Completed | 2024-04-24 | 2024-04-24 | 3 | [58 empty] | Cabling issue. | List prepared. | [129 empty] | 45706
| 25-04-24-399 | Production issue list of IP network that impacted 5G service. | ACI | Documentation | Completed | 2024-04-25 | 2024-04-25 | 1 | [189 empty] | 45707
| 29-04-24-413 | LIC servers rechability issue. | ACI | Lab Troubleshooting | Completed | 2024-04-29 | 2024-04-29 | 2 | [60 empty] | Switch went down due to high temp. | [128 empty] | 45708
| 29-04-24-414 | TOR source ip and NIP server destination IP details are required by NIP QA team. | ACI | Support Activity | Completed | 2024-04-29 | 2024-04-29 | 2 | [60 empty] | shared required details. | [128 empty] | 45709
| 30-04-24-415 | ssh access issue in 3 FMS server in LIC setup. | ACI | Lab Troubleshooting | Completed | 2024-04-30 | 2024-04-30 | 2 | [61 empty] | issue is resolved post server reboot. | [127 empty] | 45710
| 30-04-24-416 | Internet reachability issue for Airfiber user. | ACI | Lab Troubleshooting | Completed | 2024-04-30 | 2024-04-30 | 2 | [61 empty] | Discussed and req. observation shared. | [127 empty] | 45711
| 00-01-00-417 | Traffic mirroring for 3913 VLAN from TOR 510,560 and 575 to NIP server. | ACI | Provisioning and Configuration | Completed |  |  | 2 | [62 empty] | config is done. | [126 empty] | 45712
| 03-05-24-418 | Major Incident ¦¦ >5% Airfiber SUB6 Customer impacted in RJ circle ¦ Service NOC ¦¦ IIM254438546 | ACI | Production Troubleshooting | Completed | 2024-05-03 | 2024-05-03 | 2 | [63 empty] | Analysis has been shared. | [125 empty] | 45713
| 03-05-24-419 | IM252479094\\RE: KOL ens4f0 PORT Fluctuation ¦¦ PCF | ACI | Production Troubleshooting | Completed | 2024-05-03 | 2024-05-03 | 2 | [63 empty] | Analysis has been shared. | [125 empty] | 45714
| 06-05-24-420 | VLAN 3910 CP to DP intermittent reachability Issue ¦¦ Vikaspuri Enterprise Setup | ACI | Production Troubleshooting | Completed | 2024-05-06 | 2024-05-06 | 3 | [64 empty] | Analysis has been shared. | Discuss with Cisco team for config changes. | [123 empty] | 45715
| 08-05-24-421 | Prod AKS cluster to Jio FMS server rechability issue. | ACI | Production Troubleshooting | Completed | 2024-05-08 | 2024-05-08 | 2 | [66 empty] | Reverse route was not configured in FMS server. | [122 empty] | 45716
| 09-05-24-422 | PIOTA to FMS server connectivity. | ACI | Lab Troubleshooting | Completed | 2024-05-09 | 2024-05-09 | 2 | [67 empty] | Pending at IDC and IDC cloud team. | [121 empty] | 45717
| 09-05-24-423 | Automatic disconnect for xshell session ¦ BLR SC | ACI | Production Troubleshooting | Completed | 2024-05-09 | 2024-05-09 | 2 | [67 empty] | Requested details are not received to check further. | [121 empty] | 45718
| 09-05-24-424 | Packet loss in DNS reachability from Nagpur Moudha AirFiber UPF ¦¦ IM255606273 | ACI | Production Troubleshooting | Completed | 2024-05-09 | 2024-05-10 | 3 | [67 empty] | No drop observed from TOR. | Requested details are not received to check further. As discussed with UPF TAC some fiber activity has been performed win that JC site. | [120 empty] | 45719
| 13-05-24-425 | Spirent pool reachability with AMF. | ACI | Provisioning and Configuration | Completed | 2024-05-13 | 2024-05-13 | 2 | [69 empty] | Reachability has been done. | [119 empty] | 45720
| 14-05-24-426 | SWIM server pre requisite readiness for CIMC via SWIM. | ACI | Lab Troubleshooting | Completed | 2024-05-14 | 2024-05-14 | 2 | [70 empty] | Required readiness has been done. | [118 empty] | 45721
| 14-05-24-427 | NTP Offset issue in Hyderabad & Bangalore NSSF SC | ACI | Production Troubleshooting | Completed | 2024-05-14 | 2024-05-14 | 2 | [70 empty] | Observation shared. No issue observed from network end. | [118 empty] | 45722
| 15-05-24-428 | JioNMS server reachability issue in LIC setup. | ACI | Lab Troubleshooting | Completed | 2024-05-15 | 2024-05-15 | 1 | [189 empty] | 45723
| 16-05-24-429 | Infosec scanning of telco fabric | ACI | Support Activity | Completed | 2024-05-16 | 2024-05-16 | 2 | [72 empty] | discussed and Detail shared | [116 empty] | 45724
| 17-05-24-430 | Meeting for Jio vault setup. | ACI | Support Activity | Completed | 2024-05-17 | 2024-05-17 | 2 | [73 empty] | Meeting with Dev, lab team and PKB sir. It was decided by PKB sir that preprod setup will be installed in IDC. | [115 empty] | 45725
| 17-05-24-431 | VRF migration Jamnagar vBL-iBL and BGLR 7K vBL-iBL peering. | ACI | Provisioning and Configuration | Completed | 2024-05-17 | 2024-05-27 | 4 | [73 empty] | review of migration activity. |  |  |  | New L3 out config iBL to CAS | VRF Migration | [110 empty] | 45726
| 21-05-24-470 | Troubleshooting of reachability and ssh issue of swim python server. | ACI | Support Activity | Completed | 2024-05-21 | 2024-05-21 | 2 | [74 empty] | reachability is done and ssh issue is resolved. | [114 empty] | 45727
| 21-05-24-471 | RJIO LAB_CLI Spoofing_New nodes reachability with iCampaign server. | ACI | Lab Troubleshooting | Completed | 2024-05-21 | 2024-05-23 | 3 | [74 empty] | Gw to gw reachability is there. |  |  | Troubleshooting call. | [111 empty] | 45728
| 22-05-24-472 | Jamnagaer Replica server Port Down Issue. | ACI | Lab Troubleshooting | Completed | 2024-05-22 | 2024-05-22 | 2 | [75 empty] | Obseration shared. | [113 empty] | 45729
| 23-05-24-473 | CIMC test cases preparation. | ACI | Documentation | Completed | 2024-05-23 | 2024-05-23 | 2 | [76 empty] | Doc. Shared with team. | [112 empty] | 45730
| 23-05-24-474 | New JioAirfiber reachability issue in Ahmedabad SAG2. | ACI | Production Troubleshooting | Completed | 2024-05-23 | 2024-05-23 | 2 | [76 empty] | Observation shared with team. | [112 empty] | 45731
| 23-05-24-475 | Dell 100G SR BIDI SFP compatibility test with CISCO ACI Switch. | ACI | Support Activity | Completed | 2024-05-23 | 2024-05-23 | 2 | [76 empty] | work when both end Dell SFP's are connected. | [112 empty] | 45732
| 24-05-24-476 | UPF CP OAM reachability issue in jamnagar replica. | ACI | Lab Troubleshooting | Completed | 2024-05-24 | 2024-05-24 | 2 | [77 empty] | Required support provided. | [111 empty] | 45733
| 27-05-24-482 | VLAN configuration for UPF dev replica server | ACI | Provisioning and Configuration | Completed | 2024-05-27 | 2024-05-27 | 2 | [78 empty] | Config is done as per requirement. | [110 empty] | 45734
| 27-05-24-483 | CCS LB to FMS server reachability issue. | ACI | Lab Troubleshooting | Completed | 2024-05-27 | 2024-05-27 | 2 | [78 empty] | Observation shared. | [110 empty] | 45735
| 28-05-24-484 | Jio vault server reachability issue from 5G subscriber. | ACI | Production Troubleshooting | Completed | 2024-05-28 | 2024-05-28 | 2 | [79 empty] | UPF is not forwarding packet towards N6 interface as supernet is configured towards N3. Lab team changed unique public ipv6 ip for jio vault. | [109 empty] | 45736
| 28-05-24-485 | Meeting with splunk vendor. | Splunk | Support Activity | Completed | 2024-05-28 | 2024-05-28 | 2 | [79 empty] | meeting | [109 empty] | 45737
| 29-05-24-486 | Internet issue in AirFIber JamaNagar Replica setup. | ACI | Lab Troubleshooting | Completed | 2024-05-29 | 2024-05-29 | 2 | [80 empty] | Firewall issue was rectified. | [108 empty] | 45738
| 29-05-24-487 | TOR was not receiving routes from UPF in Delhi Vikashpuri 5G Enterprise site. | ACI | Production Troubleshooting | Completed | 2024-05-29 | 2024-05-30 | 3 | [80 empty] | works after changing config in aci | works after changing config in aci | [107 empty] | 45739
| 30-05-24-488 | Internet issue for ipv4 in Jamnagar airfiber setup. | ACI | Lab Troubleshooting | Completed | 2024-05-30 | 2024-05-30 | 2 | [81 empty] | CGNAT interface was down. | [107 empty] | 45740
| 30-05-24-489 | IOT BTAS to replica DNS reachability . | NXOS | Lab Troubleshooting | Completed | 2024-05-30 | 2024-05-30 | 2 | [81 empty] | Reachability done. | [107 empty] | 45741
| 31-05-24-490 | Reachability between DEV SBC setup to Exfo tester, DNS and SIB. | NXOS | Provisioning and Configuration | Completed | 2024-05-31 | 2024-05-31 | 2 | [82 empty] | Reachability has been done. | [106 empty] | 45742
| 31-05-24-491 | Attended F5 DNS product presentation session. | DNS | Support Activity | Completed | 2024-05-31 | 2024-05-31 | 2 | [82 empty] | Attended | [106 empty] | 45743
| 01-06-24-492 | ODSC port down issue. | ACI | Support Activity | Completed | 2024-06-01 | 2024-06-01 | 2 | [83 empty] | No issue at switch end. Port is showing up. | [105 empty] | 45744
| 03-06-24-493 | UPF servers are showing error in Jamnagar. | ACI | Lab Troubleshooting | Completed | 2024-06-03 | 2024-06-03 | 2 | [84 empty] | Port flap observed. No LACP PDUerror for DP port | [104 empty] | 45745
| 03-06-24-494 | Reachability from Spirent to PCF/PCRF . | ACI | Lab Troubleshooting | Completed | 2024-06-03 | 2024-06-03 | 2 | [84 empty] | Reverse route issue at server end. | [104 empty] | 45746
| 04-06-24-593 | Hyderabad JDC Airfiber ASBC is not reachable from UPF BNG. | ACI | Production Troubleshooting | Completed | 2024-06-04 | 2024-06-07 | 3 | [85 empty] | Troubleshooting | Troubleshooting | [102 empty] | 45747
| 05-06-24-594 | BTAS - replica DNS reachability issue | ACI | Lab Troubleshooting | Completed | 2024-06-05 | 2024-06-05 | 2 | [86 empty] | Reachabilitu done. | [102 empty] | 45748
| 06-06-24-595 | IoT P-SBC IP reachability from Replica S-CSCF | ACI | Lab Troubleshooting | Completed | 2024-06-06 | 2024-06-06 | 2 | [87 empty] | Reachabilitu done. | [101 empty] | 45749
| 06-06-24-596 | ERSPAN config requirement for mumbai setup. | ACI | Provisioning and Configuration | Completed | 2024-06-06 | 2024-06-06 | 2 | [87 empty] | Config is done. | [101 empty] | 45750
| 07-06-24-597 | MW Node reachability from the RDP-2405:201:fffb:94::1626 | NXOS | Provisioning and Configuration | Completed | 2024-06-07 | 2024-06-07 | 2 | [88 empty] | Reachability is done. | [100 empty] | 45751
| 07-06-24-598 | ERSPAN config requirement for Jamnagar replica setup. | ACI | Provisioning and Configuration | Completed | 2024-06-07 | 2024-06-07 | 2 | [88 empty] | Config is done. | [100 empty] | 45752
| 10-06-24-599 | SITAKSCluster to FMSConnectivityIssue | ACI | Support Activity | Completed | 2024-06-10 | 2024-06-10 | 2 | [89 empty] | config done | [99 empty] | 45753
| 11-06-24-600 | 5G CLIR transactions are still getting failed in LIC setup. | ACI | Support Activity | Completed | 2024-06-11 | 2024-06-11 | 2 | [90 empty] | Trroublwshooting done. | [98 empty] | 45754
| 12-06-24-601 | IoT Dev SBC Megaco interface connectivity with the Replica Bangalore CFX | ACI | Lab Troubleshooting | Completed | 2024-06-12 | 2024-06-12 | 2 | [91 empty] | reachability | [97 empty] | 45755
| 12-06-24-614 | reachability between Dev UPF and CLMS server. | ACI | Lab Troubleshooting | Completed | 2024-06-12 | 2024-06-12 | 2 | [91 empty] | routing done | [97 empty] | 45756
| 13-06-24-615 | SMF BNGs VLAN ERSPAN requirement. | ACI | Lab Troubleshooting | Completed | 2024-06-13 | 2024-06-13 | 2 | [92 empty] | routing done | [96 empty] | 45757
| 13-06-24-552 | Verify whether Palo Alto header added in ERSPAN packet when PTP is disabled. | ACI | Lab Troubleshooting | Completed | 2024-07-02 | 2024-07-02 | 2 | [94 empty] | Palo Alto header is not added in ERSPAN packet when PTP is disabled. | [94 empty] | 45758
| 03-07-24-616 | Server Reachability for DBIQ replica setup and FMS IOT Environment | ACI | Lab Troubleshooting | Completed | 2024-07-03 | 2024-07-03 | 2 | [95 empty] | Reachability is done. | [93 empty] | 45759
| 04-07-24-617 | BoQ preparation and SFP requirement for LIC setup. | ACI | Documentation | Completed | 2024-07-04 | 2024-07-04 | 2 | [96 empty] | Requirement shared with NPE. | [92 empty] | 45760
| 05-07-24-618 | Reachability of Ericsson E-band node on the Jamnagar ENM Server. | ACI | Provisioning and Configuration | Completed | 2024-07-05 | 2024-07-05 | 2 | [97 empty] | Reachability is done. | [91 empty] | 45761
| 05-07-24-619 | MANO IOT Testing servers iLO reachability issue | ACI | Lab Troubleshooting | Completed | 2024-07-05 | 2024-07-05 | 2 | [97 empty] | MAC is not learning. | [91 empty] | 45762
| 08-07-24-620 | Downlink data is not working for some UE in keysight setup. | ACI | Lab Troubleshooting | Completed | 2024-07-08 | 2024-07-09 | 3 | [98 empty] | troubleshooting call | troubleshooting call | [89 empty] | 45763
| 08-07-24-621 | IPv6 IPDR configuration for FTTx traffic on bangalore fabric. | ACI | Provisioning and Configuration | Completed | 2024-07-08 | 2024-07-08 | 2 | [98 empty] | config is done. | [90 empty] | 45764
| 10-07-24-622 | Switch replacement activity in LIC setup. | ACI | Provisioning and Configuration | Completed | 2024-07-10 | 2024-07-10 | 2 | [100 empty] | both swicthes have been replaced. | [88 empty] | 45765
| 10-07-24-623 | Review and update of NDI test case. | ACI | Documentation | Completed | 2024-07-10 | 2024-10-15 | 5 | [100 empty] | shared | discussion | [52 empty] | Update L1 test plan | [6 empty] | updated | [27 empty] | 45766
| 12-07-24-671 | Jaipur 5G GNB OAM connectivity issue analysis. | ACI | Production Troubleshooting | Completed | 2024-07-12 | 2024-07-12 | 2 | [102 empty] | JPURMTNRCESB01 to SAR1 and SAR2 BGP peering was down. Service was running via JPURMTNRCESB51. JPURMTNRCESB51 was rebooted due to memory issue. GNB OAM connectivity was lost during reload. NOC TAC team has made BGP up between JPURMTNRCESB01 to SAR1 and SAR2. | [86 empty] | 45767
| 12-07-24-672 | Connectivity b/w SBC &SIB server. | ACI | Lab Troubleshooting | Completed | 2024-07-12 | 2024-07-12 | 2 | [102 empty] | reachability is done. | [86 empty] | 45768
| 15-07-24-673 | Data is not working in Keysight seup | ACI | Lab Troubleshooting | Completed | 2024-07-15 | 2024-07-15 | 2 | [104 empty] | Routing done. | [84 empty] | 45769
| 15-07-24-674 | Data is not working in Simnovus seup | ACI | Lab Troubleshooting | Completed | 2024-07-15 | 2024-07-15 | 2 | [104 empty] | Routing done. | [84 empty] | 45770
| 16-07-24-675 | Data is not working in via IOT UDG server. | ACI | Lab Troubleshooting | Completed | 2024-07-16 | 2024-07-16 | 2 | [104 empty] | Routing done. | [84 empty] | 45771
| 16-07-24-676 | Fabric Log collector Server setup and testing. | ACI | MoP Validation | Completed | 2024-07-16 | 2024-08-05 | 10 | [105 empty] | config done. |  | script is not running properly. Informed cisco. | troubleshooting on space issue in VM |  |  | script started for 2 fabric with rollover time 3 days. | [17 empty] | Deployed updated script and shared observation. |  |  |  | testing | testing |  | observation shared |  | Webex with cisco team. Shared observation. | [50 empty] | 45772
| 16-07-24-677 | Genie ATM, FLB, Analytics nodes are unreachable | ACI | Lab Troubleshooting | Completed | 2024-07-16 | 2024-07-16 | 2 | [104 empty] | server not reachable locally. | [84 empty] | 45773
| 17-07-24-678 | Bandwidth rate limiting feature testing in NX-OS 5K switch. | ACI | Feature Testing | On Hold | 2024-07-17 |  | 2 | [105 empty] | No option to config qos in output as like 9k | [83 empty] | 45774
| 17-07-24-679 | Jio OSS FMS servers went unreachable. Even 5G onboarding and Airfiber services got impacted during this activity. | ACI | Production Troubleshooting | Completed | 2024-07-17 | 2024-07-17 | 2 | [105 empty] | Server active interface was down from server side. Outage occurred during standby switch image upgrade. | [83 empty] | 45775
| 18-07-24-680 | EXSi log in issue for the 10.64.91.132 server. | DNS | Support Activity | Completed | 2024-07-18 | 2024-07-18 | 2 | [106 empty] | Server rebooted. | [82 empty] | 45776
| 17-07-24-681 | Slow uploading issue in Jiovault. | ACI | Support Activity | Completed | 2024-07-17 | 2024-07-18 | 4 | [105 empty] | Call | As per ping end to end delay within 50ms. | meeting | [81 empty] | 45777
| 22-07-24-682 | IP Pool 100.88.X.X is not reachable from App-server (Jio blade server ) 10.63.73.228. | ACI | Lab Troubleshooting | Completed | 2024-07-22 | 2024-07-22 | 2 | [108 empty] | routing is done. | [80 empty] | 45778
| 25-07-24-683 | HTTPLB failover in AMF Dhanbad location. | ACI | Production Troubleshooting | Completed | 2024-07-25 | 2024-07-26 | 3 | [109 empty] | observation shared | discuused and requested details shared. | [78 empty] | 45779
| 29-07-24-732 | Discussion with Boston team regarding LIC setup. | ACI | Support Activity | Completed | 2024-07-29 | 2024-07-29 | 2 | [111 empty] | meeting | [77 empty] | 45780
| 29-07-24-733 | Support and guidance to Konda for CGNAT seup. | CGNAT | Support Activity | Completed | 2024-07-29 | 2024-07-29 | [112 empty] | support provided | [77 empty] | 45781
| 30-07-24-734 | CLM portal Access for DNS NPE. | Other Domain | Support Activity | Completed | 2024-07-30 | 2024-07-30 | 2 | [112 empty] | support provided | [76 empty] | 45782
| 30-07-24-735 | CLMS access for CGNAT NOC. | Other Domain | Support Activity | Completed | 2024-07-30 | 2024-07-30 | 2 | [112 empty] | access provided. | [76 empty] | 45783
| 31-07-24-736 | FMS Replica to JCP connectivity issue. | ACI | Lab Troubleshooting | Completed | 2024-07-31 | 2024-07-31 | 2 | [113 empty] | guided FMS team for forward path. | [75 empty] | 45784
| 31-07-24-737 | UPF BNG setup to log collector reachability. | ACI | Provisioning and Configuration | Completed | 2024-07-31 | 2024-07-31 | 2 | [113 empty] | reachability is done. | [75 empty] | 45785
| 01-08-24-738 | ping issue with 1500 MTU in private 5G setup. | ACI | Production Troubleshooting | Completed | 2024-08-01 | 2024-08-01 | 2 | [114 empty] | it is identified that all packet fragments from Genetec server to UE at 1500 MTU with 10.250.55.XX series IP are reaching to UPF, but not reaching to ODCPE. However when pinging to UE to Genetic server all the packet fragments are not reaching. ODCPE/RAN team to check. | [74 empty] | 45786
| 01-08-24-739 | Adverb Ware House Automation and private 5G solution - discussion. | NXOS | Support Activity | Completed | 2024-08-01 | 2024-08-01 | 2 | [114 empty] | attended | [74 empty] | 45787
| 01-08-24-740 | Discussion on Enabling High LPM Profile for Telco DC ACI. | ACI | Support Activity | Completed | 2024-08-01 | 2024-08-01 | 2 | [114 empty] | attended call and we have raised our queries. | [74 empty] | 45788
| 31-07-24-741 | DNS not reachable for FTTX subscriber ¦¦ Radysis OLT | ACI | Support Activity | Completed | 2024-07-31 | 2024-07-31 | 2 | [113 empty] | troubleshooting | [75 empty] | 45789
| 31-07-24-742 | Internet reachability issue for vEPDG setup. | ACI | Support Activity | Completed | 2024-07-31 | 2024-07-31 | 2 | [113 empty] | troubleshooting | [75 empty] | 45790
| 02-08-24-787 | 5G Airfiber user in the Ahmedabad MCN location was unable to browse websites destined for IPv4 (XLAT services) | ACI | Production Troubleshooting | Completed | 2024-08-02 | 2024-08-06 | 3 | [115 empty] | Issue analysis | Issue analysis | [72 empty] | 45791
| 06-08-24-788 | Support MW team for CLM creation for ATP. | Other Domain | Support Activity | Completed | 2024-08-06 | 2024-08-06 | 3 | [116 empty] | Support provided. | Support provided. | [71 empty] | 45792
| 07-08-24-789 | NTP IP reachability for Mobileum nodes. | ACI | Support Activity | Completed | 2024-08-07 | 2024-08-13 | 3 | [117 empty] | Support provided. |  |  |  | reachability done. | [67 empty] | 45793
| 08-08-24-790 | Reachability issue between jamnagar SMF and Mumbai MME. | ACI | Lab Troubleshooting | Completed | 2024-08-08 | 2024-08-08 | 2 | [118 empty] | reachability done. | [70 empty] | 45794
| 08-08-24-791 | CLM acces to IPSE NPE. | Other Domain | Support Activity | Completed | 2024-08-08 | 2024-08-08 | 2 | [118 empty] | Support provided. | [70 empty] | 45795
| 09-08-24-792 | DNS resolution issue from CCDU. | ACI | Lab Troubleshooting | Completed | 2024-08-09 | 2024-08-09 | 2 | [119 empty] | Support provided. | [69 empty] | 45796
| 09-08-24-793 | Reachability issue from Replica SMF to AMF. | ACI | Lab Troubleshooting | Completed | 2024-08-09 | 2024-08-09 | 2 | [119 empty] | reachability done. | [69 empty] | 45797
| 12-08-24-799 | Mapping of ACI and CGNAT location. | ACI | Documentation | Completed | 2024-08-12 | 2024-08-12 | 2 | [120 empty] | doc shared. | [68 empty] | 45798
| 13-08-24-800 | Discussion on server Reconciliation of Unused Servers at TC 23 Mumbai QA Labs | Other Domain | Support Activity | Completed | 2024-08-13 | 2024-08-14 | 3 | [120 empty] | discussed with team. | discussed with team. | [67 empty] | 45799
| 13-08-24-801 | AI/ML setup and NXOS 10.5.1 image upgrade. | NXOS | Support Activity | Completed | 2024-08-13 | 2024-08-16 | 5 | [121 empty] | Mail send to cisco with queries. |  |  |  | Deployed updated script and shared observation. | [27 empty] | QoS marked Traffic generation from server. | QoS marked Traffic generation from server. | [34 empty] | 45800
| 14-08-24-802 | AI fabric design for 16k GPU. | NXOS | Documentation | Completed | 2024-08-14 | 2024-08-27 | 7 | [122 empty] | discussed and draft diagram shared. | prepared diagram in visio | worked with Transport team. |  |  | Review | updated write up | updated write up shared | [59 empty] | 45801
| 12-08-24-803 | DCAP automation use case validation. | NDO | Support Activity | On Hold | 2024-08-12 |  | 6 | [120 empty] | support provided | support provided | support provided | support provided | Issue list updated. | [64 empty] | 45802
| 19-08-24-804 | LIC server reachability issue. | ACI | Lab Troubleshooting | Completed | 2024-08-19 | 2024-08-19 | 2 | [124 empty] | observation shared. | [64 empty] | 45803
| 26-08-24-850 | Connectivity from FMS sit setup to JIO OC | ACI | Lab Troubleshooting | Completed | 2024-08-26 | 2024-08-27 | 3 | [128 empty] | Discussed with team and suggested solution | discussed with concern team | [59 empty] | 45804
| 28-08-24-851 | Connectivity to UPF1 with Jio ASBC | ACI | Lab Troubleshooting | Completed | 2024-08-28 | 2024-08-28 | 2 | [130 empty] | Reachability done. | [58 empty] | 45805
| 29-08-24-852 | Review and exploration of MACsec feature support in ACI. | ACI | Documentation | Completed | 2024-08-29 | 2024-08-29 | 2 | [131 empty] | Observation shared internally. | [57 empty] | 45806
| 30-08-24-853 | Need to make reachability between vmme diameter ip to Spirent Servers TS-31 | ACI | Lab Troubleshooting | Completed | 2024-08-30 | 2024-08-30 | 2 | [132 empty] | Reachability done. | [56 empty] | 45807
| 30-08-24-854 | Preparation of MACsec requirement docs | ACI | Documentation | Completed | 2024-08-30 | 2024-08-30 | [190 empty] | 45808
| 30-08-24-855 | NDFC setup with ND 3.2.1 | NDO | Support Activity | Completed | 2024-08-30 | 09-10.24 | 5 | [132 empty] | ND Setup installation | NDFC setup | [7 empty] | fabric setup | [18 empty] | done | [28 empty] | 45809
| 10-09-24-861 | Ceragon MW node Reachability issue | ACI | Lab Troubleshooting | Completed | 2024-09-10 | 2024-09-11 | 3 | [139 empty] | Troubleshooting | Troubleshooting | [48 empty] | 45810
| 09-09-24-862 | Reachability between replica EDA servers and PCRF server. | ACI | Lab Troubleshooting | Completed | 2024-09-09 | 2024-09-10 | 3 | [138 empty] | Troubleshooting | Troubleshooting | [49 empty] | 45811
| 09-09-24-863 | Work with Cisco TAC for PBR track down issue. | ACI | Lab Troubleshooting | Completed | 2024-09-09 | 2024-09-27 | 5 | [138 empty] | Call with TAC | Call with TAC | Call with TAC and Troubleshooting | shared logs to tac | [47 empty] | 45812
| 09-09-24-864 | Jio Brain connectivity requirement. | ACI | Support Activity | Completed | 2024-09-09 | 2024-09-09 | 2 | [138 empty] | shared feedback. | [50 empty] | 45813
| 11-09-24-865 | Replica Lab - GWU : UE to Spirent reachability issue. | ACI | Lab Troubleshooting | Completed | 2024-09-11 | 2024-09-13 | 4 | [140 empty] | Troubleshooting | Troubleshooting | Troubleshooting | [46 empty] | 45814
| 11-09-24-866 | Discussion with Cisco for AI fabric deployment. | NXOS | Support Activity | Completed | 2024-09-11 | 2024-09-11 | 2 | [140 empty] | discussed | [48 empty] | 45815
| 13-09-24-867 | Call with SBC team for connectivity requirement. | ACI | Support Activity | Completed | 2024-09-13 | 2024-09-13 | 2 | [142 empty] | discussed | [46 empty] | 45816
| 10-09-24-868 | Jamnagar Virtual ePDG not reachable from Spirent TS32 | ACI | Lab Troubleshooting | Completed | 2024-09-10 | 2024-09-10 | 2 | [139 empty] | ePDG is not responding. | [49 empty] | 45817
| 17-09-24-916 | Reachability between STP and DRA. | ACI | Provisioning and Configuration | Completed | 2024-09-17 | 2024-09-18 | 3 | [144 empty] | Detail requested. | Done | [43 empty] | 45818
| 17-09-24-917 | Outage analysis in Mumbai RCP IDC1 due to power down incident. | ACI | Support Activity | Completed | 2024-09-17 | 2024-09-19 | 4 | [144 empty] | Outage analysis | Outage analysis | Outage analysis | [42 empty] | 45819
| 19-09-24-918 | Data not working with lab App server | ACI | Lab Troubleshooting | Completed | 2024-09-19 | 2024-09-19 | 2 | [146 empty] | Reachability done. | [42 empty] | 45820
| 20-09-24-919 | DNS unreachability issue in Jamnagar replica Air fiber set up | ACI | Lab Troubleshooting | Completed | 2024-09-20 | 2024-09-20 | 2 | [147 empty] | Reachability done. | [41 empty] | 45821
| 23-09-24-920 | DCNM GUI opening issue. | DCNM | Lab Troubleshooting | Completed | 2024-09-23 | 2024-09-23 | 2 | [148 empty] | Issue resolved after rebooting VM | [40 empty] | 45822
| 24-09-24-921 | ERSPAN session fault for NIP server. | ACI | Lab Troubleshooting | Completed | 2024-09-24 | 2024-09-26 | 4 | [149 empty] | TAC call | Config | Config | [37 empty] | 45823
| 26-09-24-922 | HSS connectivity with GMLC | ACI | Lab Troubleshooting | Completed | 2024-09-26 | 2024-09-26 | 2 | [151 empty] | Done | [37 empty] | 45824
| 25-09-24-923 | GR update | ACI | Documentation | Completed | 2024-09-25 | 2024-10-09 | 5 | [150 empty] | GR update | GR update | GR discussion | [7 empty] | GR update | [28 empty] | 45825
| 30-09-24-976 | High latency and packet loss issue between Jammu SMF and Chennai NMS. | ACI | Production Troubleshooting | Completed | 2024-09-30 | 2024-09-30 | 2 | [153 empty] | Issue analysis. Fiber cut | [35 empty] | 45826
| 30-09-24-977 | To check whether logsavor script is working with ISE credential. | ACI | Solution Testing | Completed | 2024-09-30 | 2024-10-16 | 4 | [154 empty] | Observation shared with Cisco. |  |  | Observation shared with Cisco. |  |  |  |  | call with cisco to correct script. | [26 empty] | 45827
| 03-10-24-978 | Meeting with Arista | Other Domain | Other | Completed | 2024-10-03 | 2024-10-03 | 2 | [155 empty] | Meeting with Arista | [33 empty] | 45828
| 09-10-24-979 | FMS to 5GCN node reachability. | ACI | Lab Troubleshooting | Completed | 2024-10-09 | 2024-10-09 | 2 | [160 empty] | reachability done. | [28 empty] | 45829
| 09-10-24-980 | LIC FMS server iLO reachability issue. | ACI | Lab Troubleshooting | Completed | 2024-10-09 | 2024-10-09 | 2 | [160 empty] | TOR in inactive state | [28 empty] | 45830
| 10-10-24-981 | Jamnagar UPF pool advertisement issue. | ACI | Lab Troubleshooting | Completed | 2024-10-10 | 2024-10-10 | 2 | [161 empty] | Infrom 5GCN team to stop advertising production UE internet routable pool. | [27 empty] | 45831
| 09-10-24-982 | Common DPI solution with L1 PBR testing. | ACI | Solution Testing | In Progress | 2024-10-09 |  | 6 | [159 empty] | failover testing |  |  |  | failover testing | failover testing | [24 empty] | 45832 | [25 empty] | Yes |  |  | Troubleshooting all with Cisco
| 16-10-24-983 | Reachability between DIAMETER & SIGNALLING GW | ACI | Provisioning and Configuration | Completed | 2024-10-16 | 2024-10-17 | 3 | [165 empty] | Reachability | Reachability | [22 empty] | 45833
| 17-10-24-984 | Reachability issue between Jamnagar Replica Lab EDPG and HPOO server | ACI | Provisioning and Configuration | Completed | 2024-10-17 | 2024-10-18 | 3 | [166 empty] | Reachability | IDC team to do the needful. | [21 empty] | 45834
| 18-10-24-1021 | ASBC server reachablity issue from UPF BNG CL-3 & CL-4 subscriber in Kharagpur MCN location. | ACI | Production Troubleshooting | Completed | 2024-10-18 | 2024-10-21 | 2 | [167 empty] | Observation shared. | [21 empty] | 45835
| 21-10-24-1022 | TAC case for High traffic loss observed during switch reload for DPI L1 PBR solution | ACI | Lab Troubleshooting | Completed | 2024-10-21 | 2025-01-06 | 3 | [168 empty] | TAC case | TAC case | [19 empty] | 45836
| 21-10-24-1023 | Arista switch requirement for lab setup. | Other Domain | Documentation | Completed | 2024-10-21 | 2024-10-21 | 1 | [168 empty] | Arista BoQ
| 22-10-24-1024 | Reachability between REPLICA ISBC to IOT IMS network | ACI | Provisioning and Configuration | Completed | 2024-10-22 | 2024-10-22 | 1 | [169 empty] | done
| 24-10-24-1025 | pNMSJ server Reachability to RDP | NXOS | Provisioning and Configuration | Completed | 2024-10-24 | 2024-10-24 | 1 | [171 empty] | done
| 24-10-24-1026 | Reachability between HSS to SIT server. | NXOS | Provisioning and Configuration | Completed | 2024-10-24 | 2024-10-24 | 1 | [171 empty] | Source and dest. Are not belongs to replica network.
| 13-01-25-1046 | Reachability between HyperLite Setup UDM API IP from SoRAF1 & 2 | ACI | Provisioning and Configuration | Completed | 2025-01-13 | 2025-01-13 | 1 | [246 empty] | Reachability has been done.
| 12-01-25-1047 | reachability between spirent Pools from the AWS IP Pool. | ACI/NXOS | Provisioning and Configuration | Completed | 2025-01-12 | 2025-01-13 | 2 | [245 empty] | Detail requested. |  | Routing is done for new pool
| 10-01-25-1048 | Connectivity between DBIQ and IPSM. | ACI | Lab Troubleshooting | Completed | 2025-01-10 | 2025-01-10 | 1 | [243 empty] | Reachability has been done.
| 09-01-25-1049 | Discussion to Replicate DCAP Production Cluster in LAB for Testing | ACI | New Product Validation | Completed | 2025-01-09 | 2025-01-09 | 1 | [242 empty] | Required detail shared.
| 14-01-25-1050 | ASBC server reachablity from UE pool. | ACI | Lab Troubleshooting | Completed | 2025-01-14 | 2025-01-14 | 1 | [247 empty] | done
| 09-01-25-1051 | SBC iLO reachability. | ACI | Provisioning and Configuration | Completed | 2025-01-09 | 2025-01-10 | 2 | [242 empty] | iLO interface config and reachability | iLO interface config and reachability
| 13-01-25-1052 | SBC to SMF reachability requirement. | ACI | Provisioning and Configuration | Completed | 2025-01-13 | 2025-01-13 | 1 | [246 empty] | done
| 27-11-24-1006 | LIC setup with Cisco switches. | NXOS | Support Activity | In Progress | 2024-11-30 |  | 8 | [202 empty] | Yes |  | Yes | Yes |  |  | Yes |  |  | Yes | [21 empty] | Yes |  | Interface flapping due to SFP heating issue. | [17 empty] | New liquid immersed SFP inserted.
| 00-01-00-1054 | Support for DCAP use case validation. | ACI | Support Activity | In Progress | 2024-12-26 |  | 2 | [229 empty] | Issue discusion | [11 empty] | Meeting with Cisco and NPE
| 00-01-00-1055 | Support for NDI product validation. | ACI | Support Activity | In Progress | 2025-01-13 |  | 2 | [246 empty] | Test case discussion | [10 empty] | Call with Cisco
| 08-01-25-1056 | SBC mgmt. reachability issue. | NXOS | Lab Troubleshooting | Completed | 2025-01-08 | 2025-01-08 | 1 | [241 empty] | Done
| 08-01-25-1057 | Packet loss observed towards Internet | ACI | Lab Troubleshooting | Completed | 2025-01-08 | 2025-01-08 | 1 | [241 empty] | done
| 07-01-25-1058 | Jio SCEF to vDRA reachability. | NXOS | Provisioning and Configuration | Completed | 2025-01-07 | 2025-01-07 | 1 | [240 empty] | Done
| 02-01-25-1059 | NTP Server reachability with SASE FTP server. | ACI | Provisioning and Configuration | Completed | 2025-01-02 | 2025-01-02 | 1 | [235 empty] | Done
| 19-12-24-1060 | EDP server to ESBC reachability. | ACI | Provisioning and Configuration | Completed | 2024-12-19 | 2024-12-30 | 4 | [221 empty] | ESXI interface mapping issue | Detail requested. |  |  |  | Observation shared. | [5 empty] | ESXi issue
| 24-12-24-1061 | Packet drop issue from AKS server to inernet. | ACI | Lab Troubleshooting | Completed | 2024-12-24 | 2024-12-26 | 2 | [226 empty] | Done |  | CGNAT licence issue.
| 11-12-24-1062 | IPSE solution document update for Hondutel. | Other Domain | Documentation | Completed | 2024-12-11 | 2024-12-18 | 2 | [213 empty] | Yes | [6 empty] | Done
| 09-12-24-1063 | Telco Lan solution document update for Hondutel. | ACI | Documentation | Completed | 2024-12-09 | 2024-12-18 | 5 | [211 empty] | Yes |  | Yes |  | Yes |  |  |  | Yes | Shared
| 12-12-24-1064 | EDP server Gw reachability issue . | ACI | Production Troubleshooting | Completed | 2024-12-12 | 2024-12-13 | 2 | [214 empty] | Done | Done
| 05-12-24-1065 | HSS NetAct mgmt ip reachability. | ACI | Lab Troubleshooting | Completed | 2024-12-05 | 2024-12-05 | 1 | [207 empty] | Done
| 05-12-24-1066 | App server reachability issue from UE. | ACI | Lab Troubleshooting | Completed | 2024-12-05 | 2024-12-05 | 1 | [207 empty] | Done
| 25-11-24-1067 | NDI Cluster DB health degraded and other service not in desired state-troubleshooting call with Cisco. | ACI | Lab Troubleshooting | Completed | 2024-11-25 | 3-12-120 | 2 | [197 empty] | call with Cisco | [7 empty] | Done
| 00-01-00-1068 | NDI server connectivity and CIMC configuration. | ACI | Support Activity | Completed | 2025-01-10 | 2025-01-17 | 3 | [243 empty] | Yes |  |  |  | Yes |  |  | Yes
| 30-11-24-1069 | JAMSHEDPUR MCN ¦ 100Mn UPF ¦ observed time difference ¦ NTP in SYNC | ACI | Production Troubleshooting | Completed | 2024-11-30 | 2024-11-30 | 1 | [202 empty] | Observation shared.
| 29-11-24-1070 | Jamnagar OpenStack DRA cluster and DNS reachability issue. | ACI | Lab Troubleshooting | Completed | 2024-11-29 | 2024-11-29 | 1 | [201 empty] | Done
| 29-11-24-1071 | LACP issue in Bangalore_Peenya_MCN UPF. | ACI | Production Troubleshooting | Completed | 2024-11-29 | 2024-11-29 | 1 | [201 empty] | Done
| 28-11-24-1072 | AWS subnet reachability from spirent. | NXOS | Provisioning and Configuration | Completed | 2024-11-28 | 2024-11-28 | 1 | [200 empty] | Done
| 28-11-24-1073 | OOB and CIMC connectivity of Cisco NDI | ACI | Provisioning and Configuration | Completed | 2024-11-28 | 2024-11-28 | 1 | [200 empty] | Done
| 25-11-24-1074 | Reachability issue for User Space TCP/IP Suite | ACI | Lab Troubleshooting | Completed | 2024-11-25 | 2024-11-25 | 1 | [197 empty] | Done
| 25-11-24-1075 | Review of NDI HLD. | ACI | Documentation | Completed | 2024-11-25 | 2024-11-25 | 1 | [197 empty] | done
| 27-11-24-1076 | Netsweeper ip reachability issue. | ACI | Lab Troubleshooting | Completed | 2024-11-27 | 2024-11-27 | 1 | [199 empty] | Done
| 21-11-24-1077 | SCP to IOT network reachability. | ACI | Provisioning and Configuration | Completed | 2024-11-21 | 2024-11-21 | 1 | [193 empty] | Done
| 14-10-24-1078 | Support for NXOS 10.5.1 image Testing for AI/ML fabric. | NXOS | Support Activity | Completed | 2024-10-14 | 2024-10-28 | 4 | [186 empty] | Yes | [7 empty] | Yes |  |  | Yes |  |  | done
| 23-10-24-1079 | JCA and HSS reachability issue. | ACI | Lab Troubleshooting | Completed | 2024-10-23 | 24-20-24 | 2 | [170 empty] | Yes | Yes
| 13-01-25-1200 | Reachability between HyperLite Setup UDM API IP from SoRAF1 & 2 in Replica. | ACI | Provisioning and Configuration | Completed | 2025-01-13 | 2025-01-13 | 1 | [246 empty] | Reachability done.
| 14-01-25-1201 | Jio 5G-CN PoC on AWS ¦¦ IPv4 and Ipv6 Pools required for connectivity with AWS | ACI | Provisioning and Configuration | Completed | 2025-01-14 | 2025-01-14 | 1 | [247 empty] | Reachability done.
| 15-01-25-1202 | Troubleshooting replical lab access issue. | NXOS | Lab Troubleshooting | Completed | 2025-01-15 | 2025-01-15 | 1 | [248 empty] | Done
| 15-01-25-1203 | Unable to SSH into AMD Servers | ACI | Lab Troubleshooting | Completed | 2025-01-15 | 2025-01-15 | 1 | [248 empty] | Done
| 16-01-25-1204 | Ciena_Server reachability issue | ACI | Lab Troubleshooting | Completed | 2025-01-16 | 2025-01-16 | 1 | [249 empty] | Observation shared.
| 17-01-25-1205 | UE to UDG server reachability issue. | ACI | Lab Troubleshooting | Completed | 2025-01-17 | 2025-01-17 | 1 | [250 empty] | Done
| 2025-01-20 | High traffic loss observed during switch reload for DPI L1 PBR solution issue troubleshooting with TAC | ACI | Lab Troubleshooting | Completed | 2025-01-20 | 2025-03-25 | 7 | [253 empty] | Yes | [7 empty] | Yes | [13 empty] | Yes | yes | [33 empty] | yes |  |  | yes |  |  |  | yes
| 21-01-25-1317 | Cable Requirement : Network Connectivity for LIC Setup (Boston) | NXOS | Support Activity | Completed | 2025-01-21 | 2025-01-22 | 2 | [254 empty] | yes | yes
| 22-01-25-1318 | Supoort IP-MPLS team for PO flap issue with 3K and SAR. | NXOS | Support Activity | Completed | 2025-01-22 | 2025-01-23 | 2 | [255 empty] | Yes | yes
| 27-01-25-1319 | LAB SFW to Replica vDRA Conncetivity | ACI | Provisioning and Configuration | Completed | 2025-01-27 | 2025-01-27 | 1 | [260 empty] | yes
| 28-01-25-1320 | Issue: RA-32 not pingable from windows server. | ACI | Lab Troubleshooting | Completed | 2025-01-28 | 2025-01-28 | 1 | [261 empty] | yes
| 29-01-25-1321 | SASE Dev Set Data Plane traffic Mirroring | ACI | Support Activity | Completed | 2025-01-29 | 2025-02-03 | 3 | [262 empty] | yes | yes |  |  |  | yes
| 30-01-25-1322 | support IP-MPLS team to check default route behaviour in RJIL-IP-MGMT vrf on BL side. | ACI | Support Activity | Completed | 2025-01-30 | 2025-01-31 | 0
| 31-01-25-1323 | Support IP-MPLS team for IXIA setup from ACI end. | ACI | Lab Troubleshooting | Completed | 2025-01-31 | 2025-01-31 | 1 | [264 empty] | yes
| 31-01-25-1324 | Issue of not receiving user mirrored traffic on netsweeper server. | ACI | Lab Troubleshooting | Completed | 2025-01-31 | 2025-01-31 | 1 | [264 empty] | yes
| 03-02-25-1325 | Support for vCGNAT setup readiness in openshift cloud. | ACI | Provisioning and Configuration | Completed | 2025-02-03 | 2025-02-07 | 3 | [267 empty] | yes | yes |  |  | yes
| 10-02-25-1326 | NDI NBI integration with SIT | ACI | Lab Troubleshooting | Completed | 2025-02-10 | 2025-02-26 | 4 | [274 empty] | yes | yes |  |  | yes | [11 empty] | yes
| 13-02-25-1327 | Reachability issue between 5G Probe1/Probe2 and SCP | ACI | Lab Troubleshooting | Completed | 2025-02-13 | 2025-02-13 | 1 | [277 empty] | yes
| 14-02-25-1328 | Discussion on Jio VAILS solution and IP requirement. | ACI | Support Activity | Completed | 2025-02-14 | 2025-02-14 | 1 | [278 empty] | yes
| 14-02-25-1329 | Support for SASE Dev Data Plane Server Readiness for forwarding both uplink and downlink traffic. | ACI | Lab Troubleshooting | In Progress | 2025-02-14 |  | 2 | [278 empty] | yes |  |  | yes
| 17-02-25-1330 | Reachability issue of Ram2 board. | ACI | Lab Troubleshooting | Completed | 2025-02-17 | 2025-02-18 | 2 | [281 empty] | yes | yes
| 18-02-25-1331 | packet loss/latency on 2405:200:1410:2d0:15:1551:27:101/102 AGW IP's. | ACI | Lab Troubleshooting | Completed | 2025-02-18 | 2025-02-19 | 2 | [282 empty] | yes | yes
| 19-02-25-1332 | Jio Enterprise Gateway Handover ¦¦ Delhi Vikaspuri AG3 ¦¦ UPF Cluster 7 HPE Servers packet loss issue with repo server. | ACI | Production Troubleshooting | Completed | 2025-02-19 | 2025-02-19 | 1 | [283 empty] | server side issue
| 19-02-25-1333 | Discussion on the requirement of UTGW solution. | ACI | Support Activity | Completed | 2025-02-19 | 2025-02-19 | 1 | [283 empty] | yes
| 19-02-25-1334 | SCP AI solution requirement discussion. | ACI | Support Activity | Completed | 2025-02-19 | 2025-02-20 | 2 | [283 empty] | yes | yes
| 21-02-25-1335 | SCP AI solution document prepartion. | ACI | Documentation | Completed | 2025-02-21 | 2025-02-28 | 2 | [285 empty] | yes |  |  | yes
| 21-02-25-1336 | Reachability Jio VAILS OAM ip's from IOT network. | ACI | Provisioning and Configuration | Completed | 2025-02-21 | 2025-02-21 | 1 | [285 empty] | yes
| 24-02-25-1337 | Reachability between Replica and UAP server | ACI | Provisioning and Configuration | Completed | 2025-02-24 | 2025-02-24 | 1 | [288 empty] | yes
| 24-02-25-1338 | Reachability between CLMS and ISNG. | ACI | Lab Troubleshooting | Completed | 2025-02-24 | 2025-02-25 | 2 | [288 empty] | yes | yes
| 25-02-25-1339 | Replica NTP IP is not reachable from the Jio VAILS servers | ACI | Provisioning and Configuration | Completed | 2025-02-25 | 2025-02-26 | 2 | [289 empty] | yes | yes
| 26-02-25-1340 | Troubleshooting downlink traffic issue from spirent. | ACI | Lab Troubleshooting | Completed | 2025-02-26 | 2025-02-27 | 2 | [290 empty] | yes | yes
| 27-02-25-1341 | Internet access for jiobrain server. | ACI | Provisioning and Configuration | Completed | 2025-02-27 | 2025-02-27 | 1 | [291 empty] | provided
| 27-02-25-1342 | Ensuring CGNAt licensing status for Jio brain server internet access. | ACI | Support Activity | Completed | 2025-02-27 | 2025-02-27 | 1 | [291 empty] | yes
| 28-02-25-1343 | VLAN 3921 GW is not reachable from the server | ACI | Lab Troubleshooting | Completed | 2025-02-28 | 2025-02-28 | 1 | [292 empty] | yes
| 03-03-25-1344 | Packet loss issue in Sambalpur UPF. | ACI | Production Troubleshooting | Completed | 2025-03-03 | 2025-03-03 | 1 | [295 empty] | server end issue
| 04-03-25-1345 | UE SYN packets are not getting forwarded from PGW to F5. | ACI | Lab Troubleshooting | Completed | 2025-03-04 | 2025-03-04 | 1 | [296 empty] | wrong ue pool used.
| 05-03-25-1346 | CN-MMP And SIT reachability. | ACI | Support Activity | Completed | 2025-03-05 | 2025-03-14 | 4 | [297 empty] | yes | yes | [6 empty] | yes | yes
| 06-03-25-1347 | reachability b/w vmme to Spirent TS45E and 46E | ACI | Lab Troubleshooting | Completed | 2025-03-06 | 2025-03-06 | 1 | [298 empty] | yes
| 06-03-25-1348 | ASBC reachability issue from remote location like Coimbatore MCN,Madurai MCN, Salem, Chennai Siruseri AG3. | ACI | Production Troubleshooting | Completed | 2025-03-06 | 2025-03-06 | 1 | [298 empty] | routing issue for Asbc subnets
| 07-03-25-1349 | R5 AWS UPF bgp route advertisement issue. | ACI | Lab Troubleshooting | Completed | 2025-03-07 | 2025-03-08 | 2 | [299 empty] | yes | Martian Prefixes used.
| 10-03-25-1350 | Dual connectivity for UPF CP server in HL2 setup. | ACI | Support Activity | Completed | 2025-03-10 | 2025-03-11 | 2 | [302 empty] | yes | yes
| 11-03-25-1351 | Discussion on MACSec from ACI. | ACI | Support Activity | Completed | 2025-03-11 | 2025-03-11 | 1 | [303 empty] | yes
| 17-03-25-1352 | Route optimalization for RJIL-CORE-MGMT To RJIL-IP-MGMT Peering | ACI | Support Activity | Completed | 2025-03-17 | 2025-03-18 | 2 | [309 empty] | yes | yes
| 24-03-25-1353 | Repo server creation and DCAP container image deployment in Kubernetes cluster. | ACI/NXOS | Support Activity | In Progress | 2025-03-24 | 2025-03-28 | 4 | [316 empty] | yes | yes |  | yes | yes
| 26-03-25-1354 | support for upf BGP association break alarm | ACI | Lab Troubleshooting | Completed | 2025-03-26 | 2025-03-28 | 2 | [319 empty] | yes | yes
| 17-03-25-1355 | Simnovas app server data not working issue. | ACI | Lab Troubleshooting | Completed | 2025-03-17 | 2025-03-18 | 2 | [309 empty] | yes | yes

## Referance
Activity Type | Node Name | Status | Owner | Team
New Product Validation | ACI | In Progress | Abhijeet | IPSE
Pluggables Testing | NXOS | Completed | Shweta | IPSE
Regression Testing | DCNM | Yet to start | Gurkirat | IPSE
MoP Validation | NDO | On Hold | Konda | IPSE
Solution Testing | CGNAT |  | Sairam | IPSE
Feature Testing | CPNR |  | Kazi | Telco
Provisioning and Configuration | CLMS |  | Sumit | Telco
Issue Analysis & Testing | TWAMP |  | Neelmani | Telco
Infosec Testing | Splunk |  | Dilpreet | Telco
Audit and Analysis | DNS |  | Ronak | Telco
Support Activity | SSM
Documentation | ISE
ATP 1A | Arbor
ATP 1B | CGNAT LC
Other | Telemetry
Release Testing | DCNM/NXOS
Lab Troubleshooting | ACI/NXOS
Production Troubleshooting | Other Domain