## Referance (hidden)
Activity Type | Node Name | Status | Owner | Team
New Product Validation | ACI | In Progress | Abhijeet | IPSE
Pluggables Testing | NXOS | Completed | Shweta | IPSE
Regression Testing | DCNM | Yet to start | Gurkirat | IPSE
MoP Validation | NDO | On Hold | Konda | IPSE
Solution Testing | CGNAT |  | Sairam | IPSE
Feature Testing | CPNR |  | Kazi | Telco
Provisioning and Configuration | CLMS |  | Sumit | Telco
Issue Analysis & Testing | TWAMP |  | Neelmani | Telco
Infosec Testing | Splunk |  | Dilpreet | Telco
Audit and Analysis | DNS |  | Ronak | Telco
Support Activity | SSM
Documentation | ISE
ATP 1A | Arbor
ATP 1B | CGNAT LC
Other | Telemetry
Release Testing | DCNM/NXOS
Lab Troubleshooting | ACI/NXOS
Production Troubleshooting | Other Domain

## Ronak
| Completed | In Progress | On Hold | Total
| 184 | 4 | 1 | 189
SN | Activity ID | Activity | Node Name | Activity Type | Status | Start date | End Date | Duration | 2024-01-11 | 2024-01-12 | 2024-01-15 | 2024-01-16 | 2024-01-17 | 2024-01-18 | 2024-01-19 | 2024-01-23 | 2024-01-24 | 2024-01-25 | 2024-01-29 | 2024-01-30 | 2024-01-31 | 2024-02-01 | 2024-02-02 | 2024-02-05 | 2024-02-06 | 2024-02-07 | 2024-02-08 | 2024-02-09 | 2023-02-12 | 2024-02-13 | 2024-02-14 | 2024-02-15 | 2024-02-16 | 2024-02-19 | 2024-02-20 | 2024-02-21 | 2024-02-22 | 2024-02-23 | 2024-02-26 | 2024-02-27 | 2024-02-28 | 2024-02-29 | 2024-03-01 | 2024-03-04 | 2024-03-05 | 2024-03-06 | 2024-03-07 | 2024-03-08 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-05-02 | 2024-05-03 | 2024-05-06 | 2024-05-07 | 2024-05-08 | 2024-05-09 | 2024-05-10 | 2024-05-13 | 2024-05-15 | 2024-05-16 | 2024-05-17 | 2024-05-21 | 2024-05-22 | 2024-05-23 | 2024-05-24 | 2024-05-27 | 2024-05-28 | 2024-05-29 | 2024-05-30 | 2024-05-31 | 2024-06-03 | 2024-06-04 | 2024-06-05 | 2024-06-06 | 2024-06-07 | 2024-06-10 | 2024-06-11 | 2024-06-12 | 2024-06-13 | 2024-06-14 | 2024-06-17 | 2024-06-18 | 2024-06-19 | 2024-06-20 | 2024-06-21 | 2024-06-24 | 2024-06-25 | 2024-06-26 | 2024-06-27 | 2024-06-28 | 2024-07-01 | 2024-07-02 | 2024-07-03 | 2024-07-04 | 2024-07-05 | 2024-07-08 | 2024-07-09 | 2024-07-10 | 2024-07-11 | 2024-07-12 | 2024-07-15 | 2024-07-16 | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-22 | 2024-07-23 | 2024-07-24 | 2024-07-25 | 2024-07-26 | 29/7/2024 | 30/7/2024 | time axis 2024-08-01 to 2025-04-18
1 | 17-01-24-69 | N5648 upgrade from 7.3(7)N1(1)b to 7.3(11)N1(1) via SWIM | NXOS | Release Testing | Completed | 2024-01-16 | 2024-01-30 | 4 |  |  |  | Yes | Yes | Yes | [5 empty] | Yes
2 | 25-01-24-77 | Follow up with Jamnagar team for Point to Point Transport Link over Ciena Transport link from Jio Labs to Jamnagar IDC | ACI/NXOS | Support Activity | Completed | 2024-01-01 | 2024-02-08 | 4 | Following up with mail | [5 empty] | Following up with mail | [8 empty] | Following up with mail |  |  | Following up with mail
3 | 12-01-24-2 | Rate limit testing in NXOS to reduce DNS QPS in production network | NXOS | Feature Testing | Completed | 2024-01-11 | 2024-01-12 | 2 | Yes | Yes
4 | 30-01-24-78 | ATP 1B for ACI | ACI | ATP 1B | In progress | 2024-01-12 |  | 106 |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  |  | Yes |  |  | yes | yes |  | 4 batches of ATP have been reviewed |  | 2 batches of ATP have been reviewed |  | 1 batch of ATP has been reviewed |  |  |  | 2 Batches of ATP 1B have been reviewed |  | 3 btches of ATP have been reviewed | [10 empty] | 4 batches of ATP have been reviewed | [13 empty] | 5 batches of ATP 1B have been reviewed | 1 batch of ATP have been reviewed | 4 batches of ATP have been reviewed |  |  | 6 batches of atp have been reviewed | [5 empty] | 7 batches of ATP have been reviewed |  | 6 atp have been reviewed | 12 atp have been reviewed | 8 atp have been reviewed | 2 atp have been reviewed |  |  |  |  | 2 batches of ATP have been reviewed | [6 empty] | 10 Batches have been reviewed |  |  | 5 atp batches have been reviewed | 8 atp batches have been reviewed | 20 ATP batches have been reviewed |  |  |  | 14 batches of ATP have been reviewed |  |  |  | 11 ATP batches have been reviewed | 16 ATP batches have been reviewed | 10 batches of ATP have been reviewed | 5 batches of ATP have been reviewed | 8 batches of ATP have been reviewed |  | 4 batches of ATP have been reviewd |  |  | 17 batches of atp have been reviewed |  | 4 batches of atp reviewd | 4 ATP batches have been reviewed | 3 ATP batches have been reviewed |  | 1 ATP batch have been reviewed |  |  |  |  | 4 batches of ATP have been reviewed |  |  | 2 devices atp have been reviewed |  |  | 5 ATP devices reviewed |  |  |  |  | 4 atp batches have been done |  |  | 2024-08-02: 8 batches of atp have been reviewed; 2024-08-05: 4 atp batches reviewed; 2024-08-06: 8 devices atp have been revieed; 2024-08-13: 9 batches of atp have been reviewed; 2024-08-16: 8 batches of atp have been reviewed; 2024-08-20: 4 batches of atp have been reviewed; 2024-08-21: 7 batches of atp has been reviewed; 2024-08-22: 7 batches of atp have been reviewed; 2024-08-23: 3 batches of ATP have been reviewed; 2024-08-26: 10 batches of ATP have been reviewed; 2024-09-20: 33 batches of ATP have been reviewed; 2024-09-30: 18ATP have been reviewed; 2024-10-10: 34 atp batches have been reviewed; 2024-10-11: 10 atp batches have been reviewed; 2024-10-16: 21 batches of ATP 1B reviewed; 2024-10-21: test cases of ATP 1A and 1B have been done; 2024-10-22: 26 ATP batches reviewed; 2024-10-25: 19 batches of ATP have been reviewed; 2024-11-14: 3 batches of atp have been reviewed; 2024-11-15: 4 batches of atp have been reviewed; 2024-11-21: 2 batches of atp reviewed; 2024-11-25: 14 atp batches reviewed; 2024-11-26: 15 ATP have been reviewed; 2024-11-27: 10 batches of atp have been reviewed; 2024-11-28: 14 batches of atp have been reviewed; 2024-11-29: 21 batches of ATP have been reviewed; 2024-12-02: 9 batches have been reviewed; 2024-12-06: 18 batches have been reviewed; 2024-12-13: ATP -4 batches reviewed; 2024-12-18: 10 atp reviewed; 2024-12-19: 20 atp reviewed; 2024-12-20: 15 atp reviewed; 2024-12-23: 10 batches of atp have been reviewed; 2024-12-24: 15 batches of atp reviewed; 2024-12-26: 10 batches of atp reviewed; 2025-01-13: 15 batches of atp have been revoiewed; 2025-01-14: 13 batches of atp have been reviewed; 2025-01-15: 21 batches of atp have been reviewed; 2025-01-16: 18 batches of atp have been reviewed; 2025-01-17: 7 batches of atp have been reviewed; 2025-01-28: 12 atp batches have been reviewed; 2025-01-30: 10 atp batches have been reviewed; 2025-02-04: 21 atp batches have been reviewed; 2025-02-05: 4 batches of atp have been done; 2025-02-06: 9 batches of atp have been done; 2025-02-07: 3 atp batches have been done; 2025-02-17: 8 atp batches have been done; 2025-02-18: 11 atp batches have been done; 2025-02-19: 4 atp batches have been done; 2025-02-27: 10 batches of ATP have been done; 2025-03-03: 12 batcehs of atp have been done; 2025-03-06: 5 batches of atp have been done; 2025-03-13: 12 batches of atp have been done; 2025-03-18: 3 batches of atp have been done; 2025-03-21: 18 batches of atp have been done; 2025-04-01: 20 devices have been reviewed; 2025-04-02: 13 devices have been checked; 2025-04-03: 18 devices have been checked; 2025-04-04: 7 devices have been reviewed; 2025-04-07: 8 devices have been reviewed; 2025-04-08: 10 devices have been reviewed
5 | 31-01-24-79 | P2P configuration for IIR IP Requirement | ACI | Provisioning and Configuration | Completed | 2024-01-12 | 2024-01-12 | 1 |  | Yes
6 | 31-01-24-80 | IPv6 pool allotment for mgmt 2521 for FCAPS testing | ACI | Provisioning and Configuration | Completed | 2024-01-12 | 2024-01-12 | 2 |  | Yes | [124 empty] | 2024-11-12: 10 batches of atp reviewed
7 | 31-01-24-81 | IPv6 pool allotment for testing CPNR functionality for NA PD | ACI | Provisioning and Configuration | Completed | 2024-01-12 | 2024-01-12 | 1 |  | Yes
8 | 16-01-24-82 | Reachability for BAN JIO IP IIR | ACI | Provisioning and Configuration | Completed | 2024-01-15 | 2024-01-15 | 1 |  |  | Yes
9 | 16-01-24-83 | IPv6 and VLAN id allocation for requirement for RHOSP | ACI | Provisioning and Configuration | Completed | 2024-01-16 | 2024-01-16 | 1 |  |  |  | Yes
10 | 11-01-24-84 | P2P configuration for AMD based SMF QA/System Team Setup in Lab | ACI | Provisioning and Configuration | Completed | 2024-01-18 | 2024-01-18 | 2 | [5 empty] | Yes
11 | 12-01-24-85 | Allocation of ports for Installation of new VM’s for CGNAT | ACI | Provisioning and Configuration | Completed | 2024-01-18 | 2024-01-18 | 1 | [5 empty] | Yes
12 | 12-01-24-86 | IP pool allocation for installation of new VM's for CGNAT | ACI | Provisioning and Configuration | Completed | 2024-01-19 | 2024-01-19 | 1 | [6 empty] | Yes
13 | 12-01-24-87 | P2P configuration for physical connectivity between leaf's management interface s to management TOR | ACI | Provisioning and Configuration | Completed | 2024-01-23 | 2024-01-23 | 1 | [7 empty] | Yes
14 | 12-01-24-88 | IPv6 pool allocation for Secured Call Using QRNG | ACI | Provisioning and Configuration | Completed | 2024-01-23 | 2024-01-23 | 1 | [7 empty] | Yes
15 | 15-01-24-89 | IGF for TOR installation in Jamnagar Replica | ACI | Provisioning and Configuration | Completed | 2024-01-17 | 2024-01-17 | 1 |  |  |  |  | Yes
16 | 16-01-24-90 | P2P configuration for Secured Call Using QRNG | ACI | Provisioning and Configuration | Completed | 2024-01-23 | 2024-01-23 | 2 | [7 empty] | Yes | [118 empty] | 2024-09-11: IBR connectivity from both Leaf has been done
17 | 16-01-24-32 | Working on AI/ML lab setup documentation and BoQ | ACI | Provisioning and Configuration | Completed | 2024-01-24 | 2025-01-17 | 53 | [8 empty] | Yes | [31 empty] | Required physical connectivity have been established | Worked on mgmt cable lab setup | Configuration has been completed and required traffic has been provided on the switch | Worked on spirent for traffic running but licence got expired | Woreked on document part of the project | Worked on the configuration of switches | Worked on the configuration of switches | Worked on the configuration of switches | [9 empty] | Worked on topology and discussed it with cisco team | [6 empty] | Spirent has been moved back to ground floor for other testing |  |  |  | Spirent mgmt ip have been changed | [57 empty] | 2024-08-12: Server movement has been done; 2024-08-13: connectivity has been established; 2024-08-14: connectivity has been established; 2024-08-19: ILO connecyivity has been done; 2024-08-20: OS installation is in progress; 2024-08-21: NDFC issue is under progress but suddeny started to work around 6; 2024-08-22: OS installation under process and ILO reachability has been established; 2024-08-23: OS under process and Mgmt connectivity configuration has been done; 2024-08-26: Mgmt connectivity has been established; 2024-08-27: Raid issue has been raised with particular HP team; 2024-08-28: OS has been installed and mgmt connectivity has been established; 2024-09-13: Reverse route has been configured; 2024-09-23: NXOS 10.5.1 image Testing meeting with Ninad; 2024-09-24: Required changes have been done for static routes on IBR side; 2024-09-25: call with ninad for traffic loss issue; 2024-09-26: required logs have been shared to trace the issue; 2024-09-27: required logs have been uploaded on tech case; 2024-09-30: required issue has been resolved with ninad sir; 2024-10-09: meeting completed for queries; 2024-10-11: PTP making has been completed for AI Fabric testing; 2024-10-14: changes updated in PPT; 2024-10-15: Meet with cisco team regarding queries; 2024-10-16: ixia problem resolved; 2024-10-17: Working on PPT; 2024-10-18: Working on PPT and meet done with cisco team; 2024-10-21: Working on PPT; 2024-10-22: Working on word document; 2024-10-23: PTP work completed; 2024-10-24: Word documentation completed; 2024-11-18: upgrade from 10.5(1) to 10.5(1j); 2024-11-19: ndfc backup working; 2024-11-21: HLD review; 2024-11-22: Backup restore completed; 2024-12-02: HLD has been discussed; 2024-12-03: both switches are upgraded; 2024-12-04: regression testing in progress; 2024-12-05: HLD document has been made; 2024-12-06: HLD has been reviewed; 2024-12-09: regression testing completed and clm released; 2025-01-16: New HLD shared has been reviewed; 2025-01-17: HLD have been updated
18 | 24-01-24-215 | ACI configuratio for new CGNAT VM connectivity for IPv6 IPDR | ACI | Provisioning and Configuration | Completed | 2024-01-24 | 2024-02-28 | 7 | [8 empty] | Yes | Yes | [8 empty] | VLAN pool have been provided and configuration have been in process | Configuration is in progress | Configuration has been completed |  |  | Troubleshooting has been done as gateway was not reachable | [8 empty] | Configuration have been changed in order to establish reachability
19 | 18-01-24-92 | Configuration for Need internet access over HFCL replica setup | ACI | Provisioning and Configuration | Completed | 2024-01-25 | 2024-01-29 | 2 | [9 empty] | Yes | Yes
20 | 19-01-24-93 | Ipv4 and IPv6 pool allotment for JIO Maas Setup in Jamnagar | ACI | Provisioning and Configuration | Completed | 2024-01-29 | 2024-01-29 | 1 | [10 empty] | Yes
21 | 23-01-24-94 | Creating the ACI/NXOS lab topology diagram from SAR onwards | ACI/NXOS | Provisioning and Configuration | Completed | 2024-01-29 | 13/02/2024 | 6 | [10 empty] | Yes |  |  |  | yes | yes | Creation of topology has been completed along with services |  | Updated changes in topology suggested by Naba sir |  |  | Changes have been updated in topology
22 | 23-01-24-95 | Reachability for PTP testing of Ericsson GNB as T-GM in g8275.1 PTP profile | ACI | Provisioning and Configuration | Completed | 2024-01-29 | 2024-01-29 | 1 | [10 empty] | Yes
23 | 17-01-24-96 | P2P configuration for Jio-5G-BR Platform Feature Release v2.0.3 | ACI | Provisioning and Configuration | Completed | 2024-01-31 | 2024-01-31 | 1 | [12 empty] | Yes
24 | 23-01-24-97 | P2P configuration for ILD Voice Solution Deployment in Production - Servers Movement request to JAMNAGAR LAB | ACI | Provisioning and Configuration | Completed | 2024-01-31 | 2024-02-01 | 1 | [12 empty] | Yes
25 | 24-01-24-98 | IPv6 pool allocation for DHCPv6 loopback interface in BNG | ACI | Provisioning and Configuration | Completed | 2024-02-01 | 2024-02-01 | 1 | [13 empty] | Yes
26 | 19-01-24-93 | Ipv4 and IPv6 pool allotment for JIO Maas Setup in Jamnagar | ACI | Provisioning and Configuration | Completed | 2024-01-30 | 2024-02-05 | 2 | [11 empty] | Yes |  |  |  | yes
27 | 07-02-24-114 | Reachability for Jio-5G-BR servers from IOT NMS for Jio-5G-BR Platform Feature Release v2.0. | ACI | Provisioning and Configuration | Completed | 2024-02-07 | 2024-02-07 | 1 | [17 empty] | Configuration have been completed
28 | 07-02-24-115 | Troubleshooting for connectivity between (GCP) Replica EPC to Replica FMS | ACI | Provisioning and Configuration | Completed | 2024-02-07 | 2024-02-07 | 1 | [17 empty] | Configuration have been completed
29 | 07-02-24-116 | Reachability between Lab Mumbai IR to EMS reachability | ACI | Provisioning and Configuration | Completed | 2024-02-07 | 2024-02-07 | 1 | [17 empty] | Configuration have been completed
30 | 09-02-24-136 | P2P configuration for NIP load testing in Replica Setup | ACI | Provisioning and Configuration | Completed | 2024-09-02 | 2024-09-02 | 1 | [19 empty] | Configuration has been completed
31 | 09-02-24-137 | IP pool allocation for Installation IPv4 on 4 servers | ACI | Support Activity | Completed | 2024-09-02 | 2024-09-02 | 1 | [19 empty] | IP pool has been allocated
32 | 13-02-24-152 | P2P configuration for IIR and ESG: Gen10+ Servers requirement | ACI | Provisioning and Configuration | Completed | 2024-02-13 | 2024-02-15 | 3 | [21 empty] | VLAN and IP pool has been allocated and required configuration has been completed | P2P configuration has been done | Reachability issues have been solved
33 | 14-02-24-153 | Configuration for Connection of HP server with ACI | ACI | Provisioning and Configuration | Completed | 2024-02-14 | 2024-02-27 | 4 | [22 empty] | VLAN, Port and Ip pool has been allocated and required configuration has been completed | [6 empty] | Reachability issue have been checked | Reachability issue have been checked | Reachability issue have been resolved
34 | 15-02-24-154 | IP pool requirenment of subscriber pool for new OLT | ACI | Provisioning and Configuration | Completed | 2024-02-15 | 2024-03-07 | 1 | [23 empty] | IP pool has been allocated askwd for traceroute will configure after getting traceroute
35 | 15-02-24-155 | P2P configuration for Replica deployment of Jio MNP | ACI | Provisioning and Configuration | Completed | 2024-02-15 | 2024-02-19 | 2 | [23 empty] | VLAN and IP pool has been allocated |  | P2P has been configured and rechability issues have been resolved
36 | 19-02-24-167 | Testing for cnBNG POC ¦¦ BFD link failover test cases | ACI | Support Activity | Completed | 2024-02-19 | 2024-03-07 | 6 | [25 empty] | Supported in the activity but was not been completed due to issue faced on their side | [30 empty] | Supported in testing |  | Helped in testing | Helped in testing |  | supported in testing | supported in testing
37 | 20-02-24-168 | Reachability to IOT RDP server | ACI | Provisioning and Configuration | Completed | 2024-02-20 | 2024-02-20 | 1 | [26 empty] | Reachability have been done
38 | 21-02-24-182 | ATP-1A | ACI | Provisioning and Configuration | In Progress | 2024-02-21 |  | 13 | [27 empty] | 1 batch of ATP have been submitted | [18 empty] | 2 batches of ATP have been reviewed | [20 empty] | 1 batches of ATP have been reviewed | 4 batches of ATP have been reviewed | [23 empty] | 5 ATPs have been rviewed | [33 empty] | 2024-08-27: 1 batches is under review; 2024-10-22: 1 batch of ATP 1A done and test cases have been shared; 2024-10-25: 1 batch od ATP 1 A reviewed; 2024-12-25: 11 atp batches reviewed; 2024-12-31: 19 atp have been reviewed; 2025-01-08: 10 batches have been reviewed; 2025-01-09: 13 batches hav ebeen reviewed; 2025-01-10: 20 batches have been reviewed
39 | 22-02-24-183 | P2P configuration at TC23 for QRNG REPLICA setup | ACI | Provisioning and Configuration | Completed | 2024-02-22 | 2024-02-22 | 1 | [28 empty] | Configuration has been completed
40 | 23-02-24-184 | IP reachability Requirement for CMA Integration with PCRF | ACI | Provisioning and Configuration | Completed | 2024-02-23 | 2024-02-23 | 1 | [29 empty] | Reverse route has been configured
41 | 22-02-24-176 | APIC L4 installation and compatibility check with new ACI release 5.3(2a) | ACI | Provisioning and Configuration | Completed | 2024-02-26 | 2024-04-04 | 16 | [30 empty] | CIMC configuration has been completed | CIMC upgrade sucessfully completed and 2 apic upgradtion have been completed | 2 APIC have been successfully migrated | Discussed the APIC 3 upgradation process and asked to getit for excess for ip change for testing purpose | Took excess from get and discussed with dilpreet sir for next step | Access issues with GETIT have been resolved | Supported in troubleshooting for APIC-1 | Supported in troubleshooting for APIC-1, Now RMA should be raised as no solution was working | Supported in troubleshooting for APIC-1 | Required logs have been shared | Supported in troubleshooting for APIC-1 |  |  |  |  | Supported the team for the activity performed in the lab to troubleshoot the issue |  |  | Connected them through mail and RMA is done for the APIC |  |  | Replaced APIC have been successfully migrated | 13 test cases have been tested |  | 2 test cases have been tested and report mking is completed
42 | 29-02-24-219 | Details of IXIA ports used in TELCO | ACI | Support Activity | Completed | 2024-02-29 | 2024-02-29 | 1 | [33 empty] | IXIA port details provided to Naba sir
43 | 01-03-24-220 | P2P configuration for Mellanox NiC installation from server 2005 to 2004........SX189955 | ACI | Provisioning and Configuration | Completed | 2024-03-01 | 2024-03-01 | 1 | [34 empty] | P2P configuration have been completed
44 | 01-03-24-221 | P2P configuation for JIO MNP | ACI | Provisioning and Configuration | Completed | 2024-03-01 | 2024-03-01 | 1 | [34 empty] | P2P configuration have been completed
45 | 07-03-24-252 | IPv6 and IPv4 pool allocation for Load Test Setup Readiness for Jamnagar Replica VPC-DI (vEPDG) | ACI | Provisioning and Configuration | Completed | 2024-03-07 | 2024-03-07 | 1 | [38 empty] | IP pool has been allocated
46 | 14-03-24-270 | P2P configuration for 2 Dell R640 Server in LAB for vMRF | ACI | Provisioning and Configuration | Completed | 2024-03-14 | 2024-03-14 | 1 | [43 empty] | Configuration has been completed
47 | 19-03-24-331 | IP pool allocation and P2P configuration for F5 for Jio in-house MNP integration | ACI | Provisioning and Configuration | Completed | 2024-03-19 | 2024-03-19 | 1 | [46 empty] | Pool allocationa nd configuration has been completed
48 | 22-03-24-332 | Reachability for communication between server to AMD server | ACI | Provisioning and Configuration | Completed | 2024-03-22 | 2024-03-28 | 3 | [49 empty] | Issue have been discussed and required details have been shared | Issue have been discussed and asked for other than provided IP's to check for the issue |  | Reachability between provided source and destination have been checked
49 | 26-03-24-333 | IP pool allocation for NIP servers for running HDFS cluster | ACI | Provisioning and Configuration | Completed | 2024-03-26 | 2024-03-26 | 1 | [50 empty] | Ip pool has been allocated and required configuration has been completed
50 | 29-03-24-334 | IP pool allocation and P2P configuration for installation of new VMs for splunk on Mumbai setup | ACI | Provisioning and Configuration | Completed | 2024-03-29 | 2024-03-29 | 1 | [53 empty] | IP pool allocation and configuration has been completed
51 | 14-03-24-281 | Audit for NXOS site in Production | ACI/NXOS | Audit and Analysis | On Hold | 2024-04-01 |  | 2 | [54 empty] | 4 sites audit completed | 10 sites audit completed
52 | 03-04-24-335 | Daily utilization report for all the switches installed for LIC setup | ACI | Other | Completed | 2024-04-03 | 2024-04-12 | 8 | [56 empty] | Report has been sent | Report has been sent | Report has been sent | Report has been sent | Report has been sent | Report has been sent | Report has been sent | Report has been sent
53 | 05-04-24-348 | Documentation making for Low loss, low latency and scalable throughput | ACI | Documentation | Completed | 2024-04-05 | 2024-04-12 | 6 | [58 empty] | Documentation making is in progress | Documentation making is in progress | Documentation making is in progress | Documentation making is in progress | Documentation making is completed | Document has been shared
54 | N/A | Activity list making | ACI | Documentation | Completed | 2024-04-05 | 2024-04-08 | 2 | [58 empty] | activity list making is in progress | activity list making has been completed
55 | 09-04-24-465 | IP pool and VLAN allocation for Replica for N9 / ENTP for Enterprise Solution | ACI | Provisioning and Configuration | Completed | 2024-04-09 | 2024-04-09 | 1 | [60 empty] | IP pool and VLAN allcation has been done and required configuration also completed
56 |  | IP Pool allocation for BTAS Expansion in KA Circle | ACI | Provisioning and Configuration | Completed | 2024-04-09 | 2024-04-09 | 1 | [60 empty] | Configuration has been completed
57 | 10-04-24-466 | VRF configuration changes for Ericsson ENM IP reachable over UE pool | ACI | Provisioning and Configuration | Completed | 2024-04-10 | 2024-04-10 | 1 | [61 empty] | Configuration has been completed
58 | 10-05-24-467 | IP pool allocation and P2P configuration for OS installation for SBC Project | ACI | Provisioning and Configuration | Completed | 2024-05-10 | 2024-05-10 | 2 | [69 empty] | Configuration has been completed | [21 empty] | Required reachability has been done
59 | 13-05-24-468 | IGF documentation for Jamnagar TOR | ACI | Provisioning and Configuration | Completed | 2024-05-13 | 2024-05-13 | 1 | [71 empty] | Documentation has been done
60 | 16-05-24-469 | OOB MGMT connectivity of Bangalore ACI fabric | ACI | Provisioning and Configuration | Completed | 2024-05-16 | 2024-07-18 | 4 | [73 empty] | BGLR ACI fabric not connected ports have been checked physically in lab | connectivity is in progress, pending to Infra team | Went to lab for updated connectivity checking, connector issue is there | [41 empty] | connector got and connectivity has been established
61 | 22-05-24-503 | P2P configuration for new TOR registered at JMNG ¦¦ SH10 ¦¦ IGF-29 ¦¦ JIOLABS_5GCN | ACI | Provisioning and Configuration | Completed | 2024-05-22 | 2024-05-22 | 1 | [76 empty] | configuration has been completed
62 | 22-05-24-504 | Troubelshooting for Interface Down Issue¦¦SX1908824 | ACI | Support Activity | Completed | 2024-05-22 | 2024-05-22 | 1 | [76 empty] | issue have been checked
63 | 24-05-24-505 | IP pool allocation for NIP load testing in Replica Setup | ACI | Provisioning and Configuration | Completed | 2024-05-24 | 2024-05-24 | 1 | [78 empty] | Ip pool has been allocated
64 | 28-05-24-506 | Reachability has been done for NIP server | ACI | Provisioning and Configuration | Completed | 2024-05-28 | 2024-05-28 | 1 | [80 empty] | reachabilty have been done
65 | 28-05-24-507 | IP allocation for New product - OSA 5405 - | ACI | Provisioning and Configuration | Completed | 2024-05-28 | 2024-05-28 | 1 | [80 empty] | pool has been allocated
66 | 28-05-24-508 | IP pool and VLAN allocation for SBC MGW VLAN assignment | ACI | Provisioning and Configuration | Completed | 2024-05-28 | 2024-09-02 | 2 | [80 empty] | pool has been allocated | [45 empty] | 2024-09-02: New IP pool has been allocated
67 | 29-05-24-509 | IP pool allocation for Kickstart RHEL-9 OS installation for SBC Project | ACI | Provisioning and Configuration | Completed | 2024-05-29 | 2024-05-29 | 1 | [81 empty] | pool has been allocated
69 | 31-05-24-511 | Reachability for Ramanujan-4 Port down | ACI | Lab Troubleshooting | Completed | 2024-05-31 | 2024-06-10 | 2 | [83 empty] | Troubleshooting has been done | Troubleshooting has been done
70 | 15-05-24-530 | CIMC upgradation via SWIM readiness and Pre requisite on LAB | ACI | Solution Testing | Completed | 2024-05-15 | 2024-06-12 | 6 | [85 empty] | Setup has been done at Mumbai fabrica for L2 and bangalore fabrica for L3 | Mumbai fabrica CIMC 1 aand 2 has been upgraded | Mumbai fabrica CIMC 3 and CIMC2 of L3 has been upgraded |  | regression testing has been started for L2 | regression testing has been in progress for L2 | regression testing has been completed for L2
71 | 13-06-24-547 | P2P configuration for Nokia Enterprise Solution | ACI | Provisioning and Configuration | Completed | 2024-06-13 | 2024-06-13 | 3 | [92 empty] | Configuration has been done |  |  |  |  | Required changes in P@P have bee done |  | Reachability has been done
72 | 12-06-24-548 | IPv4 pool allocation for EAS testing | ACI | Provisioning and Configuration | Completed | 2024-06-12 | 2024-06-12 | 1 | [91 empty] | pool has been allocated
73 | 17-06-24-561 | CGNAT failover scenario testing for IPDR on F5 VNF | ACI | Support Activity | Completed | 2024-06-17 | 2024-07-22 | 1 | [89 empty] | supported in the activity |  |  |  |  | Supported in the activity | [12 empty] | Supported in testing |  |  |  | Support has been provided | [5 empty] | IP pool and VLAN has been allocated |  | IP pool and VLAN has been allocated
74 | 20-06-24-562 | HF4 Node reachability from the RDP-2405:201:fffb:94::1626 | ACI | Lab Troubleshooting | Completed | 2024-06-20 | 2024-06-20 | 1 | [97 empty] | reachability has been done
75 | 20-06-24-563 | IPv4 Allocation for JIONMS server in Jamnagar Replica | ACI | Provisioning and Configuration | Completed | 2024-06-20 | 2024-06-20 | 1 | [97 empty] | configuration has been done
76 | 18-06-24-564 | Configuration for Mellanox MCX623106AS-CDAT Ethernet 100Gb NIC for vCGN in QA | ACI | Provisioning and Configuration | Completed | 2024-06-18 | 2024-06-18 | 1 | [95 empty] | configuration and port details has been done
77 | 24-06-24-584 | Reverse route configuration for JIONMS server in Jamnagar Replica | ACI | Provisioning and Configuration | Completed | 2024-06-24 | 2024-06-24 | 1 | [99 empty] | route has been configured
78 | 24-06-24-585 | IGF documentation for JMNGR TOR | ACI | Provisioning and Configuration | Completed | 2024-06-24 | 2024-06-25 | 2 | [99 empty] | IGF document has been in making | Excel has been updated
79 | 25-06-24-643 | Reachability between 10.64.229.240/32 and (10.64.253.180/24 and 10.64.239.176/29) | ACI | Provisioning and Configuration | Completed | 2024-06-25 | 2024-06-25 | 1 | [100 empty] | reachability has been done
80 | 27-06-24-644 | Reverse route configuration for Airspan ACP SR21 Prerelease sanity at RJIL QA lab | ACI | Provisioning and Configuration | Completed | 2024-06-27 | 2024-06-27 | 1 | [102 empty] | configuration has been done
81 | 03-07-24-645 | Reachability for DBIQ replica setup and FMS IOT Environment | ACI | Provisioning and Configuration | Completed | 2024-07-03 | 2024-07-03 | 1 | [106 empty] | have been checked
82 | 24-06-24-646 | Supported in SWIM readiness Pre requisite on LAB | ACI | Support Activity | Completed | 2024-06-24 | 2024-07-03 | 2 | [99 empty] | credentials have been provided | [6 empty] | Completed by establish connectivity
83 | 05-07-24-647 | Report making of TOR migration | ACI | Support Activity | Completed | 2024-07-05 | 2024-08-30 | 2 | [108 empty] | Excel has been made for details of 518 and 568 | [17 empty] | 2024-08-30: For leaf 720 and 750 required configuration detailes have been noted down
84 | 08-07-24-648 | P2P configuration for Jio NIP Replica Set-up | ACI | Provisioning and Configuration | Completed | 2024-07-08 | 2024-07-08 | 1 | [109 empty] | Configuration has been done
85 | 08-07-24-649 | Configuration for Collector-IPDR testing | ACI | Provisioning and Configuration | Completed | 2024-07-08 | 2024-07-15 | 6 | [109 empty] | IP pool and vlan has been allocated | IPMGT vrf is in making at JMNGR ACI | Details for vrf has been shared with IPMPLS team | VRF IP MGMT has been created at JMNGR | P2P has been done |  |  | configuration has been updated
86 | 09-07-24-650 | P2P configuration for Elasticsearch DataCentre Dashboard ( eDCD) Release for NMS/IPM | ACI | Provisioning and Configuration | Completed | 2024-07-09 | 2024-07-09 | 1 | [110 empty] | P2P has been completed
87 | 10-07-24-651 | IP pool allocation for TP-4100 MGMT/Serivce | ACI | Provisioning and Configuration | Completed | 2024-07-10 | 2024-07-10 | 1 | [111 empty] | IP pool has been allocated
1900-03-08 | 29-05-24-510 | P2P configuration for Solution testing for IOT DNS for VPN Services. | ACI | Provisioning and Configuration | Completed | 2024-05-29 | 2024-05-30 | 3 | [81 empty] | IP and VLAN pool has been allocated and required configuration has been done | required NTP IP has been given and reachability has been done | IP pool has been allocated
88 | 10-07-24-652 | IP pool and VLAN allocation, P2P configuration, and reachability for VoLTE with real PCRF on LS | ACI | Provisioning and Configuration | Completed | 2024-07-10 | 2024-07-10 | 1 | [111 empty] | POOL, vlan, P2P and reachability have been provided
89 | 10-07-24-653 | Reverse route configuration for SS-AS and S-CSCS connectivity | ACI | Provisioning and Configuration | Completed | 2024-07-10 | 2024-07-10 | 1 | [111 empty] | Reverse route has been configured
90 | 11-07-24-654 | Documentation of AI Infrastructure Technologies | ACI | Provisioning and Configuration | Completed | 2024-07-11 | 2024-07-24 | 11 | [112 empty] | Working on GenAi |  | Worked on GenAi | Working on documentation | Working on documentation | Working on documentation | Working on documentation | Working on documentation | Working on documentation | Working on documentation |  |  | Worked on presentation of document | Worked on presentation of document
91 | 12-07-24-655 | Failover scenario testing for wireline Fttx IPv6 traffic in Banglore replica for IPDR solution | ACI | Support Activity | Completed | 2024-07-12 | 2024-07-12 | 2 | [113 empty] | Supported in activity | [12 empty] | 2024-08-01: Helped in failover testing
92 | 12-07-24-656 | VLAN and IPv6 Pool allocation, and P2P configuration for SBC MGC setup (TC23-Mumbai) | ACI | Provisioning and Configuration | Completed | 2024-07-12 | 2024-07-12 | 1 | [113 empty] | IP pool and VLAN allocation, and P2P configuration has been done
93 | 15-07-24-657 | F5 CGNAT and IPv6 IPDR for FTTX the cgnat failover scenario testing | ACI | Support Activity | Completed | 2024-07-15 | 2024-07-15 | 6 | [114 empty] | Supported in the activity | [6 empty] | Supported in faiover testing |  |  |  | Helped in failover testing | 2024-08-05: Supported in failover testing; 2024-08-06: supported in the failover testing; 2024-08-07: supported in failover testing
94 | 16-07-24-684 | VLAN and IP pool allocation, and P2P configuration for ACOS 6.0.4 version vallidation for CGNAT and IPv6 IPDR for 5G, FTTX and LTE services on Mellanox 100G NIC cards | ACI | Provisioning and Configuration | Completed | 2024-07-16 | 2024-07-18 | 2 | [115 empty] | vlan and IP Pool has been allocated and P2P has been configured | vlan and IP Pool has been allocated and P2P has been configured for logging and reverse route has also been configuured for RDP reachability
95 | 16-07-24-685 | Reverse route configuration for Airspan Control Platform (ACP) EMS | ACI | Provisioning and Configuration | Completed | 2024-07-16 | 2024-07-16 | 1 | [115 empty] | configured
96 | 22-07-24-686 | IP pool and vlan allocation, and P2P configuration for Kickstart RHEL-9 OS installation for SBC Project ¦¦ 10-04-2024 | ACI | Provisioning and Configuration | Completed | 2024-07-22 | 2024-07-22 | 1 | [119 empty] | Configuration has been done
97 | 06-08-24-751 | First_Floor_MUMBRLB1CSR002_Connectivity check and label verification with proper description | ACI | Provisioning and Configuration | Completed | 2024-08-06 | 2024-08-06 | 1 | [126 empty] | 2024-08-06: description has been provided
98 | 08-08-24-752 | Destination detils for LAB cleanup Activity for B7R12 | ACI | Support Activity | Completed | 2024-08-08 | 2024-08-08 | 1 | [126 empty] | 2024-08-08: proper details have been shared
99 | 08-08-24-753 | IP subnet and P2P configuration for New Servers for Jio PQC Project | ACI | Provisioning and Configuration | Completed | 2024-08-08 | 2024-08-08 | 1 | [126 empty] | 2024-08-08: configurtion has been done
100 | 09-08-24-754 | Jio SBC MGW Media IP's reachability | ACI | Support Activity | Completed | 2024-08-09 | 2024-08-09 | 1 | [126 empty] | 2024-08-09: Reachability has been done
101 | 12-08-24-755 | Reachability for New Servers for Jio PQC Project | ACI | Support Activity | Completed | 2024-08-12 | 2024-08-12 | 1 | [126 empty] | 2024-08-12: reachability has been done
102 | 12-08-24-756 | IP pool and VLAN allocation, P2P configuration has been done for server requirenment in JMNGR | ACI | Provisioning and Configuration | Completed | 2024-08-12 | 2024-08-12 | 1 | [126 empty] | 2024-08-12: configuration has been done and pool has been allocated
103 | 13-08-24-757 | SR 697771758 : RJIL: Border Leaf is getting reloaded again and again | ACI | Provisioning and Configuration | Completed | 2024-08-13 | 2024-08-19 | 1 | [126 empty] | 2024-08-13: RMA has been done
104 | 14-08-24-758 | UP Link detils for Mumbai Fabric | ACI | Support Activity | Completed | 2024-08-14 | 2024-08-14 | 1 | [126 empty] | 2024-08-14: details have been shared
105 | 14-08-24-759 | IP pool allocation for Connectivity between Samsung nodes - Log collector | ACI | Provisioning and Configuration | Completed | 2024-08-14 | 2024-08-16 | 2 | [126 empty] | 2024-08-14: pool has been allocated; 2024-08-16: IP pool has been allocated
106 | 13-08-24-760 | Failover testing for ACOS 6.0.4 version vallidation for CGNAT and IPv6 IPDR for 5G, FTTX and LTE services on Intel 100G NIC cards | ACI | Support Activity | Completed | 2024-08-13 | 2024-08-14 | 2 | [126 empty] | 2024-08-13: supported in activity; 2024-08-14: supported in activity
107 | 16-08-24-794 | Reachability for Jamnagar ENM LAB -- ENM Unity Not reachable | ACI | Support Activity | Completed | 2024-08-16 | 2024-08-16 | 1 | [126 empty] | 2024-08-16: shut unshut has been done
108 | 19-08-24-795 | IP pool allocation for Jio 5G-CN PoC on AW | ACI | Provisioning and Configuration | Completed | 2024-08-19 | 2024-09-03 | 2 | [126 empty] | 2024-08-19: pool has been allocated; 2024-09-03: New Ip pool has been allocated
109 | 20-08-24-796 | Port shut has been done for M274244481//SGH050S93H//RE: One interface is down | ACI | Support Activity | Completed | 2024-08-20 | 2024-08-20 | 1 | [126 empty] | 2024-08-20: Shutown has been done
110 | 20-08-24-797 | IP pool and vlan allocation for IPDR FTTX Design for Netflow // CGNAT Failure | ACI | Provisioning and Configuration | Completed | 2024-08-20 | 2024-08-20 | 1 | [126 empty] | 2024-08-20: IP pool and vlan has been allocated
111 | 21-08-24-798 | P2P configuration and reachability done for SASE Signalling Module Server for replica setup | ACI | Provisioning and Configuration | Completed | 2024-08-21 | 2024-08-21 | 1 | [126 empty] | 2024-08-21: P2P and reachability has been done
112 | 22-08-24-805 | Reachability for connectivity between spirent TS-49 and CCDU UPF | ACI | Lab Troubleshooting | Completed | 2024-08-22 | 2024-08-22 | 1 | [126 empty] | 2024-08-22: route destination has been checked
113 | 27-08-24-806 | IP Pool allocation for new lab setup at TC23 D- wing new facility | ACI | Support Activity | Completed | 2024-08-27 | 2024-08-27 | 1 | [126 empty] | 2024-08-27: Pool has been allocated
114 | 27-08-24-807 | Routes has been checked for YN response for ACS communication in Replica AirFiber network for 960 VLAN | ACI | Support Activity | Completed | 2024-08-27 | 2024-08-27 | 1 | [126 empty] | 2024-08-27: Routes has been checked
115 | 27-08-24-808 | Updated RMA tracker details | ACI | Documentation | Completed | 2024-08-27 | 2024-08-28 | 2 | [126 empty] | 2024-08-27: RMA detils has been updated; 2024-08-28: list has been updtaed and uploaded on telco group
116 | 27-08-24-809 | VLAN GW is Not reachable in Jamnagar Replica | ACI | Support Activity | Completed | 2024-08-27 | 2024-08-27 | 1 | [126 empty] | 2024-08-27: Corresponding VLAN configuration has been checked
118 | 28-08-24-810 | Routes has been checked for N6 Connectivity issue with Spirent Server | ACI | Lab Troubleshooting | Completed | 2024-08-28 | 2024-08-28 | 1 | [126 empty] | 2024-08-28: Destination of routes have been checked
119 |  | NXOS 10.5.1 image Testing | ACI | Solution Testing | Completed | 2024-08-28 | 2024-10-07 | 9 | [126 empty] | 2024-08-29: required issue has been raised with team; 2024-08-30: fabric deployment for AI fabric has been done withthe support of NDFC team; 2024-09-04: Fabric deployement and meeting with romil has been done; 2024-09-06: AI fabric has been deployed; 2024-09-09: Changes in AI fabric deployment has been done; 2024-09-10: Using BGP fabric all configuration deployed on AI fabric; 2024-10-04: regression in progress; 2024-10-07: regression completed; 2024-10-08: regression testing completed
120 | 23-09-24-909 | Migration of multi Tier Leaf 520 and 570 from leaf 401 to direct Spine | ACI | Support Activity | Completed | 2024-09-02 | 2024-09-26 | 3 | [126 empty] | 2024-09-02: Leaf 720 and 770 xml extraction for jamnagar TOR migration; 2024-09-03: Leaf 720 and 770 xml extraction for jamnagar TOR migration; 2024-09-26: Migration of TOR 520 and 570 has been done and required configuration has been pushed back
121 | 03-09-24-910 | IP pool and VLAN allocation for Subscriber Readiness for SASE Testing | ACI | Provisioning and Configuration | Completed | 2024-09-03 | 2024-09-03 | 2 | [126 empty] | 2024-09-03: Pool and vlan has been allocated; 2024-09-27: new pool has been allocated and internet has been provided
122 | 12-09-24-911 | IP pool allocation and P2P configuration for for vPCRF/vDRA at Jamnagar for DL380 | ACI | Provisioning and Configuration | Completed | 2024-09-12 | 2024-09-19 | 6 | [126 empty] | 2024-09-12: IP pool has been allocated; 2024-09-13: IP pool has been allocated; 2024-09-16: IP pool has been allocated; 2024-09-17: IP pool has been allocated; 2024-09-18: p2p has been in progress; 2024-09-19: P2P has been completed
123 | 13-09-24-912 | P2P configuration for SBC MGC ¦¦ Replica setup | ACI | Provisioning and Configuration | Completed | 2024-09-13 | 2024-09-19 | 2 | [126 empty] | 2024-09-13: p2p has been completed; 2024-09-19: P2P has been completed
124 | 17-09-24-913 | IP pool allocation for SASE Signalling Module Server for replica setup | ACI | Provisioning and Configuration | Completed | 2024-09-17 | 2024-09-17 | 1 | [126 empty] | 2024-09-17: IP pool has been allocated
125 | 05-09-24-914 | IP pool allocation for Jio 5G-CN PoC on AWS ¦¦ IPv4 and Ipv6 Pools required for connectivity with AWS | ACI | Provisioning and Configuration | Completed | 2024-09-05 | 2024-09-05 | 1 | [126 empty] | 2024-09-05: IP pool has been allocated
126 | 09-09-24-915 | IPAM portal private IP pool coorection | ACI | Provisioning and Configuration | Completed | 2024-09-09 | 2024-09-10 | 1 | [126 empty] | 2024-09-09: IP pool have been removed from portal
127 | 27-09-24-937 | IP pool and vlan allocated, and P2P configuration for Release for RJio-IPSMGW (Release 4.0.0) | ACI | Provisioning and Configuration | Completed | 2024-09-27 | 2024-10-01 | 2 | [126 empty] | 2024-09-27: Ip pool and vlan aalocation along with configuration has been done; 2024-10-01: required p2p changes done
128 | 01-10-24-938 | P2P configuration for Jio FMS setup in Replica lab | ACI | Provisioning and Configuration | Completed | 2024-10-01 | 2024-10-02 | 2 | [126 empty] | 2024-10-01: Configuration has been done; 2024-10-03: reachability is done
129 | 01-10-24-939 | P2P configuration of server to AMD | ACI | Provisioning and Configuration | Completed | 2024-10-01 | 2024-10-02 | 2 | [126 empty] | 2024-10-01: Configuration has been done; 2024-10-03: changes done
130 | 03-10-24-940 | P2P configuuration for SBC MGW ¦¦ IOT setup | ACI | Provisioning and Configuration | Completed | 2024-10-03 | 2024-10-03 | 1 | [126 empty] | 2024-10-03: Completed p2p
131 | 04-10-24-941 | P2P , IP pool allocation for New Server with New CPU | ACI | Provisioning and Configuration | Completed | 2024-10-04 | 2024-10-15 | 5 | [126 empty] | 2024-10-04: ip pool has been allocated and p2p in progress; 2024-10-07: p2p configuration completed; 2024-10-08: reavhability has been done; 2024-10-09: required changes in p2p completed; 2024-10-15: reachability provided and required changes has been done && new ip pool and P2P has been done
132 | 08-10-24-942 | Migration of multi Tier Leaf 523 and 573 from leaf 401 to direct Spine | ACI | Support Activity | Completed | 2024-10-08 | 2024-10-10 | 3 | [126 empty] | 2024-10-08: excel has been made; 2024-10-09: xml making completed; 2024-10-10: migration is done
133 | 21-10-24-1027 | P2P configuration and IP allocation for New Server with New CPU MR posted | ACI | Provisioning and Configuration | Completed | 2024-10-21 | 2024-10-22 | 2 | [126 empty] | 2024-10-21: P2P has been done; 2024-10-22: IP pool allocated
134 | 21-10-24-1028 | IP pool allocation for new DNS cache at BGLR fabric | ACI | Provisioning and Configuration | Completed | 2024-10-21 | 2024-10-21 | 1 | [126 empty] | 2024-10-21: Pool has been allocated
135 | 12-11-24-1029 | P2P cofiguration for internet on the below AMF/SMF servers | ACI | Provisioning and Configuration | Completed | 2024-11-12 | 2024-11-12 | 1 | [126 empty] | 2024-11-12: P2P has been configured
136 | 22-11-24-1030 | P2P configuration for Cloud native MMP QA set up | ACI | Provisioning and Configuration | Completed | 2024-11-22 | 2024-12-13 | 3 | [126 empty] | 2024-11-22: Switch registered and downgrade completed; 2024-11-25: Pool allocated and P2P configuration done; 2024-12-05: IPv4 have been allocated; 2024-12-13: required changes has been done
137 | 22-11-24-1031 | Post SAR router reboot BL-SAR link went into channel-err-disabled | ACI | Provisioning and Configuration | Completed | 2024-11-22 | 2024-11-27 | 4 | [126 empty] | 2024-11-22: Switch has been moved to ACI; 2024-11-25: Connectivity established; 2024-11-26: Required testing completed; 2024-11-27: regression testing completed and clm released
138 | 28-11-24-1032 | Configuration for Netscout 5G monitoring solution in Jio Labs ¦¦ Jamnagar I&C - OS I&C | ACI | Provisioning and Configuration | Completed | 2024-11-28 | 2024-11-28 | 1 | [126 empty] | 2024-11-28: NTP ip have been shared
139 | 27-11-24-1033 | P2P configuration for Netsweeper Version upgrade - Infosec compliance | ACI | Provisioning and Configuration | Completed | 2024-11-27 | 2024-11-28 | 2 | [126 empty] | 2024-11-27: Congiration has been done; 2024-11-28: new ip pool and vlan allocated
140 | 28-11-24-1034 | reachability for DNS and VNFM server for RHOSP Cluster Handover - Oracle Jamnagar LAB DRA | ACI | Issue Analysis & Testing | Completed | 2024-11-28 | 2024-11-29 | 2 | [126 empty] | 2024-11-28: Reacability for provieded ip and cloud network is done; 2024-11-29: reacability from DNS server to VNFM server provided
141 | 05-12-24-1035 | P2P has been configured for JIO SBC MGW MEDIA | ACI | Provisioning and Configuration | Completed | 2024-12-05 | 2024-12-05 | 1 | [126 empty] | 2024-12-05: P2P has been configured
142 | 09-12-24-1091 | Reachability for Installation and testing of standalone Site Manager | ACI | Lab Troubleshooting | Completed | 2024-12-09 | 2024-12-09 | 1 | [126 empty] | 2024-12-09: reachability has een provided
143 | 10-12-24-1092 | P2P configurationfor Voice Clarity solution for Jio users with hearing impairment | ACI | Provisioning and Configuration | Completed | 2024-12-10 | 2024-12-10 | 1 | [126 empty] | 2024-12-10: ip pool allocated
144 | 10-12-24-1093 | P2P configuration for Jio and Nokia SBC Testing on Gen11 Servers | ACI | Provisioning and Configuration | Completed | 2024-12-10 | 2024-12-25 | 7 | [126 empty] | 2024-12-10: ip pool allocated; 2024-12-11: ip pool allocated for sbc; 2024-12-12: p2p in progress for sbc; 2024-12-13: p2p completed for sbc; 2024-12-16: p2p in progress for jio sbc; 2024-12-18: p2p has been allocated; 2024-12-25: required pool has been provided
145 | 20-12-24-1094 | Port allocation for for JIO CNSC deployment in Replica Mumbai fabric | ACI | Provisioning and Configuration | Completed | 2024-12-20 | 2024-12-30 | 6 | [126 empty] | 2024-12-20: port has been allocated; 2024-12-23: required subnet and vlan has been allocated; 2024-12-25: required support has been provided for reachability; 2024-12-26: required support has been provided for reachability; 2024-12-27: p2p has been configured; 2024-12-30: required reachability has been provided
146 | 20-12-24-1095 | IP and VLAN allocation for IPSMGW Replica set-up | ACI | Provisioning and Configuration | Completed | 2024-12-20 | 2024-12-20 | 1 | [126 empty] | 2024-12-20: IP pool has been allocated
147 | 23-12-24-1096 | P2P configuration for Cassandra DBIQ Agent at Mumbai replica | ACI | Provisioning and Configuration | Completed | 2024-12-23 | 2024-12-24 | 2 | [126 empty] | 2024-12-23: P2P configuration and vlan has bee allocated; 2024-12-24: reachability has been done
148 | 25-12-24-1097 | Reverse route configuration for Reachability between Dev ILD and Replica STP | ACI | Provisioning and Configuration | Completed | 2024-12-25 | 2024-12-25 | 1 | [126 empty] | 2024-12-25: Reverse route has been configured
149 | 25-12-24-1098 | Documentation for ACI configuration | ACI | Documentation | Completed | 2024-12-25 | 2025-01-02 | 4 | [126 empty] | 2024-12-25: Documentation in progress; 2024-12-26: required changes has been done; 2024-12-27: in progress; 2025-01-02: Documentation completed
150 | 02-01-25-1099 | IP pool and vlan allocation for for Jio MNP+in JMNGR Replica setup | ACI | Provisioning and Configuration | Completed | 2025-01-02 | 2025-01-02 | 1 | [126 empty] | 2025-01-02: IP ppol and vlan has been allocated
151 | 03-01-25-1100 | Reachability between Exfo Media IP and Jio-AGW IP in Mumbai replica | ACI | Provisioning and Configuration | Completed | 2025-01-03 | 2025-01-03 | 1 | [126 empty] | 2025-01-03: reachability has been provided
152 | 06-01-25-1223 | IP and VLAN allocation, and P2P configuration for Netsweeeper version upgrade for infosec compliance | ACI | Provisioning and Configuration | Completed | 2025-01-06 | 2025-01-10 | 4 | [126 empty] | 2025-01-06: IP pool has been allocated; 2025-01-07: vlan has been allocated; 2025-01-08: configuration has been done; 2025-01-10: new required IP pool has been allocated
153 | 07-01-25-1224 | IP pooland valn allocation, P2P configuration for Jio SASE Dev Setup Preparation and integration with 5G Core | ACI | Provisioning and Configuration | Completed | 2025-01-07 | 2025-01-09 | 2 | [126 empty] | 2025-01-07: configuration has been done; 2025-01-09: configuration has been done
154 | 08-01-25-1225 | Port allocation and P2P allocation for CNSC 0.0.5 Production Readiness and server Requirement | ACI | Provisioning and Configuration | Completed | 2025-01-08 | 2025-01-09 | 2 | [126 empty] | 2025-01-08: port has been allocated and configuration has been done; 2025-01-09: reachability has been provided
155 | 07-01-25-1226 | BGP configuration for New Server with New CPU MR posted | ACI | Provisioning and Configuration | Completed | 2025-01-07 | 2025-01-10 | 2 | [126 empty] | 2025-01-07: configuration has been done; 2025-01-10: reachability has been provided
156 | 09-01-25-1227 | GW to GW reachability for JIO MNP | ACI | Provisioning and Configuration | Completed | 2025-01-09 | 2025-01-09 | 1 | [126 empty] | 2025-01-09: reachability has been provided
157 | 10-01-25-1228 | IPv4 pool allocation for old Gen10 SLF setup | ACI | Provisioning and Configuration | Completed | 2025-01-10 | 2025-01-10 | 1 | [126 empty] | 2025-01-10: pool has been allocated
158 | 13-01-25-1229 | IP Pool allocation for HFCL testing | ACI | Provisioning and Configuration | Completed | 2025-01-13 | 2025-01-13 | 1 | [126 empty] | 2025-01-13: pool has been allocated
159 | 14-01-25-1230 | P2P configuration for ilo at JMNGR | ACI | Provisioning and Configuration | Completed | 2025-01-14 | 2025-01-14 | 1 | [126 empty] | 2025-01-14: P2P has been configured
160 | 29-01-25-1275 | IP pool allocation for JIO SASE Load Setup Readiness | ACI | Provisioning and Configuration | Completed | 2025-01-29 | 2025-01-29 | 1 | [126 empty] | 2025-01-29: pool has been allocated
161 | 29-01-25-1276 | IP pool allocation for AMRs connectivity with CMR7 | ACI | Provisioning and Configuration | Completed | 2025-01-29 | 2025-01-29 | 1 | [126 empty] | 2025-01-29: pool has been allocated
162 | 29-01-25-1277 | Reachability for LLM Inference Poc at BGLR fabric | ACI | Provisioning and Configuration | Completed | 2025-01-29 | 2025-01-29 | 1 | [126 empty] | 2025-01-29: reachability issue has been resolved
163 | 31-01-25-1278 | P2P configuration for Evaluation of Intel and AMD Servers from HP and Dell | ACI | Provisioning and Configuration | Completed | 2025-01-31 | 2025-02-03 | 3 | [126 empty] | 2025-01-30: p2p configuration in progress; 2025-01-31: p2p configuration has been completed; 2025-02-03: p2p has been configured
164 | 07-02-25-1279 | P2P configuration for New Jio Project : UTGW | ACI | Provisioning and Configuration | Completed | 2025-02-07 | 2025-02-07 | 1 | [126 empty] | 2025-02-07: p2p has been configured
165 | 10-02-25-1280 | P2P configuration for Jamnagar iLO port | ACI | Provisioning and Configuration | Completed | 2025-02-10 | 2025-02-10 | 1 | [126 empty] | 2025-02-10: p2p has been done
166 | 11-02-25-1281 | Pool, VLAN and port allocation for Ericsson Data Exchange Server Installation | ACI | Provisioning and Configuration | Completed | 2025-02-11 | 2025-02-12 | 2 | [126 empty] | 2025-02-11: port has been allocated; 2025-02-12: vlan and pool has been allocated
167 | 13-02-25-1282 | P2P configuration for REPLICA_Jamnagar ¦¦ Jio-CTAS ¦¦ Jio-SIB ¦¦ Jio-IPSM ¦¦ | ACI | Provisioning and Configuration | Completed | 2025-02-13 | 2025-02-13 | 1 | [126 empty] | 2025-02-13: p2p has been configured
168 | 13-02-25-1283 | P2P configuration for Evaluation of Intel and AMD Servers from HP and Dell | ACI | Provisioning and Configuration | Completed | 2025-02-13 | 2025-02-13 | 1 | [126 empty] | 2025-02-13: p2p has been configured
169 | 12-02-25-1284 | P2P configuration for AWS EKS Anywhere installation for Jio UPF Deployment | ACI | Provisioning and Configuration | Completed | 2025-02-12 | 2025-02-14 | 3 | [126 empty] | 2025-02-12: required configuration has been done; 2025-02-13: changes have been done in configuration; 2025-02-14: new configuration has been done
170 | 19-02-25-1285 | P2P configuration for Server Formatting and OS/Docker Installation for Jio OCS | ACI | Provisioning and Configuration | Completed | 2025-02-19 | 2025-02-19 | 1 | [126 empty] | 2025-02-19: p2p has been done
171 | 19-02-25-1286 | IP pool allocation for checking exhausted IPv4 pool in IPAM portal | ACI | Provisioning and Configuration | Completed | 2025-02-19 | 2025-02-19 | 1 | [126 empty] | 2025-02-19: pool has been allocated
172 | 20-02-25-1287 | IP pool and vlan allocation for Jio and Nokia SBC Testing on Gen11 Servers | ACI | Provisioning and Configuration | Completed | 2025-02-20 | 2025-02-20 | 1 | [126 empty] | 2025-02-20: pool and vlan has been allocated
173 | 20-02-25-1288 | 400G and 100G breakout testing for new upf server using provided SFP, cables and switches | ACI | Solution Testing | Completed | 2025-02-20 | 2025-03-20 | 21 | [126 empty] | 2025-02-20: required connectivity has been established; 2025-02-21: testing has been done on aci switch; 2025-02-24: testing has been done on aci to nxos switch and observation has been shared; 2025-02-25: new sfp provided are under testing; 2025-02-26: new sfp provided are under testing; 2025-02-27: new sfp provided are under testing; 2025-02-28: new sfp provided are under testing; 2025-03-03: new sfp provided are under testing; 2025-03-04: new servers are under cabling; 2025-03-05: all sfps testing started on new switch; 2025-03-06: all sfps testing started on new switch; 2025-03-07: all sfps testing started on new switch; 2025-03-10: both switches have been upgraded; 2025-03-11: new sfp provided are under testing; 2025-03-12: new sfp provided are under testing; 2025-03-13: new sfp provided are under testing; 2025-03-14: all testing have been done; 2025-03-17: documentation under progress; 2025-03-18: documentation under progress; 2025-03-19: documentation under progress; 2025-03-20: clm released
174 | 21-02-25-1289 | P2P configuration for for Gen 11 replica setup for Jio VAILS | ACI | Provisioning and Configuration | Completed | 2025-02-21 | 2025-02-21 | 1 | [126 empty] | 2025-02-21: P2P has been done
175 | 25-02-25-1290 | Reachability has been provided for SX1921618 // RE: JMNG-DC1-SH10-5R20 port down issue (ens2f0) HGW System installtion | ACI | Provisioning and Configuration | Completed | 2025-02-25 | 2025-02-25 | 1 | [126 empty] | 2025-02-25: reachability has been provided
176 | 25-02-25-1291 | Reachability has been provided TM agent upgrade in Lab and Prod for Telco nodes¦ 6D DNS | ACI | Provisioning and Configuration | Completed | 2025-02-25 | 2025-02-26 | 2 | [126 empty] | 2025-02-25: reachability has been in progress; 2025-02-26: reachability has been done
177 | 26-02-25-1292 | IPv4 pool allocation for the testing of PTP over BVI feature on the NCS540 | ACI | Provisioning and Configuration | Completed | 2025-02-26 | 2025-02-26 | 1 | [126 empty] | 2025-02-26: pool has been provided
178 | 28-02-25-1293 | Reachability has been provided for TM agent upgrade in Lab and Prod for Telco nodes | ACI | Provisioning and Configuration | Completed | 2025-02-28 | 2025-02-28 | 1 | [126 empty] | 2025-02-28: reachabilty has been provided
179 | 03-03-25-1294 | IP pool allocation for Sanmina new Setup IPv4 Required | ACI | Provisioning and Configuration | Completed | 2025-03-03 | 2025-03-03 | 1 | [126 empty] | 2025-03-03: pool has been allocated
180 | 03-03-25-1295 | IP pool allocation for for Multiple Enterprise testing for SASE QA Validation | ACI | Provisioning and Configuration | Completed | 2025-03-03 | 2025-03-03 | 1 | [126 empty] | 2025-03-03: pool has been allocated
181 | 03-03-25-1296 | IP allocation for RHEL 9.5 installation at JMNGR | ACI | Provisioning and Configuration | Completed | 2025-03-03 | 2025-03-03 | 1 | [126 empty] | 2025-03-03: pool has been allocated
182 | 05-03-25-1297 | IP pool allocation to build simulator setup in replica domain | ACI | Provisioning and Configuration | Completed | 2025-03-05 | 2025-03-05 | 1 | [126 empty] | 2025-03-03: pool has been allocated
183 | 13-03-25-1298 | IP pool and vlan allactaion and P2P configuration for Jio and Nokia SBC Testing on Gen11 Servers | ACI | Provisioning and Configuration | Completed | 2025-03-13 | 2025-03-18 | 4 | [126 empty] | 2025-03-13: p2p is in progress; 2025-03-14: p2p is in progress; 2025-03-17: p2p is in progress; 2025-03-18: p2p has been done
184 | 18-03-25-1299 | P2P allocation for AWS EKS Anywhere installation for Jio UPF Deployment | ACI | Provisioning and Configuration | Completed | 2025-03-18 | 2025-03-20 | 3 | [126 empty] | 2025-03-18: p2p is in progress; 2025-03-19: p2p is in progress; 2025-03-20: p2p has been done
185 | 19-02-25-1334 | AUDIT for dual home connectivity | ACI | Provisioning and Configuration | In Progress | 2025-03-24 |  | 2 | [126 empty] | 2025-03-21: all dual home connectivity has been checked; 2025-03-26: there uplink have been noted down
186 | 25-03-25-1301 | AUdit for BD/EPG configuration | ACI | Provisioning and Configuration | In Progress | 2025-03-25 |  | 3 | [126 empty] | 2025-03-25: For BGLR BD EPG check have been started; 2025-03-27: For BGLR BD EPG check have been competed; 2025-03-28: for mumbai audit has been started
187 |  | 400G breakout testing with Huber+Suhner SFP | ACI | Provisioning and Configuration | Completed | 2025-04-08 | 2025-04-18 | 8 | [126 empty] | 2025-04-08: sfp have been tested on switch; 2025-04-10: changes have been made into sfp then have tested; 2025-04-11: for throughput testing setup is established; 2025-04-14: setup is done; 2025-04-15: sfp have been tested which was working fine; 2025-04-16: documentation is in progress; 2025-04-17: documentation have been completed; 2025-04-18: clm released
188 |  | IP pool and vlan allocation and P2P configuration for Jio SBC and SIB production deployment Sync-up | ACI | Provisioning and Configuration | Completed | 2025-04-09 | 2025-04-18 | 6 | [126 empty] | 2025-04-09: ip pool and vlan has been allocated; 2025-04-14: p2p is in progress; 2025-04-15: p2p is in progress; 2025-04-16: p2p is in progress; 2025-04-17: p2p is in progress; 2025-04-18: p2p is completed
189 |  | Reachability provided from New Jio - AI Product: Network Guardian Platform (NGP) | ACI | Provisioning and Configuration | Completed | 2025-04-10 | 2025-04-10 | 1 | [126 empty] | 2025-04-10: reachability has been provided
190 |  | IP pool allocation and P2P configuration for Regarding Storage Requirement of BTAS | ACI | Provisioning and Configuration | Completed | 2025-04-16 | 2025-04-17 | 2 | [126 empty] | 2025-04-16: configuration and pool has been allocated; 2025-04-17: reachanility has been provided
0
0
0